DRAFT  CONTRACT  No. ……...

for

NEK SAFETY UPGRADE PROJECT – PHASE 3

BB2 Project – Engineering, Design and Construction

hereinafter referred to as:

“BB2 Project ”

concluded on __________________  by and between:

NUKLEARNA ELEKTRARNA KRŠKO d.o.o.

Vrbina 12, 8270 Krško, Slovenia, 	
represented and duly authorized by Mr. Stanislav Rožman, President of the Management Board and Mr. Hrvoje Perharić, Member of the Management Board

(hereinafter referred to as "PURCHASER" or "NEK" or "NPP Krško")

on one part

and

………………………………………………………………………………………

represented and duly authorized by ……………………………………........

(hereinafter referred to as "SELLER" or “Contractor”)

on the other part

Whereas, SELLER represents that it is fully qualified to provide  PURCHASER  with  the turnkey Project “BB2 Project – Engineering, Design and Construction” and shall do so in accordance with the terms and conditions herein specified,

and

Whereas, the representatives of SELLER and PURCHASER possess proper and sufficient authority to agree, and

Now therefore, SELLER and PURCHASER have agreed as follows:

Subject of the Contract: NEK Safety Upgrade Project  Phase 3,  BB2 Project – Engineering, Design and Construction

The following documents shall constitute the Contract:

-  PART I: -  General Terms and Conditions (this Document)

- PART II: -  NEK Technical Specification No. SP-ES5115, Rev. 0  for

NEK Safety Upgrade Project – Phase 3, BB2 Project –

Engineering, Design and Construction (hereinafter

referred to as “SP-ES5115”)

-  PART III:  - Quotation   No. ……………….

PART I - GENERAL TERMS AND CONDITIONS

# TABLE OF CONTENTS

TABLE OF CONTENTS	3

0	DEFINITIONS AND ABBREVIATIONS	4

1	SELLER'S SCOPE  OF SERVICES AND DELIVERY	8

2	PURCHASER'S RESPONSIBILITIES	9

3	QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS	9

4	DELIVERABLES TO BE PROVIDED TO PURCHASER	9

5	SCHEDULE REQUIREMENTS	9

6	DELIVERY TERMS AND CONDITIONS	10

7	PRICE	11

8	PAYMENT TERMS AND SCHEDULE	12

9	INSPECTIONS, TESTS & HANDOVER PROTOCOL	15

10	LIQUIDATED DAMAGES FOR DELAY	16

11	SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION	17

12	WARRANTY	17

13	T A X E S	19

14	LICENSES, PERMITS AND AUTHORIZATIONS	20

15	INSURANCE AND INDEMNITY	20

16	LIABILITY	21

17	PROPRIETARY INFORMATION	23

18   CLAIMS	  24

19   ARBITRATION	25

20   SUBSTANTIVE LAW	26

21   FORCE MAJEURE	26

22   SUSPENSION OF WORK AND TERMINATION	27

23   CHANGES	32

24   OTHER PROVISIONS	33

25    ASSIGNMENT	34

26    ENTIRE AGREEMENT	34

27    LANGUAGE	34

28    EFFECTIVE DATE OF CONTRACT	35

29    NOTICES	35

30    ATTACHMENTS	35

# DEFINITIONS AND ABBREVIATIONS

As used throughout the Contract, the following terms shall have the meaning set forth hereinafter:

PURCHASER shall mean NUKLEARNA ELEKTRARNA KRŠKO (NPP Krško), Vrbina 12, 8270 Krško, Slovenia, represented by Mr. Stanislav Rožman, President of the Management Board and Mr. Hrvoje Perharić, Member of the Management Board.

SELLER or CONTRACTOR shall mean ………………………………..

…………………………………………………………………………………,represented by ………………………………………………………………

PARTY or PARTIES shall mean PURCHASER or/and SELLER as herein referred to individually or collectively.

CONTRACT shall mean the agreement between PURCHASER and SELLER consisting of General Terms and Conditions of the Contract (PART I), NEK Technical Specification SP-ES5115, Rev.0 (PART II) and Quotation .No.........................

The Contract documents are complementary, and what is called for by anyone of them shall be binding as if called for by all. Any conflicts in the Contract documents shall be reasonably resolved by PURCHASER after mutual discussion with SELLER. The validity dates of documents and any data listed in this Contract shall commence with the effective date of the Contract.

SCOPE OF SERVICES AND DELIVERY or WORK shall mean all engineering and design (per ZGO and NEK ESD procedures), licensing support, construction and construction supervision, procurement and supply of all equipment and material, installation and installation supervision, commissioning of BB2 Project and Start-up testing supervision of all related Safety Upgrade Systems and all other requirements set forth in or necessary to perform the Contract for BB2 Project.

PROJECT  shall mean all activities requested by SP-ES5115, Rev. 0

i.e. by this Contract.

PROJECT MANAGERS shall mean the PURCHASER’s and the SELLER’s designated representatives through whom all technical, commercial, Quality Assurance and Licensing matters shall be channeled.

COMMERCIAL REPRESENTATIVES shall mean the PURCHASER’s and the SELLER’s designated representatives through whom commercial matters will be evaluated.

SP-ES5115 shall mean NEK Technical Specification SP-ES5115 Rev. 0 for BB2 Project – Engineering, Design and Construction  with all design, technical, engineering, QA and other requirements incorporated.

QUOTATION shall mean SELLER’s Quotation No.: ……………………..

dated ………………, 2017.

PLANT, NE Krško, NEK, NPP Krško shall mean Nuclear Power Plant Krško.

SITE shall mean and include the area of the Plant  and its adjacent areas necessary and relevant to the operation of the Plant.

Nuclear Site shall mean the territory of the Nuclear Power Plant, situated in Krško, Slovenia, all within the licensed nuclear site.

APPROVED shall mean the status of any document to be furnished by the SELLER to PURCHASER under Contract which is approved by PURCHASER with or without comments but which is not rejected by PURCHASER. The date for the resolution of PURCHASER’s comments shall be mutually agreed upon prior to the approval. In no circumstances the approval can relieve SELLER from the responsibility for failures within SELLER’s Scope of Services and Delivery.

FIXED AND FIRM TOTAL CONTRACT PRICE  shall mean all inclusive total price to be paid to SELLER as per Article 7.1 of the Contract.

HARDWARE shall mean all equipment, spare parts, consumables and material together with required software needed for BB2 Project.

INSTALLATION AND SERVICE ACTIVITIES shall mean all the activities and measures to successfully install and operate the projects in accordance with the requirements of the NEK procedure ESP 2.619.

MAJOR EQUIPMENT shall mean all equipment as specified in Appendix 22.7 of the SP-ES5115.

MISCELLANEOUS HARDWARE shall mean all equipment (including their installation) as specified in Appendix 22.8 of the SP-ES5115 and other miscellaneous pieces of hardware unknown at the time of Contract signature (including their installation) needed to make the Project physically and functionally complete.

DESIGN shall mean documentation preparation in accordance with NEK ESP 2.602 and all other relevant procedures of the ESP 2.602 under item 2.0

DESIGN DOCUMENTS  shall mean the Specifications and drawings derived from regulatory requirements and/or design, quality assurance, and process requirements for use in the procurement, fabrication, installation, examination and testing; and analyses and reports that substantiate design characteristics or evaluate item performance.

DESIGN BASIS  shall mean the information that identifies the specific functions to be performed by a structure, system or component of a facility, and the specific values or ranges of values chosen for controlling parameters as reference bounds for design. These values may be (1) restraints derived from generally accepted state-of-the art practices for achieving functional goals or (2) requirements derived from the analysis (based on calculation and/or experiments) of the effects of the postulated accident for which a structure, system, or component must meet its functional goals. They may also result from the regulatory requirements or applicable codes and standards.

ENGINEERING shall mean the profession of applying scientific principles to the design, construction, maintenance, and of operation of buildings, equipment and systems.

PROCUREMENT shall mean the provision of all personnel, techniques, services and tools/equipment necessary or appropriate to successfully complete the Project.

INSTALLATION shall mean all activities and measures to successfully install the projects in accordance with the requirements of the NEK procedure ESP 2.619.

START-UP shall mean testing to validate system functionality and performance while operating new equipment.

TURNOVER shall mean activities and documentation signifying that the work required by the plant modification packages has been (installed and tested) in accordance with requirements of the design modification package.

COMMISSIONING shall mean the process by means of which systems and components of facilities and activities, having been constructed, are made operational and verified to be in accordance with the design and to have met the required performance criteria.

ALARA shall mean As Low as Reasonably Achievable.

ASL shall mean Approved Suppliers List

BB1 shall mean existing DG-3 Bunkered Building

BB2 shall mean New Bunkered Building for DEC systems

BOM shall mean Bill of Material

BS shall mean Bunkered System

CDP shall mean Conceptual Design Package

DAT shall mean Delivered at Terminal NPP Krško site as per Incoterms 2010

DEC shall mean Design Extended Conditions

DG shall mean Diesel Generator

DMP shall mean Design Modification Package

ECR shall mean Emergency Control Room

ESD shall mean Engineering Service Division

FAT shall mean Factory Acceptance Testing

IP shall mean Installation Package

PMM shall mean Project Management Manual

PGD shall mean Project for Getting approval for Construction (by ZGO)

PZI shall mean Project for Construction (by ZGO)

PQP shall mean Project Quality Plan

QA shall mean Quality Assurance

SAT shall mean Site Acceptance Testing

SNSA shall mean Slovenian Nuclear Safety Authority

TOP shall mean Turn-Over Package

VAT shall mean Value Added Tax

ZGO shall mean Zakon o Graditvi Objektov  (Slovenian Construction

Code)

ZVISJV shall mean	 Zakon o varstvu pred ionizirajočimi sevanji in

Jedrski varnosti (Radiation Protection and Nuclear Safety Act).

# SELLER'S SCOPE  OF SERVICES AND DELIVERY

SELLER shall perform the BB2 Project fully in accordance with NEK Technical Specification SP-ES5115.

SELLER’s Scope of Services and Delivery includes full scope of Engineering & Design Activities, Civil/Structural, Mechanical, Piping, HVAC, Electrical and I&C on a turnkey basis.

Plant Design Modifications - Engineering and design (per NPP Krško ESD procedures including ESP-2.602) of Safety Upgrade Systems per CDP attached to SP-ES5115  includes  (4) individual DMP’s as follows:

•	1024-BS-L – Construction of BB2 building with support systems

•	1005-SI-L  –  Alternate Safety Injection (ASI)

•	1010-AF-L –  Alternate Auxiliary Feedwater (AAF)

•	1030-EE-L – BB2 Emergency Electrical Power Supply

Within the scope of BB2 Project the following major activities shall be implemented but not strictly limited to the following:

- Preparation of required documentation per Slovenian Construction Code Act – ZGO-1 (to enable PURCHASER to obtain Construction Permit, mod. 1024-BS-L) for:

- Construction pit (protection diaphragm wall and excavation works)

- Construction of BB2 building

- Detailed seismic analysis as defined in Appendix  22.6 of SP-ES5115

- Design per ESP-2.602 (Plant Design Modification) for each of the above listed projects (1024-BS-L, 1005-SI-L, 1010-AF-L and 1030-EE-L)

- Project Implementation:

- BB2 pit excavation

- BB2 building  construction

- Equipment installation

- Project coordination & Quality Assurance

- Licensing support

- Planning & scheduling

- Project Closure

Detailed description of SELLER’s Scope of Services and Delivery is

given in SP-ES5115.

Turnkey principle referred to in this Contract means that any scope needed to meet the requirements of this Contract and to make the subject Project physically and functionally complete shall be considered as SELLER's Scope of Supply and Services, unless clearly specified in Art. 2 below as PURCHASER's  responsibility.

Transfer of title and risk of loss shall pass from SELLER to PURCHASER upon the Handover Protocol (Attachment D) signature by both Parties.

Subcontractors

For part of the Scope of Services and Delivery or Work SELLER may engage the subcontractors which have been listed in the Quotation and accepted by NEK. If SELLER upon signature of this Contract wants to change or select new subcontractor(s), this shall be subject of NEK approval, which shall not be unreasonably withheld. Based on the law of ZVISJV (Act on Protection against Ionizing Radiation and Nuclear Safety) and based on “Pravilnik o dejavnikih sevalne in jedrske varnosti (JV 5)” Article 67, PURCHASER is responsible for establishing surveillance on SELLER and its subcontractors to ensure high quality and nuclear safety for the public.

SELLER shall ensure that all subcontractors meet high standards of competence, experience and capacity in relation to the tasks to be entrusted to them and that they fully comply with the SP requirements.

Full overall responsibility always remains on SELLER’s side concerning participation of SELLER’s subcontractors.

# PURCHASER'S RESPONSIBILITIES

PURCHASER’s responsibilities are defined in  Section 12 of SP-ES5115.

# QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS

SELLER shall meet all quality assurance requirements, design, engineering, and technical requirements as well as procedures, codes and standards as stated in SP-ES5115.

# DELIVERABLES TO BE PROVIDED TO PURCHASER

SELLER shall submit to PURCHASER all deliverables as stated in  SP-ES5115.

# SCHEDULE REQUIREMENTS

Overall Project Schedule is given in Attachment A to this Contract.

Main Schedule Completion Milestones are given in the Table below:

| No. | Description | Duration (months) |
| --- | --- | --- |
| 1 | Contract awarded | T0 |
| 2 | PMM and PQP submittal | T0+1 |
| 3 | Documentation for Construction Pit submittal | T0+6 |
| 4 | Construction Pit completed | T0+11 |
| 5 | Documentation per ZGO submittal | T0+11 |
| 6 | Development of BB2 Floor Response Spectra | T0+11 |
| 7 | a) Start of Building construction b) Completion of Building construction | T0+11 T0+….(max 28) |
| 8 | Equipment specifications submittal | T0+11 |
| 9 | DMPs (all four) submittal | T0+18 |
| 10 | Major Equipment delivery at NEK | T0+33 |
| 11 | IP submittal | T0+24 |
| 12 | - Start of Equipment installation - Completion of Equipment installation | T0+26 T0+46 |
| 13 | Outage installation activities | October 2019, April 2021 |
| 14 | Site Acceptance Test | October 2019, April 2021 |
| 15 | Start-up procedure submittal | TF-3 |
| 16 | TS and USAR Change (approved by SNSA) | T0+24 |
| 17 | Essential Drawings (ESP-2.602) | TF |
| 18 | Operability Declaration (ESP-2.602) | TF |
| 19 | TOP submittal | TF+4 |
| 20 | Project close out | TF+5 |

Note:

T0 = effective date of Contract

TF = April 2021-outage-SAT/SUP completed

Integrated detailed Project Schedule shall be submitted for PURCHASER’s approval within one (1) months upon signature of the Contract as a part of the PMM.

# DELIVERY TERMS AND CONDITIONS

Equipment, spare parts, material and all other deliverables of SELLER’s Scope of Services and Delivery as stated in Art. 1 above shall be delivered DAT  NPP Krško Site as per Incoterms 2010.

Temporary Import to NPP Krško site

SELLER shall organize and perform at its cost all transportation and insurance of all temporarily imported equipment, instruments, material, etc. necessary to perform SELLER’s Scope of Services and Delivery under this Contract to NPP Krško site, return from NEK site and insurance of them also during the stay at NEK site.

Title and risk of loss/or damage to such temporarily imported equipment, tools, etc. shall remain all time with SELLER.

Delivery of shipping documents

As soon as possible, but not later than on the same day of delivery of goods, in order to ensure timely receipt and customs clearance, SELLER or its forwarding agent shall send to PURCHASER the following information and documents:

- estimated time of arrival of shipment at NEK site

- shipping invoice with description of goods, quantity, unit and total price per each item and total price

- packing list

- copy of AWB or RWB or B/L, etc. (relative to means of transportation)

The use of EUR-1 Form for optimizing of customs formalities shall be mandatory whenever feasible.

# PRICE

7.1     The all-inclusive Total  Fixed and Firm Contract Price for the whole

contractual Scope of Services and Delivery as per Art. 1 above, under

the terms and conditions of this Contract is:

EUR  ................................... (excl. V.A.T.)

(in words: ............................................................  Euros)

All labor, materials, equipment, parts, components, and services like engineering and documentation, as well as living, traveling and similar costs of SELLER's personnel, etc. necessary for SELLER to fulfill its obligations as stated in Art. 1 of this Contract  are included in the above Fixed and Firm Total Price.

7.2.   The price structure is given below:

| Item | Scope of Services and Delivery | Fixed price / € (excl. VAT) EU origin | Fixed price /€ (excl. VAT) non EU origin |
| --- | --- | --- | --- |
| 1 | Engineering & Licensing |  |  |
| 2 | Design Total |  |  |
|  | Documentation per ZGO (IDZ, PGD, PZI, PID) |  |  |
|  | Documentation per NEK ESP procedures (DMP) |  |  |
| 3 | Procurement & Manufacturing |  |  |
|  | a) Major Equipment as per tables a) List of Supply of Major Equipment & Prices Proposed by Bidder as the Best Scope of Supply - Subset of Major Equipment Option I or Option II (including recommended spare parts) given in Attachm. 1- Bid Form to Bidding Documentation |  |  |
|  | b) Bidder’s mark-up on supplier’s prices as per item a) above |  |  |
|  | c) Miscellaneous Hardware including installation costs as per tables b) List of Supply of Miscellaneous Hardware including installation costs & contingency costs given in Attachm. 1 – Bid Form to Bidding Documentation |  |  |
| 4 | BB2 Construction Pit (excavation preparation) |  |  |
| 5 | BB2 Construction (1024-BS-L) |  |  |
| 6 | Installation & Commissioning |  |  |
|  | 1005-SI-L modification |  |  |
|  | 1010-AF-L modification |  |  |
|  | 1030-EE-L modification |  |  |
| 7 | Preparation of Turn-over packages and Project closure |  |  |
| 8 | Other services: …………………….. ……………………… ……………………… | ………………….. ………………….. ………………….. | ………………… ………………… ………………… |
|  | TOTAL FIXED AND FIRM CONTRACT PRICE |  |  |

# PAYMENT TERMS AND SCHEDULE

All payments under this Contract will be made by means of a bank transfer, net due thirty (30) days upon PURCHASER approval of the received invoice. The invoice shall be approved or rejected within 15 days from the receipt. If the invoice is not rejected within 15 days from the receipt, it is considered to be approved.

8.1     Payment will be made against commercial invoices, upon receipt of

deliverables as described in the Tables provided below:

Payment Table

| Item | Description of Payment Milestones |  | Payment Amount (% of Fixed and Firm Contract Price) | Estimated Month of Invoice (to be filled by Bidder) |
| --- | --- | --- | --- | --- |
|  | Detailed PMM and PQP for complete Project approved by PURCHASER |  | 2 | T0+ |
|  | Submittal of Conceptual design of BB2 building (IDZ per ZGO) |  | 1 | T0+ |
|  | Documentation submittal per ZGO for BB2 (PGD) |  | 3 | T0+ |
|  | Documentation submittal per ZGO for BB2 (PZI) |  | 3 | T0+ |
|  | Submittal of Procurement Specifications for Major Equipment per SP-ES5115 and PO issued to Suppliers |  | 5 | T0+ |
|  | Design Modification Package 1005-SI-L approved by PURCHASER |  | 5 | T0+ |
|  | Design Modification Package 1010-AF-L approved by PURCHASER |  | 5 | T0+ |
|  | Design Modification Package 1024-BS-L approved by PURCHASER |  | 5 | T0+ |
|  | Design Modification Package 1030-EE-L approved by PURCHASER |  | 5 | T0+ |
|  | Construction pit excavation completed |  | 5 | T0+ |
|  | Major concrete work completed |  | 10 | T0+ |
|  | Basic BB2 installation (electrical & mechanical) per 1024-BS-L completed |  | 5 | T0+ |
|  | Technical inspection per ZGO completed |  | 5 | T0+ |
|  | Major Equipment delivery at NEK site |  | 7 | T0+ |
|  | Successfully completed Installation per 1005-SI-L and 1010-AF-L |  | 10 | T0+ |
|  | Successfully performed SAT for BB2 Project |  | 10 | T0+ |
|  | As Built all drawings and Turn over package (TOP) per ESP-2.611 for all modifications completed |  | 5 | T0+ |
|  | Signature of Handover Protocol per Art. 9 and submittal of Bank Guarantee for Good Performance during the Warranty Period as stated in Art 8.2 below |  | 7 | T0+ |
|  | Resolution of Warranty Issues and signature of the Statement on Successful Completion of the Warranty Inspection (18 months after signature of HOP) as stated in the Attachment E |  | 2 | T0+ |
|  |  | SUM | 100 |  |

Note:

T0 = effective date of Contract

Payment of SELLER's Subcontractors

If the Bidder engages the subcontractor(s) who wants to be paid directly and they submit the signed »Subcontractor’s Data and Bidder’s Consent for Direct Payment« as per Attachment E, NEK is obliged to pay the Subcontractor directly.

Besides the invoice submitted by  SELLER to PURCHASER with total amount of the payment due including the value of subcontractor work specified separately, SELLER shall also approve and submit the invoice of its subcontractors for each payment milestone.

SELLER authorizes  PURCHASER to make direct payments to the subcontractors for their services and supplies, based on the approved invoices addressed to SELLER.

In case that  the subcontractors are not paid directly by PURCHASER, SELLER and subcontractor shall submit a Statement of performed payment to subcontractor within sixty (60) days after the Project completion.

8.2	Guarantees

The Bank Good Performance Guarantee to the amount of 10% of the  Fixed and Firm Total Contract Price as per Art. 7.1, in the form and content according to Attachment B, shall be submitted to PURCHASER not later than thirty (30) days after the Contract signature with a validity of 30 days upon signature of the Handover Protocol. The validity of the Bank Good Performance Guarantee shall be extended, if needed.

If SELLER fails to perform its contractual obligations as to the quantity, quality and schedule, due to reasons attributable to SELLER, PURCHASER shall be entitled to call for the Good Performance Guarantee up to its total amount. PURCHASER shall notify SELLER of disputed contractual obligations and its intent to call for the Guarantee.

The Bank Guarantee for Good Performance During Warranty Period to the amount of 5% of the Fixed and Firm Total Contract Price (see Art. 7.1) shall be submitted to PURCHASER in the form and content according to Attachment C with a validity of 30 days after the end of Warranty period as stated in Art. 12.3, item a) below.

Two years (2) upon Handover Protocol signature the original  amount of the Bank Guarantee for Good Performance During Warranty Period will be reduced for the  amount of 5% of the total price for  the Services (see table in Art. 7.2, item 1,2,6,7&8)  and Miscellaneous Hardware (see table in Art. 7.2, item 3, c))  as per Art. 12.3, item c) below.

Three (3) years upon Handover Protocol signature the  amount of the Bank Guarantee for Good Performance During Warranty Period will be additionally reduced for the  amount of 5% of the total price for Major Equipment except AWBT and ACYT tanks as per Art. 12.3, item b) below.

If SELLER does not fulfill its obligations under Art. 12 within reasonable mutually agreed period of time in no case exceeding the warranty period as stated in Art.12.3, PURCHASER is then entitled to call for the Good Performance Guarantee during Warranty Period issued by SELLER’s bank up to its total amount. PURCHASER shall notify SELLER of disputed contractual obligations and its intent to call for the Guarantee.

All here above mentioned Guarantees shall be issued at SELLER’s cost by a first class bank and shall be returned by PURCHASER to SELLER on their date of expiry.

8.3     Delayed Payment

If PURCHASER fails to effect any payment due (for which payment preconditions as stated in Payment Schedule Table above have been fulfilled) to SELLER, PURCHASER shall pay to SELLER interest on the amount of each delayed payment. The interest shall be calculated in accordance with the Statutory Default Interest Rate Act (“Zakon o predpisani obrestni meri zamudnih obresti - ZPOMZO”) at the due payment date from the date the payment is due until the payment in full is effected. Such interest shall be paid by PURCHASER to SELLER on a quarterly basis by bank transfer.

# INSPECTIONS, TESTS & HANDOVER PROTOCOL

All tests and inspections shall be performed in accordance with SP-ES5115.

After successful completion of the Project the Parties, SELLER and PURCHASER, shall sign the Handover Protocol as per Attachment D if no significant faults are counteracting. Minor remaining issues to be taken care of by SELLER or PURCHASER shall be registered in the Handover Protocol.

The prerequisites to sign the Handover Protocol are successfully performed Site Acceptance Tests and Start-up with completed resolution of all open items (non-conformances and deficiency reports category A and B) and NEK receipt of Test Reports.

The Parties shall sign the Handover Protocol within 10 days after the preconditions in the previous paragraph are fulfilled. The protocol shall include at least:

(i)	the date on which all the requirements of Article 9 have actually been met and consequently the date and exact hour on which the warranty period commences;

(ii)	a list of all open Project deficiencies reports of category C and D. No open deficiencies category A and B (as defined in PMM) are allowed.

Signing of the Handover Protocol does not interfere with the rights of PURCHASER related to Article 12 - Warranty for which SELLER is responsible.

# LIQUIDATED DAMAGES FOR DELAY

10. 1   Liquidated Damages for Delay

In case of delay in completion of the milestones as defined in Article 5 of the Contract and PMM approved by PURCHASER due to reasons solely attributable to SELLER, SELLER shall  pay to PURCHASER liquidated damages as follows:

- EUR …………. (min. EUR 50.000,00)  per entire week (7 days) of

delay in the submittal/completion of the milestones as per Art. 5,          Item  3, 4, 5, 6,7 a), 9, 10, 11, 12 a) , 12 b), 15 and 17

- EUR …………... (min. EUR 500.000,00)  per each day of delay

(on a pro rata basis) in completion of outage activities related to          BB2 Project implementation (each outage)  as per Art. 5, item 13 and further  defined in PMM  approved by PURCHASER

- EUR …………... (min. EUR 50.000,00)  per each day of delay

(on a pro rata basis) in completion of Site Acceptance Tests for

BB2 Project  as per Art. 5, item 14 and further  defined in PMM  approved by PURCHASER

Liquidated damages for delay as set forth above shall not exceed, in

aggregate 10% of the Fixed and Firm Total Contract Price set forth in   Article 7.1

Liquidated damages for delay shall be the sole and exclusive remedy for PURCHASER in case of delay.

- 10.2   Liquidated Damages for Performance

SELLER warrants to PURCHASER that upon completion of the Project, the Hardware  delivered under this Contract and the services performed shall meet all Performance Requirements as stated below:

- ABWT volume is  ………….. m3  (to be filled by Bidder  – min 1367 m3)

- ACYT volume  is  ………….. m3  (to be filled by Bidder  – min 1300 m3)

- End of BB2 Building construction  is T0 + …….. months (to be filled by Bidder  –  max T0 +28 months as defined in Art.5, item 7.b)

If SELLER fails to achieve the warranted performance(s) as given above the Fixed and Firm Total Contract Price shall be reduced in respect of the performance value not met by 2% of the Fixed and Firm Total Contract Price as per Article 7.1, per each deviation.

Total  liquidated damages with respect to the failure in performance as set forth above shall  be  limited to 6% of the Fixed and Firm Total Contract Price as per Article 7. 1.

SELLER's total liability for liquidated damages as per this Art. 10. shall be limited to 16% of the Fixed and Firm Total Contract Price as per Article 7.1.

# SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION

In order to ensure safety and health at work, SELLER shall follow the provisions of the Law on Safety and Health at Work (Official Gazette of RS No. 43/11), ADP procedure 1.1.033 Safety and Health at Work at NPP Krško and in compliance with provisions of a separate written Agreement concluded in accordance with Article 39 of the Law on Safety and Health at Work of the Republic of Slovenia.

SELLER shall make sure that the performance of Work be in accordance with internal procedures and instructions issued by responsible PURCHASER’s employees.

In order to fulfill the provisions of the Act on Protection against Ionizing Radiation and Nuclear Safety, the contractual parties shall adhere to the Agreement on Protection against Ionizing Radiation (applicable for suppliers performing services in the controlled area). Based on the provisions of this Agreement, SELLER shall provide all necessary data and signed statements of workers by which they allow transferring the information on their personal dose rates for further use.

SELLER shall test his subcontractor workers on their knowledge of safety rules and document such in-house testing by signing Statement on complying with Act on Ionizing Radiation Protection and Nuclear Safety.

# WARRANTY

12.1	SELLER warrants that all the Hardware furnished under this Contract shall be new and free from liens, encumbrances and defects in title and shall be free from defects in design, workmanship and material and that the Hardware delivered under this Contract shall achieve the design, performance and functional requirements as stipulated in SP-ES5115 i.e. in this Contract. Approval of designs, drawings, samples, test results, suppliers and schedules by PURCHASER shall not in any way limit or diminish the SELLER’s warranties hereunder.

12.2	SELLER warrants that all services he provides shall be in full conformity with the Contract; shall comply with all applicable codes, standards, laws, rules, and regulations; shall be performed in a highly professional and workmanlike manner which would be exercised by  those who perform similar services at the time the  services are  performed and shall be free from defects in design, material and workmanship; shall conform to applicable specifications, and shall be free from all liens  and encumbrances and shall  achieve the design, performance and functional requirements as stipulated in SP-ES5115 i.e. in  this Contract. Warranties shall survive acceptance or payment for any and all services required pursuant hereto but shall end with the elapse of the pertinent warranty period as per Article 12.3

12.3	The warranty mentioned in paragraph 12.1  and/or 12.2 above shall be for the following period as stated below:

- Warranty period for Civil Construction and ABWT and ACYT         tanks   shall be for a period of …..……… years (minimum ten

(10) years)  starting from the date of signature of the Handover

Protocol;

- Warranty period for Major Equipment except ABWT and ACYT

Tanks shall be for a period of …..……… years (minimum three

(3) years)  starting from the date of signature of the Handover

Protocol;

- Warranty period for the Services and Miscellaneous Hardware

shall be for a period of  …..……… years (minimum two (2)

years)  starting from the date of signature of the Handover              Protocol;

12.4	SELLER shall remedy at his own cost all faults and hardware and software deficiencies other than normal wear and tear or faults or deficiencies not attributable to PURCHASER detected and reported in writing claim to SELLER by PURCHASER provided that such PURCHASER’s claim has been received by SELLER within the warranty period. The reporting shall be made within thirty (30) days after the detection of the fault or deficiency. The remedy shall be made by (i) replacement or repair of the faulty or deficient unit (spare part or equipment) at SELLER’s option approved by PURCHASER, such approval being not unreasonably withheld, and within shortest reasonable period of time to be determined between the Parties or (ii) repeat of the defective services.

SELLER’s obligations to remedy faults or deficiencies under the warranty shall be deemed to have been fulfilled when SELLER has made the remedy by delivering the replacement unit to PURCHASER and PUCHASER has inspected and accepted it. A refusal shall be for justified reasons only. SELLER shall pay the transportation and insurance cost from Krško Site to the designated facility and back to DAT Krško Site.

A fresh warranty period shall commence for the repaired or replaced Hardware or the repeated services. The duration of the fresh warranty shall be as stated in Art. 12.3 above. SELLER shall, however, have no warranty obligations anymore after two (2) years upon expiration of the relevant warranty period as per Art. 12.3 above.

12.5	SELLER does not fulfill his obligations under Article 12.4 above within a mutually agreed upon period of time, PURCHASER shall be entitled to correct the defective pieces of Hardware or services at the expense of SELLER provided that such expense shall not exceed the price of the new above defective pieces/services as reasonably evaluated by PURCHASER and SELLER on the basis of the current international market prices.

12.6	If it becomes necessary for SELLER to repair or provide replacement Hardware under these warranties, PURCHASER, without cost to SELLER, shall, to the extent necessary for SELLER to perform its warranty obligations,  make available to SELLER, PURCHASER's facilities, equipment and tools available on Site.

12.7   SELLER shall also ensure the supply of required repair/remedy services for Hardware  delivered under this Contract for the period of minimum ten (10) years upon expiration of the Warranty period defined in Art. 12.3 above. SELLER shall be entitled to appropriate remuneration in accordance with SELLER’s standard rates and international market prices in effect at the time of performance of any such work described in this Art.12.7.

In case SELLER does not fulfill its above  said obligation, SELLER shall reimburse NEK for  all the costs of engineering services done in order to modify the Hardware due to SELLER’s  inability to provide required original spare parts and/or repair services.

Following the 10-years period after the expiration of the contractual Warranty Period, if the replacement parts are not available, the Purchaser and Seller will discuss and agree an alternative solution. involving the provision of adequate  replacement parts at SELLER standard prices.

12.8	The express warranties and remedies set forth in this Article 12 shall constitute the sole and exclusive warranties, guarantees and remedies made to the PURCHASER and are exclusive and in lieu of all other warranties, guarantees and remedies of any kind. Any further rights and claims arising from warranty are excluded except as provided under Article 16.1.

# T A X E S

  - SELLER shall be responsible for the payment of all taxes, duties, tariffs,

- fees and other like charges of SELLER arising from or in connection with

- the subject matter of the Contract except for taxes stated in Art. 13.2

- below.

  - PURCHASER shall be responsible for the payment of Slovenian customs

## duties (payable at Slovenian border) and relevant  Slovenian V.A.T.

13.3   SELLER shall register with Slovenian Financial Authorities and obtain

Slovenian VAT ID Number. In that case SELLER's invoices to

PURCHASER shall include Slovenian VAT. SELLER is responsible for calculation and payment of Slovenian VAT according to the Slovenian VAT Act.

13.4   If SELLER does not register with the Slovenian financial authorities and has no Slovenian VAT ID Number, PURCHASER will pay VAT based on safety reverse charge provision implemented in the Slovenian legislation in accordance with »Article 205 of Council Directive 2006/112/EC«.  In such case SELLER loses the right to deduct or refund the VAT charged to him by Slovenian subcontractors. In no case shall SELLER impose to PURCHASER the potential cost of VAT charged to him by the Slovenian subcontractors.

# LICENSES, PERMITS AND AUTHORIZATIONS

14.1	If required, SELLER shall assist PURCHASER in all its own dealings with the Government Agencies, Licensing Bodies/Authorities and independent inspection agencies in Slovenia. This shall be limited to assistance in obtaining and maintaining licenses, permits and authorizations that may be required for SELLER’s performance under the Contract. To the extent requested, SELLER shall make any necessary presentations to, participate in meetings with, and furnish required information to the competent Slovenian authorities.

SELLER shall be responsible for all dealings with Government Agencies outside Slovenia. This shall include but not necessarily be limited to obtaining, maintaining and paying for licenses, permits and authorizations that may be required for SELLER’s performance under this Contract concerning manufacturing, export and transportation of Hardware within SELLER’s Scope of Services and Delivery.

14.2	Licensability

SELLER shall make sure that the design of the Hardware supplied as far as the SELLER’s Scope of Services and Delivery is concerned meets the applicable licensing standards existing in Slovenia at the time of Contract signature.

# INSURANCE AND INDEMNITY

PURCHASER’s Insurance at PURCHASER’s Cost

PURCHASER represents that it is the responsible operator of the Plant. Therefore, in no event and under no circumstances shall SELLER, its subcontractor, suppliers, directors, agents and the personnel employed by any of them, (hereinafter collectively referred to as the “Indemnified Parties”), irrespective of their activities under this Contract be considered as being the nuclear operator of the Krško Nuclear Power Plant. For its own protection and the protection of the Indemnified Parties, the PURCHASER has in effect and shall maintain in force Material Damage Insurance Policy including machinery break down, and Third Party Liability Insurance Policy against liability and risks arising out of or resulting from a Nuclear Incident (as defined in the Convention on Third Party Liability in the Field of Nuclear Energy of 29th July 1960, as amended by the Additional Protocol of 28th January 1964 and by the Protocol of 16th November 1982 - the Paris Convention) provided in accordance with Slovenian Nuclear Liability Legislation Purchaser represents that Indemnified Parties during the performance of services on Site are covered by Third Party Liability Insurance Policy mentioned above.

SELLER’s Insurance at SELLER’s Cost

Equipment Insurance. SELLER shall procure and maintain in full force and effect, until their removal, insurance of SELLER’s materials, equipment, tools and other objects on Site.

Liability Insurance. SELLER shall procure and maintain in full force and effect until leaving the Site insurance against damage to or loss of the property of PURCHASER and damage or loss and injury to third parties (including without limitation PURCHASER’s subcontractor and suppliers and its or their employees), occasioned by any negligent act or omission of SELLER, its subcontractor and suppliers and its and their employees.

Scope of Services and Delivery Insurance. SELLER shall procure and maintain in full force and effect until leaving the Site insurance of the Scope of Services and Delivery for its full replacement value insofar as it relates to equipment and material, at any time against damage or loss howsoever caused. PURCHASER shall be a named insured under such insurance. Any proceeds under such insurance shall be applied towards the repair or replacement of any part of the Scope of Services and Delivery damaged or lost.

Personnel Insurance. SELLER in respect of all personnel employed by SELLER and its subcontractor for work on Site shall procure and maintain such insurance against occupational injury as is lawfully required from employers in the relevant jurisdiction(s).

Insurance arranged in pursuance of the above Articles shall be with a recognized international insurer. SELLER upon request shall submit to PURCHASER certificates of the insurance policies.

# LIABILITY

SELLER's Liability and Indemnity. SELLER shall be liable in respect of, and hereby agrees to indemnify and hold PURCHASER and its subcontractor and all of its or their officers, agents, servants and employees ("Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of PURCHASER and of damage to the property of, and injury (including death) to, any third party (such term including employees of PURCHASER's and SELLER's subcontractor and suppliers of any tier) to the extent that such claim, loss, damage, liability or expense arises out of or results from acts or omissions attributable to SELLER, its subcontractor and suppliers of any tier and their respective directors, officers, agents, servants or employees during their performance of the Work or from defects in design, workmanship and material of the Scope of Services and Delivery.

As an express condition precedent to SELLER's indemnification obligations hereunder, except in case of PURCHASER’s claim, PURCHASER agrees to: 1) promptly notify SELLER in writing of any claim, whether made or threatened; 2) agree with the SELLER on the level of his authority to defend, compromise or settle the claim; and 3) provide to SELLER all available information and assistance regarding such claim in timely manner. SELLER will not be responsible or liable for any costs, damages, fees, settlement of such suit or proceeding which is incurred or made without SELLER prior written consent.

PURCHASER’s Liability and Indemnity. PURCHASER shall be liable in respect of, and hereby agrees to indemnify and hold SELLER, its subcontractor and suppliers and all of its or their directors, officers, agents, servants and employees (hereinafter referred to as the "Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of and/or injury (including death) to the Indemnitee or any third party which arises out of or results from acts or omissions attributable to PURCHASER or its subcontractors, or any of its or their respective directors, officers, agents, servants or employees.

The Indemnified Parties as defined in Article 15.1 shall in no event be liable with respect to any loss of, damage to property (except for damage to Nuclear Power Plant itself and on Site property) and/or injury (including death), caused by or resulting from a Nuclear Incident and PURCHASER shall indemnify, hold harmless and waive any and all claims and rights of recourse against SELLER. The Indemnified Parties total liability for damages to the Nuclear Power Plant itself and on Site property caused by or resulting from a Nuclear Incident shall be limited to 5.000.000,00 EUR.

Definition. For purposes of this Contract, "Nuclear Incident" shall have the meaning assigned to it by the Paris Convention on Third Party Liability in the field of Nuclear Energy of 1960 as amended by the Protocol of 1964 and 1982, including any nuclear risks such as contamination as provided with Slovenian Nuclear Liability legislation.

A party to the Contract who employs a subcontractor to perform its obligations under the Contract shall be liable to the other party, as for its own actions, for the non-performance or improper performance of the party’s obligations by the subcontractor.

Damages, to which parties to the Contract are entitled in accordance therewith, shall be paid against the indemnified party’s invoice thirty (30) days net. If SELLER fails to pay damages in accordance with the Contract against said PURCHASER’s invoice, the PURCHASER is entitled to demand the payment out of the guarantee valid at that time SELLER’s Bank Good Performance Guarantee or Bank Guarantee for Good Performance During Warranty Period.

The total and cumulative liability of the SELLER, including any claim, warranty, cost and expenses of any kind arising out of or resulting from any cause whatsoever, whether based on contract, tort (including negligence), strict liability or otherwise shall in no event exceed 100% of the Fixed and Firm Total Contract Price. In no event and under no circumstances shall SELLER and PURCHASER be liable for indirect or consequential damages, unavailability of plant, plant outage, plant shutdowns or services interruptions, loss of use of equipment or replacement power, costs of capital, loss of profits or revenues or loss of use thereof, arising at any time, whether founded on contract, tort (including negligence), strict liability or otherwise.

The limitations under this Article shall not apply for damages which are caused willfully or by gross negligence on the part of SELLER, its subcontractors and all of their directors, officers, agents, servants and employees.

SELLER shall only be liable for damages occurring up to the end of the pertinent Warranty Period if such damages are reported to the SELLER immediately after occurrence or discovery of the damage.

# PROPRIETARY INFORMATION

PURCHASER’s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by PURCHASER in connection with the Scope of Services and Delivery under this Contract shall remain PURCHASER' s property. SELLER agrees not to use or release to any third party such Information except for purposes of performance of SELLER's obligations under the Contract unless prior written consent of the contrary is given by the PURCHASER. With respect to such information being disclosed to a subcontractor of SELLER, SELLER shall cause the subcontractor to execute such undertakings as are necessary to give effect to this provision. SELLER shall give PURCHASER a receipt for property furnished by PURCHASER and shall be responsible for safekeeping and return to PURCHASER upon request, upon termination of the Contract, or upon termination of the services to which such property applies.

SELLER‘s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by SELLER or its subcontractor in connection with the Scope of Services and Delivery under this Contract shall remain SELLER 's or its subcontractor's property.

PURCHASER agrees not to use or release to any third party such information only for purposes of verification of the design of the Scope of Services and Delivery, for commissioning, operation, testing, analyses, maintenance, and repairs and the installations at Site and the design and execution of any modification therein or extension thereof and may be disclosed to third parties only for such purposes or for obtaining licenses, permits and other official approvals or as required by law.

In case of disclosure to third parties, PURCHASER shall cause the party to which information is to be provided to execute such undertakings as are necessary to give effect to this provision, save in the case of disclosure to public authorities where PURCHASER shall limit as far as practicable the scope of information so furnished.

SELLER’s proprietary information may not be disclosed to any competitor of SELLER in the field of design and/or construction without SELLER’s prior approval which shall not be unreasonably witheld, provided that this shall not apply to the extent disclosure is necessary on account of the failure by SELLER to comply with the provisions of this Contract to provide Hardware and services on reasonable terms and conditions with any material provision of the Contract, which failure has not been corrected after 30 days notice.

The ownership for SELLER's software shall remain with SELLER. SELLER grants the PURCHASER a non-exclusive, nontransferable, personal right to use the software and firmware supplied under the Contract for operation, maintenance and repairing the deliveries of the SELLER under this Contract.

SELLER shall have the right to call for arbitration in the event PURCHASER violates Section 17.2, and also to seek and receive provisional ruling awaiting the valid arbitral decision.

17.3	The provision of this Article 17. shall not apply to Information, notwithstanding any confidential designation thereof, which is known to the receiving Party without any restriction as to disclosure or use at the time it is furnished, which is or becomes generally available to the public without breach of any agreement, or which is received from a third party without limitation or restriction on said third party or to the receiving Party at the time of disclosure.

# 18     CLAIMS

Any claim of a Party to the Contract shall be in writing and shall be justified in detail and shall be immediately submitted by the Party through a letter or fax, to the authorized representative of the other Party and in no event later than thirty (30) days after discovery of basis for such claim. In case the basis of the claim is of such a nature that it requires longer claim submittal period, then this period will be adequately prolonged. The claiming Party will inform the other Party thereof in advance. No claim shall be valid under the Contract if submitted to the other party 30 days after the expiry of the respective warranty period. The Party against whom the claim has been made shall notify the claiming Party of its acceptance or dismissal of the claim within thirty (30) days after the receipt of the claim. If no such notification is received by the claiming Party within the said time, the claim is deemed to have been accepted by the other Party.

It shall be claiming party’s responsibility to prove that the respective warranty defect existed before the end of the warranty period if the defect was discovered after the expiry of the warranty period.

All claims shall be resolved satisfactorily within mutually agreed time period.

# 19     ARBITRATION

  - Any differences or disputes arising from or in connection with this Contract shall be settled by an amicable effort on the part of both the Parties to the Contract. An attempt to arrive at a settlement shall be deemed to have failed as soon as one of the Parties to the Contract so notifies the other Party in writing.

  - If an attempt by the parties to arrive at a settlement has failed, any differences or disputes arising out of or in connection with the Contract shall be finally settled in accordance with the Arbitration Rules of the International Chamber of Commerce (Paris) by three arbitrators appointed in accordance with the said Rules.  Any such arbitration shall take place in Zurich (Switzerland) and shall be conducted in the English language. The procedural law of this place shall apply where the Rules are silent.

  - Any arbitral award shall be rendered in writingand be final and binding upon the Parties. To enforce compliance with such arbitration   decision, it may be entered in the appropriate court in either SELLER’s country or Slovenia, assuming the country otherwise has jurisdiction over the Parties. The arbitral tribunals shall decide on the matter of costs of the arbitration.

  - All disputes shall be settled in accordance with the provisions of this Contract. Arbitration under this Article is the sole remedy for disputes arising out of the Contract, its performance or the enforcement thereof.

  - Performance under this Contract shall continue if reasonably possible during any disagreement or court proceeding, and no funds payable to  either Party under the Contract shall be withheld on account of such disagreement or proceeding.

# 20     SUBSTANTIVE LAW

All differences, disputes or claims shall be settled in accordance with the provisions of the Contract, otherwise in accordance with the substantive law in force in Switzerland, without reference to any Swiss conflict of laws and connexity rules incompatible with such choice of law.

# 21     FORCE MAJEURE

21.1	Neither Party to the Contract shall be considered to be in default in the performance of its obligations to the extent that the performance of any such obligation is hindered, prevented or delayed by a Force Majeure circumstance, occurred after entering into the obligations, and which could not be foreseen by the Party in entering into obligations.

21.2	A force majeure circumstance shall mean any circumstance existing which is beyond a Party’s reasonable control and which is not a result of its fault or negligence, including but not limited to: acts of God, such as storm, flood, or earthquake; acts or omissions of civil or military authority,; war (declared or undeclared), acts or omissions of governmental authority, such as quarantine, embargo, priorities of trade, delay or failure to issue Construction Permit; civil disturbances, such as revolution, rebellion, riots, or insurrection; sabotage, transport accident, fuel or energy shortage, or any other circumstances beyond reasonable control of the Party, which may interfere with the commencement or progress of the Scope of Services and Delivery. The deficiency of labor force and/or defects in material and/or strike of local character with SELLER’s suppliers and subcontractors will not be deemed as Force Majeure.

21.3 	Upon the discovery of the occurrence of any such Force Majeure circumstance, the party affected by it shall within thirty (30) days of becoming known notify the other Party thereof, and of its estimated effect, by a registered letter, shall use diligent efforts to eliminate such circumstance and mitigate its effects, and shall keep the other Party fully informed of the progress of its efforts. In the notice of the Force Majeure circumstance, the Party shall indicate the cause of the Force Majeure circumstance, its beginning date and anticipated duration with the confirmation by a competent authority, such as Chamber of Commerce, of the validity of the notice. The affected Party shall also notify in the same way the other Party of the termination of the Force Majeure circumstance. However, this communication is dispensed with if the impact of the conditions of Force Majeure on compliance with the contractual obligations becomes obvious to the other Party in any other way. If the circumstances of Force Majeure also affect the postal routes, the thirty (30) days period for notification shall be deemed to apply only after termination of the obstacles in postal transmission.

21.4	The time for the performance of the obligation of the affected Party shall be extended by a time mutually agreed upon and reasonably necessary to overcome the effects of the Force Majeure circumstance. Any exceptions to the above shall be mutually agreed upon by the Parties.

21.5	If either Party is prevented from performance of the Contract for a continuous period in excess of three weeks because of Force Majeure either Party may suspend the Scope of Services and Delivery. If furthermore a Force Majeure impediment exceeds one (1) month individually or three (3) months in aggregate due to Force Majeure the Contract may be terminated if both the Parties agree in writing with such decision provided that neither Party is entitled to any profit on the account of the other Party. The termination shall take effect at the date mutually agreed by the Parties. In case the Scope of Services and Delivery is suspended or terminated, the SELLER shall be paid for the Scope of Services and Delivery performed up to the date of suspension or termination.

21.6 	Under Force Majeure circumstances, each Party bears its own costs.

# 22     SUSPENSION OF WORK AND TERMINATION

  - Suspension of Work and Termination of Contract by PURCHASER for Default

PURCHASER shall have the right to suspend the Work or any portion of the Work or to terminate the Contract for material default, except for a case of Force Majeure as defined in Art. 21, which shall include the following:

- Failure of SELLER to start the work within ten (10) days from the date of coming into force of the Contract.

- Significant discontinuances and disturbances of SELLER in the progress of the Work which seriously delays the Project Time Schedules and failure of SELLER to initiate within a reasonable time after PURCHASER's notice to do so the corrective measure to minimize such delays.

- SELLER’s insolvency or bankruptcy, or other financial inability to carry on the Work.

- Failure on the part of SELLER to observe any material requirements of the Contract (not limited to schedule, quality and technology of work), having a direct consequence on the performance of the Contract.

- Collusion for the purpose of illegally procuring a contract or perpetrating fraud on PURCHASER in the construction of the Work under this Contract.

- SELLER has engaged subcontractors for a part of the Scope of Services and Delivery for which PURCHASER did not provide approval or even rejected them

- SELLER did not make  additional efforts and improvements requested by PURCHASER in case of delay caused by SELLER

PURCHASER shall give SELLER written notice of any default which may be a basis for termination hereunder, and shall provide SELLER the opportunity to cure or institute acceptable action to cure such default in a period not to exceed thirty (30) days from receipt of such notice. Such suspension or termination, if issued, will be by a written order to SELLER whereupon SELLER shall immediately comply therewith. When the Work is suspended for any of the causes itemized above; or for any other cause or causes constituting a material default of SELLER, SELLER shall discontinue the Work or such part thereof as PURCHASER shall designate.

In case of termination, PURCHASER shall have the power to complete by Contract or otherwise, as it may determine, the Work herein described or such part thereof as it may deem necessary, and PURCHASER shall have the right to take possession of or use the whole or any portion of the Work completed or then in progress. SELLER shall assign to PURCHASER, in the manner and to the extent directed by PURCHASER, all the right, title and interest of SELLER in each subcontract or order, and to continue such orders of subcontracts, or to settle or pay any or all claims arising out of termination of such orders and subcontracts. The expense so charged shall be deducted by PURCHASER out of such monies as may be due or may at any time thereafter become due SELLER under and by virtue of the Contract or any part thereof. PURCHASER is also entitled to call for the Bank Good Performance Guarantee for the  total amount of the expenses  imposed on PURCHASER.PURCHASER shall not be required to obtain a lowest bid for the Work of completing the Contract, but the expenses to be deducted shall be reasonable under the circumstances and on the basis of the current international market prices.

In case such expense is less than the sum which would have been payable under the Contract, if the same had been completed by SELLER, then in such case PURCHASER shall pay to SELLER the difference in the cost, provided that SELLER shall not be entitled to any claim for damages or for loss of anticipated profits. In case such expense shall exceed the amount which would have been payable under the Contract if the same had been completed by SELLER, then SELLER shall pay the amount of the excess to PURCHASER on notice from PURCHASER for excess due. Such amount to be paid by SELLER shall in no event exceed 100% of the Total Contract Price portion of the relevant portion of the Scope of Services and Delivery terminated.

When any particular part of the Work is being carried on by PURCHASER by Contract or otherwise under the provisions of this section, the SELLER shall continue the remainder of the Work in conformity with the terms of the Contract and in such manner as not to hinder or interfere with the performance of workmen employed as above provided by PURCHASER.

SELLER shall not suspend Work without written direction by PURCHASER order of a court, or governmental agency and will not be entitled to additional compensation by virtue of such order. Neither will it be liable to PURCHASER in the event the Work is suspended by such order.

  - Suspension of Work and Termination of Contract for Convenience by PURCHASER

- The performance of the Work under this Contract may be terminated by PURCHASER at any time, for its convenience. Any such termination shall be by submittal to SELLER of a written Notice of Termination, which shall be effective upon receipt. In such case, SELLER shall be entitled to 1) such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and to 2) reimbursement of all expenses demonstrably incurred in the performance of this Contract, 3) reimbursement of all direct and documented expenses demonstrably incurred including demobilization costs in the termination of this Contract and SELLER’s supplies and subcontracting arrangements.

- After receipt of a Notice of Termination, and except as otherwise directed by PURCHASER, SELLER shall:

- Stop Work under the Contract on the date specified in the Notice of Termination.

- Place no further orders or subcontracts for materials, services or facilities.

- Terminate all orders and subcontracts.

- Settle all outstanding liabilities and all claims arising out of such termination of orders and subcontracts, with the approval or ratification of PURCHASER to the extent it may require, which approval or ratification shall be final for all purposes of this clause.

- Transfer title to PURCHASER and deliver in the manner, at the times, and to the extent, if any, directed by PURCHASER:

1) 	The fabricated parts, work in process, completed work, supplies, and other material produced as a part of, or acquired in connection with the performance of the Work terminated by the Notice of Termination; and

2) The completed, or partially completed plans, drawings, information, software and other property (except for SELLER proprietary software) which, if the Contract had been completed, would have been required to be furnished to PURCHASER.

- Take such action as may be necessary, or as PURCHASER may direct, for the protection and preservation of the property related to the Contract which is in the possession of SELLER and in which PURCHASER has or may acquire an interest.

At any time after thirty (30) days after the termination date specified in the Notice of Termination, SELLER may submit to PURCHASER a list, certified as to quantity and quality; of any or all items of termination inventory not previously disposed of, exclusive of items the disposition of which has been directed or authorized by PURCHASER, and may request PURCHASER to remove such items or enter into a storage agreement covering them. Not later than fifteen (15) days thereafter, PURCHASER will accept title to such items and remove them or enter into a storage agreement covering the same; provided, that the list submitted shall be subject to verification by PURCHASER upon removal of the items or, if the items are stored, within forty-five (45) days from the date of submission of the list, and any necessary adjustments to correct the list as submitted, shall be made prior to final settlement.

- After receipt of a Notice of Termination, SELLER shall submit to PURCHASER his termination claim. Such claim shall be submitted promptly but in no event later than five (5) months from the effective date of termination, unless one or more extensions in writing are granted by PURCHASER upon request of SELLER made in writing with such five (5) months period or authorized extension thereof. Upon failure of SELLER to submit his termination claim within the time allowed, PURCHASER may determine, on the basis of information available to it, the amount, if any, due to SELLER by reason of the termination and shall thereupon pay to SELLER the amount so determined, which shall be the sole amount to which SELLER shall be entitled as a result of such termination.

- PURCHASER shall have the authority to suspend the Work wholly or in part for such period or periods as it may deem necessary. For the suspension under this clause SELLER shall be entitled to receive payment for the part of the Works performed up to the date of suspension including all additional costs and expenses demonstrably accruing to SELLER and its subcontractors  as consequence  of the suspension and shall be entitled to an equitable adjustment of price and schedule. Should such suspension exceed a maximum period of 12 months, SELLER and PURCHASER shall mutually agree how to proceed. If the agreement is not reached SELLER shall be entitled to terminate the Contract within next six months and be entitled to the reimbursement as stated in article 22.2., first paragraph. If it should become necessary to stop Work for an indefinite period, SELLER shall store all materials in such manner that they will not obstruct or impede activities at the Site unnecessarily nor become damaged in any way, and it shall take every precaution to prevent damage or deterioration of the Work performed. SELLER shall proceed with the Work in agreement with the PURCHASER.

- Nothing contained in this section shall limit or alter the rights which PURCHASER may have for termination of this Contract under the article hereof entitled Suspension of the Work and Termination of Contract by PURCHASER for Default or any other right which PURCHASER may have for default or breach of Contract by SELLER.

22.3 	In case of material breach of the Contract by PURCHASER including but not limited to PURCHASER’s failure to make payment or PURCHASER’s insolvency and if PURCHASER fails to make good such material breach within reasonable time (three months) after having been informed by SELLER in writing of such material breach, SELLER may terminate the Contract. In case of termination, SELLER shall have the remedies available as per Art.22.2 above

22.4 	Anti-Corruption Clause

The Contracting Parties shall undertake not to give, promise or receive any present or payment in cash or in any other valuable object to or from each other either directly or indirectly or through any official, officer or any other individual employed in the government or any authority (division, department, agency) or through any political party or any candidate of any political party with the intention of bribing so that any official, officer or any other employee, party or candidate would be tempted to abuse his/her position or to exert influence on any law or any decision made by government or any other competent government department with the purpose to obtain or retain a deal or to direct a deal to a commission agent or to any of his assistants, representatives, distributors, subsidiary companies or any other associated companies. In case the act stated in the previous paragraph has been committed or attempted to be committed, the Contract that had been concluded or had come into force already shall become null and void. In case the Contract is not valid yet, it shall be deemed not to be concluded.

22.5   Social Clause

During his involvement in this Project, SELLER shall fulfil all applicable obligations in the field of environmental, social and labour laws, as they are set out in the European Union legislation, national legislation, collective agreements or the rules of international environmental, social and labour regulations and if they do not fulfil the above stated obligations the contract will be terminated. Applicable international social and environmental conventions are listed in Attachment X of EU Directive 2014/24/EU and Attachment XIV of EU Directive 2014/25/EU.

# 23    CHANGES

In case that certain services and supplies are not included in the original Contract, but due to unpredicted circumstances unknown at the time of Contract signature have become necessary for the completion of the Project and without difficulties cannot be performed separately from the Contract, according to the Slovenian Public Tendering Law (Article.46) the Contractor can be invited for negotiation.

The SELLER shall, at the PURCHASER’s request, make changes in design or equipment, material or services, not included in the original Contract, but due to unpredicted circumstances unknown at the time of the conclusion of the Contract, if changes in design, equipment, material or services become necessary for the completion of the Project and cannot be performed separately from the Contract without significant difficulties. In such a case the PURCHASER shall invite the SELLER to negotiations by means of a formal letter, while the negotiations shall be subject to the rules provided in this Article.

Any changes to this Contract shall not have any effect until the SELLER and the PURCHASER have agreed on the price to be paid to the SELLER, the delivery or the performance schedule, Quality Assurance conditions and other affected terms and conditions, so as to reflect any changes in (i) SELLER’s efforts which may be required, 2) the scope of work, 3) the time of the performance and the impact on the schedule, 4) the warranties, and 5) the costs to complete.

Upon receipt of the formal letter with the invitation for negotiations, which must include a description of the object of the change and the reasons for such a change, the SELLER shall prepare and submit to the PURCHASER a proposal for a Change Order in written form, which shall:

a) describe the scope of the proposed change,

b) quote in term of man-hours, rates, prices or otherwise as appropriate, the estimated increase or decrease in the total price that would result from the implementation out of the requested change,

c) specify those terms and conditions which are affected by the change, including time for performance and warranties, and

d) if appropriate, indicate the date on which the SELLER would proceed with the change.

If changes are to be required by any Governmental Agency or Authority, including the United States Nuclear Regulatory Commission, such a requirement will constitute an obligation for the PURCHASER to initiate the new public procurement procedure as required.

The PURCHASER and the SELLER agree that negotiations for change of this Contract shall be considered an independent procedure in which the SELLER may submit reservations with a technically viable justification or other conditions, insofar as they apply only to the object of the change.

In the event negotiations regarding changes requested by the PURCHASER do not lead to a Change Order but do have an impact on the schedule, the project schedule will be extended appropriately.

The SELLER may propose changes to the PURCHASER, but may not implement them without the prior written consent of the PURCHASER.

Any changes to this Contract shall be made in writing; the Parties agree that changes in any other form shall be considered void.

# 24     OTHER PROVISIONS

Documentation to be Submitted for SELLER Team

The documents to be submitted to PURCHASER at the latest 30 days before arrival of SELLER's personnel, including his subcontractors at NEK site are as follows:

Documents needed for NEK's cardkey issuance and security vetting:

Based on the NEK Instructions on Security Vetting of Outside Workers attached hereto as part of Attachment G, SELLER shall perform security vetting for his on-site crew.

Additionally, SELLER shall fill in, sign and submit to PURCHASER the following documents attached hereto as Attachment G:

- Request for Entry Card for Outside Worker (6.5-C)

- Written Agreement on Ensuring Collective Occupational Health   and Safety, Fire Protection and Environmental Management

- Statement on complying with Act on Ionizing Radiation Protection  and Nuclear Safety (6.3-C)

- Agreement with Security Vetting Procedure (6.1-C) *

- Security Vetting Questionnaire (6.2-C) *

*These documents, completed and signed, should be kept in the

personal file of the worker in SELLER’s company for five years after

the service/work performed at NEK. These forms (including the

required attachments) are not requested to be submitted to

PURCHASER but should be available at PURCHASER request.

Documents needed for work in NEK's radiation controlled area:

The documents to be submitted to PURCHASER for the workers who shall perform the activities in NEK's radiation controlled area are as follows:

- Agreement on Radiological Protection (to be previously

provided for signature by PURCHASER )

- Personal qualification records

- HP records

- Medical examination certificate

SELLER shall also, at SELLER's cost, obtain an Approval from Slovenian Nuclear Safety Administration (SNSA) at the Ministry for Agriculture and Environment that SELLER has obtained license in his country to work in the radiation controlled area under conditions and in accordance with procedures equivalent to conditions and procedures as required under the Slovenian Act on Protection against Ionising Radiation and Nuclear Safety.

Labor Permits and Visas

SELLER shall obtain, at SELLER's cost, Slovenian labor permits and visas required by Slovenian authorities to permit SELLER's personnel to perform the services under this Contract.

# 25     ASSIGNMENT

No Party shall assign this Contract in whole or in part without the prior written consent of the other Party, which consent shall not be unreasonably withheld.

# 26     ENTIRE AGREEMENT

The Contract shall constitute the entire and definitive agreement between Parties thereto with respect to the terms and conditions which shall govern. The Contract will supersede all prior written or oral communications between the Parties concerning the subject matter of the Contract which communication upon signature of the Contract by both Parties shall become null and void.

No waiver, alteration or modification of the Contract shall be binding to the Parties unless made in writing and signed by duly authorized representative of the Parties.

# 27     LANGUAGE

SELLER and PURCHASER agree that the official version of the Contract, the Appendices and the Technical Specification shall be in English or Slovenian or Croatian  language.

All notices, communications or approvals contemplated hereunder shall be in English.

All Technical Documentation, specifications, drawings, reports specified in the Technical Specification and all other documents referred to by this Contract and any of its constituting part are required to be in English or Slovenian language.

# 28    EFFECTIVE DATE OF CONTRACT

The effective date of the Contract shall be the date  provided on the first page of the Contract.

# 29   NOTICES

Any notice pursuant to this Contract shall be deemed to have been

duly  made when sent to the following address:

PURCHASER:

Nuklearna Elektrarna Krško

Vrbina 12

8270 Krško

Slovenia

Attention: 	Mr. Istok Junkar, for  technical issues

Phone:   00386/7/48-02-591

e-mail: istok.junkar@nek.si

Mrs. Vesna Deak, for commercial issues

Phone:   00386/7/48-02-436

e-mail:  vesna.deak@nek.si

Telefax:  00386/7/4921-528, 4921-006

SELLER:

…………………………

…………………………

………………………….

Attention: …………………..

…………………..

# 30   ATTACHMENTS

The following Attachments are constituent integral parts of this  Document Part I General Terms and Conditions, as listed below, and are attached hereto:

ATTACHMENT A:	Overall Project Schedule

ATTACHMENT B:	Bank Good Performance Guarantee

ATTACHMENT C:    Bank Guarantee for Good Performance during

Warranty Period

ATTACHMENT D: 	Handover Protocol on Successful Completion of

the Project

ATTACHMENT  E:	Subcontractor’s Data and SELLER’s Consent for Direct Payment

ATTACHMENT F:	Payment Table related to SELLER’s and its Sub-

contractors price portion per payment instalments

ATTACHMENT  G:    Documentation to be filled in, signed and  provided  				by SELLER  for its and its  subcontractors on-site

team

In witness thereof the Parties have signed this Contract in two (2)

identical originals of which each Party hereto retains one (1).

For SELLER:

For PURCHASER:

Nuklearna Elektrarna Krško d.o.o.

Hrvoje Perharić					   Stanislav Rožman

Member of the Management Board                President of the Management Board

## ATTACHMENT A

OVERALL PROJECT SCHEDULE

for

NEK Safety Upgrade Project  Phase 3,

BB2 Project – Engineering, Design and Construction

## ATTACHMENT B

BANK GOOD PERFORMANCE GUARANTEE (draft)

Date: ……..

Name and address of the Beneficiary

TYPE OF GUARANTEE: Performance Guarantee

GUARANTEE NO.: …………………..

THE GUARANTOR: ……………..

THE APPLICANT: ……………

THE BENEFICIARY: …………………

THE UNDERLYING RELATIONSHIP: The Applicant’s obligation in respect of the Contract

No. …….. dated ………….concluded between Beneficiary and the Applicant, with which the Applicant is obliged to perform the Project ..…………. at a total price of EUR ……….... According to the conditions of the above mentioned Contract, a Performance Guarantee in the amount of ……% of the total Contractual price,

i.e. EUR ……….., is required.

GUARANTEE AMOUNT AND CURRENCY: ………………………EUR

(in words:  .………………./100 Euros)

ANY DOCUMENT REQUIRED IN SUPPORT OF THE DEMAND FOR PAYMENT, APART FROM THE SUPPORTING STATEMENT THAT IS EXPLICITLY REQUIRED IN THE TEXT BELOW: none

LANGUAGE OF ANY REQUIRED DOCUMENTS: English

FORM OF PRESENTATION: paper presentation only by registered mail or any courier service.

For the purpose of identification, Beneficiary’s demand for payment has to be presented through Beneficiary’s business bank, confirming the Beneficiary’s signature(-s) in demand for payment appear to conform to specimen(s) held in Beneficiary’s Bank’s records.

PLACE OF PRESENTATION:

EXPIRY: ……………….

As Guarantor, we hereby irrevocably undertake to pay the Beneficiary upon receipt by us of his first written demand, any amount up to the Guarantee Amount upon presentation of the Beneficiary’s complying demand, in the form of presentation indicated above, supported by such other documents as may be listed above and in any event by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, indicating in what respect the Applicant is in breach of its obligations under the Underlying Relationship.

The Guarantor will effect payment at sight without delay and not later than fifteen (15) days from the receipt of Beneficiary's first written request as set out above.

Any demand under this Guarantee must be received by us on or before Expiry at the Place for presentation indicated above.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758.

## ATTACHMENT C

BANK GUARANTEE FOR GOOD PERFORMANCE

DURING WARRANTY PERIOD (draft)

Date: ……..

Name and address of the Beneficiary

TYPE OF GUARANTEE: Warranty Guarantee

GUARANTEE NO.: …………………..

THE GUARANTOR: ……………..

THE APPLICANT: ……………

THE BENEFICIARY: …………………

THE UNDERLYING RELATIONSHIP: The Applicant’s obligation during warranty period in respect of the Contract  No. …….. dated ………….concluded between Beneficiary and the Applicant for the Project …….………..at a total price of EUR ………...

According to the Conditions of the above Contract a Warranty Guarantee in the amount of ……% of the total contractual price, i.e. EUR ……….., is required.

GUARANTEE AMOUNT AND CURRENCY: EUR ……….

(in words: Euro .………………./100)

ANY DOCUMENT REQUIRED IN SUPPORT OF THE DEMAND FOR PAYMENT, APART FROM THE SUPPORTING STATEMENT THAT IS EXPLICITLY REQUIRED IN THE TEXT BELOW: none

FORM OF PRESENTATION: Paper presentation only by registered mail or any courier service. The demand must be presented through the intermediary of your bank confirming that your signature(s) on your demand for payment appear to conform to specimen(s) held in your bank’s records.

PLACE FOR PRESENTATION: ………

EXPIRY: ………………. (The Guarantee shall be valid from the date of issuance of this Guarantee till 30 days after the end of the Warranty period as stated in the Contract, Art. 12.3.)

The Guarantee shall be valid from the date of issuance of this Guarantee till  30th day after the end of the Warranty period as stated in the Contract.

As Guarantor, we hereby irrevocably undertake to pay the Beneficiary upon receipt by us of his first written demand, any amount up to the Guarantee Amount upon presentation of the Beneficiary’s complying demand, in the form of presentation indicated above, supported by such other documents as may be listed above and in any event by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, indicating in what respect the Applicant is in breach of its obligations under the Underlying Relationship.

Beneficiary’s statement must state, that the Applicant after the receipt of request to make good a deficiency in the warranty period under the Underlying Relationship, hasn’t fulfilled his contractual warranty obligations under the Underlying relationship.

The Guarantor will effect payment at sight without delay and not later than fifteen (15) days from the receipt of Beneficiary's first written demand as set out above.

Any demand under this Guarantee must be received by us on or before Expiry at the Place for presentation indicated above.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758.

## ATTACHMENT D

## HANDOVER PROTOCOL

ON SUCCESSFUL COMPLETION

of

NEK Safety Upgrade Project  Phase 3,

BB2 Project – Engineering, Design and Construction

We hereby certify that the Project “NEK Safety Upgrade Project  Phase 3,  BB2 Project – Engineering, Design and Construction” has been successfully completed fully in line with the scope, schedule, delivery time and other terms and conditions stipulated in the Contract No.  ……..   and is operationally and functionally satisfying the requirements as stated in NEK Technical Specification No. SP-ES5115, Rev.0.

The list of all open Project deficiencies reports of category C and D is attached hereto.

The list of remaining non-installed items of hardware with relevant technical/QA documentation and part numbers and other details necessary for warehouse acceptance which shall be moved to PURCHASER’s warehouse with the transfer of Title and Risk of Loss is attached to this Protocol.

The date on which all the requirements as stated in Art. 9 of the Contact No. ……. have actually been met and consequently the date and exact hour on which the warranty period commences is: ----------------------

Date: 	                                                                           Date:

For SELLER						For PURCHASER

## ATTACHMENT E

SUBCONTRACTOR’S DATA AND SELLER’S CONSENT FOR DIRECT PAYMENT

Contractor ……………………………………………………………………………

……………………………………………………………………………………………………………………………….

We declare that we will engage below stated Subcontractor for the part of the Scope of Services and/or Delivery under the Contract for

…………………………………………………………………………………………

Name and head office: …………………………………………………………………………………………

TAX number: …………………………………………………………………………………………

Registration number: ………………………………………………………………………………………

IBAN: …………………………………………………….…………………………………

Statutory representative: ……………………………………………………….……………………………..…

Scope of Services and/or Delivery to be performed by Subcontractor: .………………………………………………………………………………………

Value of the Services and/or Delivery to be performed by Subcontractor:

…………………………………………without VAT………….……………………….... with VAT

Place of performance of services: ……………………………………………………………………….…………………

Deadline for performance of services and/ or delivery: …………………………………………………………………………………………

We declare to be engaged for the above stated Scope of Services and/or Delivery  as the Subcontractor to the Contractor.

We, the Subcontractor agree to be paid as follows (please encircle your option):

- We request to be paid directly by the Purchaser at our account number, for our part of performed Scope of Services and/or Delivery based on the invoice approved by the Contractor.

- We request to be paid directly by the Contractor for our part of performed Scope of Services and/or Delivery.

- Within sixty (60) days upon completion of the Project, the Subcontractor and the Contractor shall submit to Purchaser  the Statement by which confirm  that the Subcontractor was reimbursed  by the Contractor for the complete Scope of Services and /or Delivery performed per the relevant contract signed between the Contractor and the Subcontractor.

With signature of this statement we declare the fulfillment of the following conditions:

- Subcontractor fulfills all the conditions requested in  the subject Bidding documentation regarding the part of the Scope of Services and/or Delivery for which the Subcontractor is engaged .

We authorize the Purchaser to acquire the necessary data  which will confirm the fulfillment of the above conditions.

Place and date: 			Stamp: 	   Contractor’s Signature:

________________

Subcontractor’s Signature:

## ATTACHMENT  F

Project

»NEK Safety Upgrade Project  Phase 3,  BB2 Project – Engineering, Design and Construction »

Payment Table related to SELLER’s and its  Sub-contractors price                                            portion per payment instalments

## ATTACHMENT  G

Documentation to be filled in, signed  and  provided (except

form 6.1-C & 6.2-C) by SELLER  for its and its subcontractors

on-site team:

- Instructions on Security Vetting of Outside Workers for Unescorted Access to and Work at Krško NPP, and on Obtaining the Entry Card

- Request for a Personnel Security Clearance Information Sheet

- Request for Entry Card for Outside Worker (6.5-C)

- Written Agreement on Ensuring Collective Occupational Health

and Safety, Fire Protection and Environmental Management

- Statement on complying with Act on Ionizing Radiation Protection

and Nuclear Safety (6.3-C)

- Agreement with Security Vetting Procedure (6.1-C)

- Security Vetting Questionnaire (6.2-C)

- Agreement on Radiological Protection