Contracting authority: University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia

Tender dossier for the public procurement procedure

»A telephone business survey (CATI) in several European countries 
for the GLOBALINTO project«

Ljubljana, January 2020

This project has received funding from the European Union’s Horizon 2020 The mechanisms to promote smart, sustainable and inclusive growth under grant agreement No 822259.

Contents

1 Subject matter and details of the tender	4

1.1 Overview	4

1.2 Technical specifications	5

1.2.1 The sample and unit eligibility	5

1.2.2 Establishment of contact, respondent identification and interview implementation	7

1.2.3 Questionnaire	8

1.2.4 Pilot	8

1.2.5 Field staff and organisation of work	9

1.2.6 Data validation, delivery and reporting	10

1.2.7 Meetings	12

1.2.8 Preliminary schedule	12

1.2.9 Deliverables	12

2 Submission of tenders and deadline for submission of tenders	13

3 Obtaining tender documents and explanations	15

4 Tender format, language and cost	15

5 Validity of the tender	16

6 Joint tender	17

7 Subcontracting	17

8 Confidentiality	19

9 Provision of information to the Contracting Authority	19

10 Change in the scope of the object of the contract and conclusion of the contract	20

11 REASONS FOR EXCLUSION	20

11.1. Prior impunity	20

11.2. Inclusion on the list of tenderers with negative references and records of business entities from ZintPK (Law on Integrity and Prevention of Corruption)	21

11.3. Unpaid taxes and social contributions	21

11.4. The fine in respect of work remuneration	21

11.5. A serious breach of professional rules	22

11.6. Significant professional mistake	22

11.7. Insolvency	23

12 SELECTION CRITERIA	23

12.1 Registration of activity	23

12.2. Acting in accordance with the standards for best practice in marketing and social research	23

12.3 Criteria related to the Tenderer	24

12.4 Criteria related to the teams	24

12.5 Implementation plan	25

13 Financial insurance	26

13.1 Financial tender guarantee	26

13.2. Performance guarantee	27

14 Award criteria	28

14.1 Financial evaluation of offers	28

14.2 Additional references of nominated staff	29

14.3 Awarding of the contract	29

15 Legal basis	29

16. Legal recourse	30

Annex	31

Tender pro forma invoice – initial bid	32

Bill of Exchange Statement for tender guarantee	34

Declaration on submitting the bill of exchange statement for the proper performance of contractual obligations	35

Bill of Exchange Statement for the proper performance of contractual obligations	36

References of the Tenderer	37

Certificate of the Reference (see also 12.3)	38

Team Competences (see 12.4.)	39

Sample contract	41

Tender pro forma invoice – final bid	52

1 Subject matter and details of the tender

University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana (hereinafter: the Contracting authority), in accordance with Article 44 of the Public Procurement Act invites all interested tenderers to submit their written tender in accordance with this documentation, published on the Public Tender Portal and the European Union Portal: "A telephone business survey (CATI) in several European countries for the GLOBALINTO project".

The GLOBALINTO project is funded by the European Union’s Horizon 2020 Program under the grant agreement No 822259. The project runs from February 2019 to January 2022 and seeks to provide data and develop new measures of intangible assets in order to analyse the role of knowledge production and diffusion for innovation, productivity and growth. Given the project’s relevance for policy and research, data collection should follow the highest ethical and methodological standards to obtain high quality data (see ICC/ESOMAR International Code on Market, Opinion and Social Research and Data Analytics, 2016; the ESOMAR/WAPOR Guideline on Opinion Polls and Published Surveys, 2014; The European Statistics Code of Practice, 2017).

This documentation is released in the Slovenian and English languages. In case of an inconsistency between the two versions, the Slovenian version will be considered.

1.1 Overview

The subject of the tender is a cross-national business survey conducted using CATI (computer-assisted telephone interviewing) (hereinafter also the survey). The Client will provide the questionnaire in national languages of the countries covered in the tender. The contractor will be required to conduct telephone interviews with business respondents from top management after having identified them through a screener interview.

The contractor will be required to first conduct a small pilot and then to obtain 2,005 complete interviews from eight European countries so that:

- at least 310 complete interviews come from each of the following large countries: France, Germany, and The United Kingdom;

- at least 215 complete interviews come from each of the following small countries: Denmark, Finland, Greece, Norway, and Slovenia.

Full details are provided under 1.2 Technical specifications.

The required term of completion of the services specified in Chapter 1.2. of this documentation is 4 months after the signing of the contract, estimated by 15 July 2020. The Tenderer will provide additional information regarding the implementation of the survey, interpretation of the data or other information required by the Contracting authority for additional 5 months after submitting the final technical report.

The work is scheduled to start in February 2020.

The Tenderer must offer all the services that are the subject of this tender, otherwise the tender will be considered technically inappropriate and consequently inadmissible.

The subject of the tender is whole, and it is not divided into lots

The Contracting authority will award the contract to the Tenderer that will submit an admissible offer that will be most advantageous according to criteria.

Variants and optional tenders will not be accepted.

1.2 Technical specifications

1.2.1 The sample and unit eligibility

The unit of observation is an enterprise. The target population are enterprises with their principal activity in the following economic activities (accompanied with their 2-digit NACE codes):

- Manufacturing industries with intensive investments in intangible capital

  - 10	Manufacture of food products

  - 20	Manufacture of chemicals and chemical products

  - 21	Manufacture of basic pharmaceutical products and pharmaceutical preparations

  - 24	Manufacture of basic metals

  - 26	Manufacture of computer, electronic and optical products

  - 28	Manufacture of machinery and equipment n.e.c.

- Knowledge-intensive services

  - 62	Computer programming, consultancy and related activities

  - 63	Information service activities

  - 69	Legal and accounting activities

  - 70	Activities of head offices; management consultancy activities

  - 71	Architectural and engineering activities; technical testing and analysis

  - 72	Scientific research and development

  - 73	Advertising and market research

  - 74	Other professional, scientific and technical activities

  - 90 Creative arts and entertainment activities

The Contracting authority will supply the list of enterprises with contact information and basic data about the enterprise (including the NACE code and number of employees), mainly based on Orbis, a commercially available database. Exceptions are possible, especially for small countries. For instance, Slovenia is not well covered in Orbis so the administrative business register AJPES will be used as a complement. Nevertheless, the two variables used for drawing the sample (number of employees and the NACE codes) need to be verified during the screener interview.

The sample will be drawn so as to include enterprises that have their main activity in manufacturing and enterprises that have their main activity in services. The sample will also include enterprises described as large with at least 250 employees and enterprises described as small with less than 250 employees. A threshold will be used to include only enterprises with a specified minimum employment to avoid inclusion of very small enterprises.

The contractor is required to collect 2005 complete interviews, namely 215 complete interviews in each of the following countries: Denmark, Finland, Greece, Norway, and Slovenia, and 310 complete interviews in each of the following countries: France, Germany and the UK. The final sample has to reflect the initial sample population with regard to the sector of main activity (manufacturing vs. services), as well as any other variable of interest (e.g. employment size) agreed between the Contractor and the Contracting authority.

The Contracting authority will provide an adequate initial sample and specify relationships between manufacturing and service enterprises. The Contracting authority will provide at least four times the target sample in order to come up with the required number of complete interviews, namely at least 860 units per small country and at least 1240 units per large country. If the contractor cannot achieve the required number of complete interviews despite the agreed data collection strategy, the Contracting authority will provide additional units.

1.2.2 Establishment of contact, respondent identification and interview implementation

The contractor is required to establish contact with the enterprise, conduct a screener interview to verify unit eligibility and identify the right respondent, and conduct the main interview with an appropriate respondent.

The contractor is required to send a formal invitation letter to units. The letter is to be drafted by the Contracting authority and finalised in agreement with the contractor. The invitation letter and the questionnaire are to be sent by email only after the screener interview and respondent identification. The Tenderer is invited to propose other contacting solutions to enhance response based on the experience and knowledge of the response behaviour and available data in the target countries.

To establish the initial contact with the enterprise, the contractor is required to make at least five contact attempts to an enterprise by telephone before discarding it as a non-contact. These attempts should be made at different times of the day and at different days of the week. The record of work should include detailed information on such enterprises, contact attempts and reason for non-response.

Upon contacting an enterprise, a screener interview by telephone should be carried out with two objectives:

- To verify unit eligibility with respect to the economic activity and employment size (see 1.2.1). If the economic activity or employment size is different from those reported on the initial sample but still within the target population, the unit is still considered eligible, otherwise the unit is discarded as non-eligible.

- To identify an appropriate respondent from the top management. The respondent should have a good overview of the enterprise’s strategies, current activities, human resources, and related financial costs. When selecting the respondent, the first choice is the chief executive officer (CEO) or an equivalent executive position leading the enterprise, and the second choice is the chief financial officer (CFO) or an equivalent executive position responsible for financial matters. Other top management positions and assistants to top management positions are acceptable if they have a sufficient overview of the aforementioned topics. The contractor is required to record the position of the respondent as part of the paradata.

After identifying an appropriate respondent, the main interview might start right away or be scheduled for a later point in time. The contractor is required to attempt to conduct the main interview at least three times after the initial scheduling before discarding it as a non-response. The record of work should include detailed information on such enterprises, contact attempts and reason for non-response.

Some questions require reporting of financial data. For this reason, the preferred sequence, especially in large enterprises, is to first send the questionnaire to the selected respondent and then to conduct the main interview so that the respondent has a chance to look at the questionnaire and collect financial data in advance. However, if a respondent is immediately available for the main interview after the screener interview, good estimates are acceptable instead of exact numbers.

With regard to ensuring cooperation of gatekeepers and ultimately respondents, the Tenderer is required to outline its contact and response enhancement strategies, especially with regard to spreading contact attempts, refusal conversion, scheduling of the main interview and follow-up actions. The Tenderer is also required to outline its strategy for minimising non-response bias and facilitating its assessment.

1.2.3 Questionnaire

The Contracting authority will provide the questionnaire in national languages of the countries covered by the tender. The questionnaires will contain approximately 46 questions with an interview duration up to 30 minutes. The Contracting authority will supply to the contractor the Word version to prepare the questionnaire for CATI and the pdf version to be sent to the respondent by email. The Tenderers can get the current English version of the questionnaire by contacting tjasa.redek@ef.uni-lj.si.

1.2.4 Pilot

The contractor is required to carry out a pilot and obtain at least 25 complete interviews. The pilot should be conducted in all countries so that at least three complete interviews per country and altogether at least 25 complete interviews are obtained. The objective of the pilot is to check the contacting and recruiting strategy, the adequate functioning of the survey instrument, interviewer instructions, recording of answers and paradata, as well as any other aspect of survey implementation.

The contractor is required to use the same approach for the pilot as will be used in the actual data collection. After each interview, the interviewer should systematically debrief respondents and note down own observations. The content of debriefing and interviewer notes should be agreed between the contractor and the Contracting authority prior to the pilot.

The contractor is required to provide a report to the Contracting authority on the pilot, including the interviewers’ evaluations, the outcomes of respondent debriefing and a dataset with microdata and all supporting information as specified in 1.2.6.

1.2.5 Field staff and organisation of work

The Tenderer is required to outline the characteristics of the field staff (e.g. the number, language capacity and experience of interviewers by country, etc.) capable of completing the fieldwork to the required standards, with a steady pace, and in the agreed period of time.

The contractor is required to set up a single central coordinator to serve as a point of contact and organise work with a local team in each country covered by the contract. A country team leader has to be appointed for each country.

The coordinator, country team leaders, supervisors and interviewers should have experience with business surveys conducted using CATI. Each supervisor and each interviewer should be assigned a unique ID and appended to all their contacts with enterprises. Interviewers should be native speakers of the language in which they are carrying out interviews.

Before the fieldwork, the contractor is required to provide detailed information on the characteristics of the interviewers that are foreseen for the pilot and the main survey (at least age, gender, native language, English proficiency, level of education, field of education, and relevant experience; relevant experience refers to interviewing in CATI surveys, business surveys, EU-funded projects etc.)) to ensure the high quality of the workforce. This information can be provided in aggregate form before the fieldwork while individual characteristics of each interviewer should be provided together with the contact and paradata dataset.

The contractor should organise a 2-day training in English for interviewers and other team members to become fully familiar with the content, survey objectives and survey procedures before the pilot. The content of training should be agreed with the Contracting authority at least one week before the training. Representatives from the Contracting authority will assist the contractor during the preparations and will also join the training at own costs to answer any questions on the spot. Given the topic complexity, no interviewer should conduct interviews without prior training.

Quality control measures such as regular random checks on interviewers (e.g. listening in on phone calls and/or listening to recorded interviews) should be performed in sufficient extent and for all types of contacts with enterprises. Interviewers should regularly provide feedback from their contacts to be included in the weekly report. Other quality control measures include but are not limited to session duration, item non-response, etc. If an anomaly has been detected, the interviewer should be corrected, retrained or replaced while the results of all previous calls by such interviewer checked and followed up if needed.

The Tenderer is required to outline its training, monitoring and briefing strategies for interviewers.

1.2.6 Data validation, delivery and reporting

Data validation is expected to take place in real-time and should be agreed between the contractor and the Contracting authority to ensure high data quality. For instance, specific validation rules should be embedded in the underlying software and interview script.

The contractor is required to deliver microdata in a single electronic file for all countries using two formats: an SPSS data file with English variable and value labels, and a text data file in English. In addition to microdata, the data file should also contain all supporting information, that is other types of data (contact data, paradata, monitoring data, quality control data) accompanied with captured item-level timestamps. All information should be given in English. Timestamps should allow for re-creation of the whole process with each unit (e.g. exact timing, duration, nature and content of each contact during recruitment and questionnaire implementation, entry of each item, any corrections to the data, etc.). For non-electronic communication, dates are sufficient (e.g. mail shipments if needed). Additionally, the contractor is required to provide data on interviewer characteristics (see 1.2.5).

The Tenderer is required to outline its procedure for recording contact data, paradata, monitoring data and quality control data.

SPSS syntax files must be provided for all the data manipulations that are carried out to produce the micro-datasets, or that underlie quantitative information provided in any of the fieldwork reports.

The contractor is required to provide weekly reports to the Contracting authority indicating the pace and outcomes of the fieldwork overall, and broken down by country and stratification cell. These weekly updates should include the number of discarded units, units without the final disposition (still in the process) and with completed main interview. Specifically, the Contracting authority is interested in the number of:

- successful contacts by type of achievement: screener interview completed, main interview completed, both interviews completed in a single session;

- partly successful contacts by issue: contact established but the screener interview not completed, main interview initiated but not completed;

- unsuccessful contacts by issue: disconnected telephone number, wrong telephone number, non-contact, gatekeeper refusal, ineligible unit, respondent non-contact, respondent refusal.

Additionally, the Contracting authority is interested in the number of interviewers, interviewer workload, feedback from interviewers, the number of monitored calls and their outcome, and any measures taken if the fieldwork is not meeting expectations.

Weekly reports are due by Tuesday of the following week. Interim versions of the microdata file shall be part of these updates. The contractor is also expected to inform the Contracting authority immediately of any unforeseen events or developments impacting the fieldwork progress, and any measures taken to minimise this impact.

The Contracting authority reserves the right to send a representative to attend the fieldwork without prior notice.

The contractor is required to deliver the final technical report with a concise summary of all implementation steps with metrics and issues encountered during fieldwork as well as measures taken to overcome them, overall and on a country by country level.

The contractor must keep all documents relevant to the preparation and implementation for at least five years following the final payment by the Contracting authority.

1.2.7 Meetings

The contractor will be required to organise a physical meeting between the Contracting authority, the coordinator, and the country team leaders prior to the start of fieldwork. The Contracting authority will cover travel and subsistence costs of own representatives.

The Contracting authority will also join the training at own costs when the training is conducted in English.

Other meetings are expected to be held via teleconferences or via videoconferences. One of these meetings must be scheduled after the pilot to discuss the outcome and take the necessary measures prior to the main survey. Another meeting must be scheduled in the second week of the fieldwork after having received the first weekly report. Additional meetings might be held depending on the outcomes of the fieldwork.

1.2.8 Preliminary schedule

The works are expected to start immediately upon the signing of the contract in February 2020. The estimated term of completion of the services subject to the contract is  four months after the signing of the contract. The preliminary schedule is as follows:

Signing of the contract (February 2020)

Preparatory phase (2 weeks)

Pilot (2 weeks for implementation and report)

Field work (10 weeks)

Report and data delivery (2 weeks)

1.2.9 Deliverables

D1 Training for interviewers (due before the start of the pilot)

D2 Report of the pilot (due in four weeks after the signing of the contract)

D3 Data file from the pilot (microdata and all supporting information as specified in 1.2.6) (due in four weeks after the signing of the contract)

D4.1 – D4.10 Weekly reports on fieldwork (due each Tuesday of the following week)

D5 Data file (microdata and all supporting information as specified in 1.2.6) (due date four months after the signing of the contract)

D6 Final technical report (due date four months after the signing of the contract)

D7 Period of ensuring the interpretation of data (5 months after submission of final technical report)

2 Submission of tenders and deadline for submission of tenders

Tenders must be submitted by the deadline for submission to the e-JN information system at https://ejn.gov.si/eJN2 , in accordance with point 3 of the document Instructions for use of the information system for the use of e-JN bidding functionality: Tenderers (hereinafter referred to as the "e-JN User's Guide"), which is part of this tender documentation and is available at https://ejn.gov.si/eJN2 .

The deadline for submission of tenders is 6 February 2020 at 1:00 p.m. (CET).

“Submitted tender” is considered to be a tender, which is marked “SUBMITTED” in the e-JN information system.

The Tenderer may withdraw or modify its tender before the deadline for submission. If a Tenderer withdraws its tender in the e-JN information system, the tender shall be deemed not to have been tendered and shall not be seen by the Contracting authority in the e-JN system. If the Tenderer changes its tender in the e-JN information system, only the last submitted tender shall be considered and visible to the Contracting authority in the system.

Before submitting a tender, the Tenderer must register at https://ejn.gov.si/eJN2, in accordance with the Instructions for use of e-JN. If the Tenderer is already registered in the e-JN information system, it shall login to the application at the same address.

Tender opening will take place on 6 February 2020 at 1:01 p.m. (CET) in the e-JN information system at https://ejn.gov.si/eJN2.

Negotiations

Upon receipt of the tenders, the Contracting authority will verify that the Tenderers do not fulfill the grounds for exclusion and fulfil all the selection criteria and other requirements of the Contracting authority and that the tenders are technically appropriate.

The Contracting authority will invite Tenderers considered qualified to negotiations. Negotiations will be held on the amount of the bid price set out in the Criterion chapter in order to lower the starting bid price. The starting point for the negotiation will be the bid price given in the initial bid.

The Contracting authority will invite to tender 3 Tenderers who will submit the lowest price in the initial tender, or less, if there are fewer tenders or fewer admissible tenders.

Invited tenderers will enter the final bid price in the Bid Estimate-Final Price Form.

Negotiations will take place in one round, solely on the amount of the bid price, it is possible to lower the overall bid price or the bid price of each item (country price). The pro forma invoice with reduced prices per item will be annexed to the contract that the Contracting authority will conclude with the successful Tenderer.

The starting point for the negotiations will be the amount of the bid price from the initial offer, i.e. the Contracting authority will enter in negotiations with the Tenderers in descending order of the amount of the initial offer. The Contracting authority will tell the same desired price to all the Tenderers with whom it will negotiate and the Tenderer will only be able to lower the total tender price from the initial tender.

Negotiations will be held separately with each Tenderer and will last for a maximum of 30 minutes.

The Contracting authority reserves the right not to conduct physical negotiations, but only to invite tenderers to submit an electronic submission.

After negotiations, the bidders will submit the final bid, which they shall enter in the Pro Forma Invoice – Final Bid and submit via the e-JN portal.

Only authorized persons authorized to participate in the negotiations may participate in the negotiations. If the Tenderer who is invited to participate in the negotiations does not participate in the negotiations, the Contracting authority will invoke the financial tender guarantee.

3 Obtaining tender documents and explanations

Tender documentation is available free of charge on the Public Tender Portal (www.enarocanje.si) and on the TED Tenders Electronic Daily (https://ted.europa.eu)

The Tenderer may request further clarification regarding the documentation through the Public Tender Portal no later than 28 January 2020, 11:00 am (CET). The Contracting authority will provide answers through the Public tender portal no later than 30  January 2020, 11:00 am (CET). The Contracting authority will not answer questions that will not be asked in the above manner and by the stated deadline.

The Contracting authority reserves the right to partially amend or change the documentation and, if necessary, extend the deadline for submission of tenders. Changes and amends to the tender documentation are an integral part of the documentation related to the tender.

4 Tender format, language and cost

Tenders shall be submitted electronically in the manner set out in Chapter 2.

The Tenderer must upload to the ESPD tab the completed ESPD form, the completed Tender pro forma invoice form to the "Pro forma Invoice" tab, and all other documentation to the "Other Attachments" tab.

Tenders shall be submitted in the Slovene or English language.

Tender documentation must be given on the forms in the Annex of the tender documentation or on the forms with the same content and format prepared by the Tenderer. Where proof is required, the Tenderer is not required to provide the original, but a photocopy of the proof is sufficient. However, the Contracting authority may, at any time during the tender process, require from the Tenderer to submit the originals for inspection. All documents submitted by the Tenderer must show current status, except where a document for a specific period or a document of a certain age is explicitly required. The Contracting authority may request the documents proving eligibility or the power to obtain the documents subsequently, if they come from an official record (after opening and evaluation process of tenders). In this case, the Contracting authority will ask the Tenderer to provide the Contracting authority with all the documents within the specified deadline for proving the fulfilment of the conditions. If the requested Tenderer fails to deliver the documents, authorizations or supporting documents in a timely manner or if it delivers the documents, authorizations or supporting documents contrary to the requirements of the Contracting authority, the Contracting authority will reject the tender as incomplete.

The selected parts of the tender documentation must be signed by the legal representative of the Tenderer or other person authorized to conclude tenders of the intended type, value and scope.

The services provided must fully comply with the requirements of the tender documentation. If the Tenderer does not offer all services / goods (blank spaces in the tender pro forma invoice) or the offered service does not meet the technical requirements, the Contracting authority will exclude such tender from further evaluation.

If the Contracting authority determines on its own or at the proposal of the Tenderer that the application needs to be supplemented, the Contracting authority shall proceed in accordance with the fifth paragraph of Article 89 of the Public Procurement Act.

The Tenderer shall bear all costs associated with the preparation and submission of the application / offer. In the event of termination of the procedure, rejection of all tenders or cancellation of the public tender, the Contracting authority shall not reimburse the Tenderers for any costs incurred in preparing the tender. Tenderers are aware of this and expressly agree with the submission of the application.

5 Validity of the tender

The tender must be valid until at least until 30 April 2020. In case of shorter validity of the tender, the tender shall be eliminated. Submission of the ESPD form shall be deemed to have been submitted by the Tenderer with a validity of at least the required period.

6 Joint tender

Multiple contractual partners are allowed to tender jointly. Chapter 11 Reasons for exclusion and Chapter 12 Selection criteria determine which condition in the case of a joint tender each partner has to fulfil or which conditions partners can fulfil together.

In the case of a joint tender, the joint tender contract must be submitted in the tender. The joint tender contract must show the following:

- appointment of the lead partner in the execution of the tender,

- authorization of the lead partner and the responsible person to sign the tender and to sign the contract,

- a statement that all Tenderers in the joint tender are aware of and fully agree with the Contracting authority’s instructions and the tender conditions and criteria for the award of the tender,

- a statement that all the Tenderers are aware of the payment terms in the tender documentation,

- provisions concerning the method of payment through the lead partner,

- an indication that they are responsible to the Contracting authority for the entire obligation and for each part of it, all partners jointly and severally.

The offer is signed by the lead partner, who is also the signatory of the tender and the main contact with the Contracting authority. The Tenderer assumes a guarantee against the Contracting authority for the work of other partners and / or subcontractors under the rules of the Obligations Law. The Contracting authority shall require remedy of any shortcomings against the Tenderer.

In the case of a joint tender, the obligatory component of the tender documentation is a copy of the contract, which shows the value, type and scope of the works in the tender assumed by each partner.

7 Subcontracting

The Tenderer who intends to subcontract the contract must state so in the ESPD form. Subcontractors must fill out the ESPD Form and meet the conditions set out in Chapter 11 for subcontractors, which they prove by signing the ESPD form. If the subcontractor will require the payment directly from the Contracting authority, it must submit the request for direct payment, which must be signed by the Tenderer or in case of joint tender the lead partner.

When the Tenderer intends to subcontract the public contract, it must in the tender:

- List all the subcontractors and each part of the public contract that it intends to subcontract.

- List contact details and legal representatives of proposed subcontractors.

- Submit the filled-out ESPD forms of the subcontractors.

- if the subcontractor requests so: enclose the subcontractor's request for direct payment.

If the subcontractor requests direct payment, in the tender it has to include a statement indicating:

- The statement of the subcontractor that it agrees that the Contracting authority pays the claim to the subcontractor instead of the main contractor.

- The statement of the Tenderer that it empowers the Contracting authority to directly pay the subcontractors based on confirmed invoice or intermediate invoice (if allowed).

If the subcontractor does not request a direct payment from the Contracting authority, the Contracting authority will, within 60 days from the payment of the final invoice, request a written statement from the main contractor and the subcontractor that the subcontractor has received the payment for the performed services outlined in the public contract. Failure to submit such a statement will initiate the minor offense procedure according to the provisions of the Public Procurement Act.

If the main contractor is to subcontract the public contract, it must submit the abovementioned proofs in its tender. It also has to submit those proofs in case of a change of the subcontractor in five days after the change at the latest.

The Contracting authority in line with the provision of the fourth paragraph of Article 94 of the Public Procurement Act rejects a subcontractor who fulfills the compulsory and non-compulsory grounds for exclusion.

If the Contracting authority determines that the replacement of a subcontractor or inclusion of a new contractor would disturb the work or that the new subcontractor does not meet the requirements for the subcontractors specified by the Contracting authority, the Contracting authority will reject the subcontractor within 10 days of receipt of the proposal to replace or include a new subcontractor.

The Tenderer assumes the responsibility for the execution of the entire public contract, including the subcontracted works.

In the case of subcontracting the public contract, the tender application must include the copy of the contract which outlines the type, value and the scope of subcontracted work.

8 Confidentiality

The Contracting authority shall not disclose any information that the business entity provides and labels as confidential. The Contracting authority shall ensure protection of personal data and classified information in accordance with legislation regulating personal data and classified information.

The Tenderer shall label as “confidential” or “business secret” those forms or statements that the Tenderer considers within the scope of data protection legislation.  If only a specific datum is considered confidential in a form or document, the confidential part shall be underlined and the line on which this part appears shall be labelled as “confidential” or “business secret” at its right margin. The Tenderer may submit a non-disclosure agreement to the tender.

9 Provision of information to the Contracting Authority

The successful Tenderer shall, at the request of the Contracting authority, provide information on:

- its founders, company members, stakeholders, limited partners or other owners and information on the equity of those persons;

- Commercial entities, considered to be affiliated companies according to the provisions of the law governing companies.

10 Change in the scope of the object of the contract and conclusion of the contract

The Contracting authority reserves the right to conclude the contract with the selected Contractor only in the case of sufficient funds. In case of the absence of sufficient resources, the Contracting authority will not conclude the contract. In the event that the Contracting authority does not have all the financial and other resources provided, the Contracting authority reserves the right not to select any Tenderer or to cancel the public contract or to reduce the volume of supply.

By signing the ESPD form, the Tenderer demonstrates an understanding and agreement with the above paragraph.

Pursuant to Article 89 of the Public Procurement Act, the Contracting authority reserves the right to terminate the procedure, reject all tenders, and withdraw from the performance of the contract.

The contract will be concluded under the suspensive condition of submission of performance guarantee as set out in the sample contract.

If the Tenderer does not respond to the invitation to sign the contract within five (5) days, the Contracting authority may consider the Tenderer has withdrawn from the tender. In such a case, the Contracting authority can invoke the financial tender guarantee submitted by the Tenderer. The Contracting authority may also claim any additional damages resulting from such conduct of the selected Tenderer. The Contracting authority also reserves the right to bring procedures for the signature of the contract to the court if it would be in the Contracting authority’s interest.

11 REASONS FOR EXCLUSION

The Contracting authority will exclude from the public procurement procedure the Tenderer who will fulfill the following grounds for exclusion.

11.1. Prior impunity

The Contracting authority will exclude from the participation in the public procurement procedure the Tenderer if the Tenderer or the person who is a member of the administrative, managerial or supervisory body of that Tenderer, or who has the power to represent it or to decide or supervise it, has been convicted by a final judgement for criminal offenses defined in the Criminal Code (Official Gazette of the Republic of Slovenia, No. 50/12 – official consolidated text and 54/15, hereinafter: KZ-1) and listed in article 75 of the Public Procurement Act.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

11.2. Inclusion on the list of tenderers with negative references and records of business entities from ZintPK (Law on Integrity and Prevention of Corruption)

The Contracting authority will exclude from the participation in the public procurement procedure the Tenderer if, on the day on which the deadline for submitting the tender expires, the Tenderer is excluded from the procedures for the award of public contracts due to listing in the register of economic entities with negative references.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

11.3. Unpaid taxes and social contributions

The Contracting authority will exclude the Tenderer if it finds that at the date of the submission of the tender, the Tenderer has not complied with its obligations relating to the payment of compulsory charges or other pecuniary non-tax liabilities under the law governing financial administration, collected by the tax authority in accordance with the regulations of the country in which it is established or with the regulations of the country of the Contracting authority, where those unpaid overdue liabilities total EUR 50 or more.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

11.4. The fine in respect of work remuneration

The Contracting authority will exclude from the participation in the public procurement procedure the Tenderer if, in the three years preceding the expiry of the time limit for the submission of tenders, the Tenderer was fined twice, by way of a final decision of the competent authority of the Republic of Slovenia or another Member State or a third country, for a minor offence relating to remuneration for work and the Tenderer has been the subject of a finally legal sanction for such an infringement.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

11.5. A serious breach of professional rules

The Contracting authority will exclude the Tenderer from the procurement procedure if the Contracting authority by appropriate means proves that the Tenderer has committed a serious breach of professional rules, which undermines its integrity.

Final decisions of the inspection bodies are considered as appropriate means.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

11.6. Significant professional mistake

The Contracting authority will exclude from the procurement process a Tenderer who is proven to have committed a significant professional error in its business undertaking.

A significant professional mistake is an expert and professional error in carrying out of works comparable to the object of the public contract, which indicate a serious unprofessional behaviour of the Tenderer; low-quality performance of services, the performance of services with inadequate staff, provision of services contrary to the regulations and the instructions, violation of statutory regulations and similar.

The Contracting authority will establish if the significant professional error was made on the basis of written evidence; rightly enforced guarantees (financial insurance), final court decisions indicating unprofessional performance of works and intentional breach of the provisions of contracts concluded in the last five years before the deadline for the submission of tenders, records of low-quality performance of services, sanctions imposed by the final acts issued by competent authorities bodies, sanitary inspection decisions, early termination of the contract due to the Tenderer’s conduct which is contrary to the provisions of the contract.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

11.7. Insolvency

The Contracting authority shall exclude from the procurement procedure a Tenderer which:

- Is in the procedure of compulsory settlement or the petition for instituting a compulsory settlement procedure has been presented and the court has not yet decided on the petition;

- Is in a bankruptcy proceeding or a petition for bankruptcy has been presented and the court has not yet decided on the petition;

- Is in the compulsory dissolution proceeding or a petition for compulsory dissolution has been presented and the court has not yet decided on the petition, its business is managed by the court for other reasons or it has suspended its business activity or is in similar position.

Reason for exclusion refers to each partner in case of a joint tender and to each subcontractor if applicable.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

12 SELECTION CRITERIA

12.1 Registration of activity

The Tenderer must have the activity that is subject of this tender registered.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

12.2. Acting in accordance with the standards for best practice in marketing and social research

The Tenderer must prove its commitment to work in in accordance with the standards for best practice that are accepted in their field by providing certificates of membership of ESOMAR, WAPOR or an equivalent body.

PROOF: The Tenderer/partner/subcontractor completes the ESPD form.

12.3 Criteria related to the Tenderer

The Contracting authority recognises competence of the Tenderer that proves extensive experience in the field of cross-national business surveys conducted by telephone (CATI) by having implemented at least 5 comparable similar contracts undertaken during the last five years before the publication of this tender. Relevant surveys are those that were conducted as computer-assisted telephone interviewing (CATI) in at least three countries and achieved complete response from at least 1000 enterprises overall.

The list of references that the Tenderer submits to the Contracting authority has to include: names of contracting authorities, types and number of organisations surveyed, topic, targeted respondents, geographical coverage, period of implementation, description of team composition and experience, and contractual price.

The Tenderer must list at least five relevant references, three out of which have to be accompanied by written evidence of satisfactory execution, specifying that surveys have been carried out in a professional manner and have been fully completed (e.g. a copy of final technical report, statement of a contracting authority).

The Tenderer may fulfil the criteria jointly with partners or subcontractors.

PROOF: The Tenderer completes the form References of the Tenderer. The Tenderer attaches at least three certificates of the reference (see Sample for Certificate of the Reference in the Annex) or other documents with the same content.

12.4 Criteria related to the teams

The Tenderer must prove to have the organisational capacity to carry out the contract, on its own, with partners or subcontractors, by describing its organisational structure, manpower and technical infrastructure in all countries covered by the contract.

The Tenderer has to nominate the central coordinator and the country team leaders in its offer. The Tenderer must prove to have adequate human resources in targeted countries to carry out the contract in quality and timely manner by providing the number of staff working in the area of the contract by country and CVs of staff proposed to work on carrying out the contract. CVs should preferably be submitted in the Europass format.

The Tenderer must ensure that the central coordinator has:

- a minimum of five years of experience in the coordination of cross-national telephone surveys, of which at least one business surveys,

- a minimum of five years of experience in the implementation of business surveys,

- a minimum of five years of experience in operating as a team leader in surveys,

- proficiency level in English at least C1.

The Tenderer must ensure that the country team leaders have:

- a minimum of five years of experience in the implementation of business surveys,

- a minimum of five years of experience in operating as a team leader in surveys,

- proficiency level in English at least C1.

The Tenderer may fulfil the criteria jointly with partners or subcontractors or based on employment or contractual law.

PROOF: The Tenderer completes the form Team competences and attaches CVs of the nominated personnel.

12.5 Implementation plan

The Tenderer has to provide a document with an implementation plan specifying:

- organisational capacity to carry out the contract (i.e. organisational structure, manpower and technical infrastructure in the countries covered by the contract);

- proposed project management (i.e. time plan, work organisation and co-ordination, resource allocation and identification of critical risks for implementation and proposal of appropriate risk mitigation measures);

- proposed field force description (i.e. qualifications and experience of staff assigned to interviewing, interviewer training, monitoring and feedback);

- proposed pilot test implementation;

- proposed methodology underlying main data collection (i.e. contact, response enhancement and follow-up strategies; minimisation of non-response bias; quality assurance measures).

Before the fieldwork begins, the contractor will be asked to provide more detailed information on the qualifications and experience of the proposed interviewers and fieldwork supervisors in each country. This information shall be updated by the contractor on completion of the fieldwork.

The Tenderer may fulfil the criteria jointly with partners or subcontractors or based on employment or contractual law.

PROOF: Document with an implementation plan.

13 Financial insurance

The Tenderer must provide financial guarantees to the Contracting authority to insure its obligations, as set out in the samples of financial guarantees and declarations in the tender documentation, or in the documents which may not differ in content from the samples of financial guarantees contained in the tender documents. The Tenderer may also provide, as a financial guarantee, adequate insurance with the insurance companies, which in substance should not differ significantly from the financial guarantee sample.

In the case of subcontracting, the insurance is submitted by the main Tenderer and, in the case of a joint tender, the lead partner.

The successful Tenderer with whom the Contracting authority concludes the contract, guarantees the elimination of all types of errors or irregularities, in accordance with the provisions of the Obligations Code and the regulations governing the subject matter of the contract.

13.1 Financial tender guarantee

The Tenderer must, by the deadline for tender submission, submit in physical form an unconditional, without protest and redeemable on demand, promissory note declaration and a bill of exchange in value of 2,500.00 EUR. The financial tender guarantee must be valid until at least 30 April 2020 with the possibility of extension upon the request of the Contracting authority.

The content of the submitted promissory note declaration must correspond to the content of the sample as it appears in the form Promissory note declaration. The Tenderer must submit 1 promissory note as a mandatory attachment to the form Promissory note declaration -tender guarantee.

The tender guarantee will be invoked in the following cases:

•	if the Tenderer withdraws or changes the tender within the period of its validity as indicated in the tender or

•	if the Tenderer who was informed by the Contracting Authority of the acceptance of its tender during the period of validity of the tender:

-	refuses to conclude the contract or does not fulfill the contract in accordance with the provisions of the instructions to the tenderers or

- does not submit or refuses to submit a performance guarantee in accordance with the provisions of the instructions to tenderers or

- does not submit a new promissory note declaration upon the request of the Contracting authority in case of extension of the validity of the tender.

Promissory note declaration which has not been invoked shall be returned to the Tenderer upon its request after completion of the procurement procedure.

The Tenderer must submit the promissory note declaration and the bill of exchange to the Contracting authority in physical form to the address of the Contracting authority by the deadline for the tender submission. If the Contracting authority does not receive the bill of exchange together with the promissory note declaration on time, the tender will be considered late and inadmissible, and will consequently be excluded.

13.2. Performance guarantee

The successful Tenderer must, as a condition for the validity of the contract, no later than twelve (12) days after the conclusion of the contract, submit to the Contracting authority a bill of exchange and a promissory note for the good performance of the contractual obligations in the amount of 5% of the bid value excluding value-added tax.

The Tenderer must also submit its statement in the form Statement about the submission of bill of exchange for god performance of the contractual obligations from tender documentation, that it will deliver the bill of exchange and promissory note for good performance of contractual obligations in twelve (12) days after the conclusion of the contract. The Tenderer signs and stamps the form Promissory note for good performance of contractual obligations. The bill of exchange has to be valid at least 40 days after the expiry of the contract.

14 Award criteria

The Contracting authority will award the contract to the Tenderer with the most economically advantageous offer. The quality of the tender will be evaluated based on financial evaluation of the offers (see 14.1) and additional references of nominated staff (see 14.2).

Each offer may achieve:

- a maximum of 70 points according to financial evaluation of the offers (70 % of the total) – criterion T1,

- a maximum of 30 points according to additional references of nominated staff (30 % of the total) – criterion T2.

The total number of points that an offer achieves is calculated in such a way that first, the number of points achieved is determined for each criterion, and then, the points are summed up.

14.1 Financial evaluation of offers

The number of points that the offer of an evaluated Tenderer receives for the financial criterion will be calculated according to the following formula:

T1=70∙CmC

Cm	...	the lowest price offered (in EUR without VAT)

C	...	the price of the specific Tenderer (in EUR without VAT)

T1	...	number of points

The Tenderer must provide the total price exclusively in euros. The price has to be given without VAT.

All payments from this tender will be made exclusively in euros.

The price offered must take into account all constituent elements and must include all costs so that no costs related to the subject of the tender can be charged to the Contracting authority.

The Tenderers must take into account all elements that have an impact on the price calculation such as, but not limited to, labour costs, overhead, any overtime, travel and subsistence costs, cost of equipment, any translation costs, other costs related to the public procurement procedure, and all other elements that influence the price calculation.

14.2 Additional references of nominated staff

The Tenderer that will nominate staff who can provide at least the following references in the last five years since the publication of the tender (so that the service was completed 5 years before the publication of the tender at the latest) will receive additional points:

| Nominated staff | Description of additional reference | Number of points for references |
| --- | --- | --- |
| Central coordinator | Coordination of at least two cross-national (involving at least three different countries) business surveys conducted using CATI in the last five years | 6 points |
| Country team leader | Participation in the implementation of at least three national business surveys conducted using CATI in the last five years | 3 points per country team leader with requested references (for a maximum of 24 points in total) |

14.3 Awarding of the contract

Among the tenderers that are authorised to participate in the tendering procedure and fulfil all selection criteria, the contract will be awarded to the Tenderer that received the highest number of points. If two or more Tenderers receive the same number of points, the Tenderer will award the contract to the one with a lower price offered or the one randomly chosen if the price offered is the same.

PROOF: The Tenderer states the price of each item and the number of references of nominated staff in the form Tender proforma invoice – initial bit.

15 Legal basis

In the process of awarding a public contract and during the execution of a public contract, the following must be taken into account:

- Public Procurement Act (Official Gazette of the Republic of Slovenia, No. 91/2015, as amended);

- The Law on Legal Protection in Public Procurement Procedures (Official Gazette of the Republic of Slovenia, No. 43/2011, as amended, hereinafter: ZPVPJN)

- Obligations Code (Official Gazette of the Republic of Slovenia, No. 97/07, as amended);

- all applicable legislation governing the subject of the public procurement contract.

16. Legal recourse

A request for an audit relating to the content of the announcement, the invitation to tender or the tender documentation shall be made within ten working days of publication of the tender notice or receipt of an invitation to tender.

Where the Contracting authority changes or adds the provisions in the notice, the invitation to tender or in the tender documentation, the request for audit regarding the amended, added or clarified content of the notice, the invitation or the tender documentation or the directly related statement in the original notice, the invitation to tender or the tender documentation, shall be submitted within ten working days of the date of publication of the notice about additional information, information on the pending procedure or correction, if this notice changes or adds the requirements or criteria for the selection of the most economically advantageous tenderer.

The request for the audit must contain all the information and proof as provided for in article 15 of the ZPVPJN. Pursuant to the second indent of the first paragraph of article 71 of the ZPVPJN, the fee for filing an application for an audit relating to the content of the publication, the invitation to tender or the tender documentation if the subject of the public procurement is goods and services is EUR 4.000,00. The fee is paid to the transaction account opened with the Bank of Slovenia, Slovenska cesta 35, 1505 Ljubljana, Slovenia no. SI56 0110 0100 0358 802, SWIFT code BS LJ SI 2X, IBAN SI56011001000358802 and reference 11 16110-7111290XXXXX.

prof. dr. Metka Tekavčič

Dean

Annex

Tender pro forma invoice – initial bid

The Tenderer _______________________________________________________________,

who in the process of awarding a public contract »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project«, offers an offer, quotes the bid price in EUR without VAT:

| Country | Price in EUR without VAT |
| --- | --- |
| Survey implementation in Denmark |  |
| Survey implementation in Finland |  |
| Survey implementation in France |  |
| Survey implementation in Germany |  |
| Survey implementation in Greece |  |
| Survey implementation in Norway |  |
| Survey implementation in Slovenia |  |
| Survey implementation in the UK |  |
| Other services not included elsewhere |  |
| Total in EUR without VAT |  |

(the form continues on the next page)

| Staff | Number of relevant references (references of nominated staff as specified in point 14.2.) |
| --- | --- |
| Number of references of central coordinator |  |
| Number of references of country team leader in Denmark |  |
| Number of references of country team leader in Finland |  |
| Number of references of country team leader in France |  |
| Number of references of country team leader in Germany |  |
| Number of references of country team leader in Greece |  |
| Number of references of country team leader in Norway |  |
| Number of references of country team leader in Slovenia |  |
| Number of references of country team leader in the UK |  |

Place and date:                                                       stamp and signature of the authorised person

Bill of Exchange Statement for tender guarantee

As collateral for the guarantee of the »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project« tender ________________________________________ we deliver to the contracting authority University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia one (1) blank bill of exchange with the authorised representative:

______________________                                        _________________________

(signature of authorised representative)

We hereby authorise University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia, to fill out this blank bill of exchange in the amount of 2.500,00 EUR. We also authorise University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia to fill out all other blank sections of the bill of exchange and uses the filled out bill of exchange for the purpose it was issued (collateral for tender guarantee). The bill of exchange statement and the bill of exchange are delivered without objection, at the first call and unconditionally. University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia may not make a draft.

We authorise the University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia to domicile the bill of exchange at _ _ _ _ _ _ _ _ _ _ _ _ _ _ (the authorised entity), keeping our transaction account, number _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _. University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia may present the bill of exchange for payment until 30 April 2020 at the latest, with extending option.

Place and date: 						   Security issuer:

Mandatory appendix: 1 x Blank bill of exchange

Declaration on submitting the bill of exchange statement for the proper performance of contractual obligations

Regarding the »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project« procurement, published on the Public Procurement Portal on ____________(date), under the Publication No.____________________, _______________________________________(name and address of the supplier) I declare we will deliver the bill of exchange statement with a blank bill of exchange to the contract authority in 12 days after signing the public procurement contract, in line with the Bill of exchange statement for the proper performance of contractual obligations model, for the amount of 5 % of the tender value, including VAT.

Place and date:                                                                                      Stamp and signature of the supplier

Bill of Exchange Statement for the proper performance of contractual obligations

The below signed legal representative or authorised party

___________________________________________________________________________

of the selected supplier

(the company and registered seat of the company or sole proprietor)

In the procedure of awarding the »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project« public procurement, I irrevocably declare to authorise the University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia to fill out the signed blank bill of exchange delivered as collateral for the proper performance of contractual obligations under the contract, concluded on the basis of the awarding procedure for public procurement of »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project«, in line with the provisions of the tender documents, the tender and the contract for this public procurement, without prior notice in all blank sections for the amount of _________ EUR. The selected supplier waives all objections to the bill of exchange filled out as described and undertakes to pay the bill of exchange at its maturity in cash. This authorisation ceases 40 days after validity of the framework agreement expires. The amount of the bill of exchange is transferred on the account of the contracting authority, University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia, No.___________________________.

The supplier declares to be aware of the legal consequences of issuing a bill of exchange as collateral. The bill of exchange must be filled out with the clause “WITHOUT OBJECTION”. The supplier also authorises the Contracting authority University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia, to present the bill of exchange for payment and explicitly grant permission to the bank to pay out such bill of exchange. I hereby give a payment order or authorisation to all the banks listed below from the following my accounts:

If I open another account that is not listed above, I explicitly allow the bill of exchange to be paid out and I authorise the bank, where such an account is opened, to execute the payment.

The bill of exchange statement is valid 40 days after validity of the agreement expires.

Date:  							Signed (name and surname)

Signature and stamp:

Mandatory appendix: a blank bill of exchange

References of the Tenderer

In the process of awarding a public contract »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO / A telephone business survey (CATI) in several European countries for the GLOBALINTO project«, we notify the following information for each reference:

| Reference name (specify the service notified as a reference, including the survey topic) |  |
| --- | --- |
| Contracting authority |  |
| Type and number of organisations surveyed |  |
| Target respondents in organizations |  |
| Geographical coverage |  |
| Period of implementation and date of contract finalisation |  |
| Description of survey team composition and experience |  |
| Contractual price (in EUR without VAT) |  |

Place and date:                                            Stamp: 			Signature of the Tenderer:

Certificate of the Reference (see also 12.3)

Contracting authority that the Tenderer has provided services for which the reference is notified:

…………………………………………………………………………………………………

(name/title of referee)

DECLARE, that the contractor

…………………………………………………………………………………..

(list the name of the contractor)

implemented ……………………………………………………………………………..

……………………………………………………………………………………….

(list the title and description of implemented services)

in the period from ……………….. to……………….. and that on the following date …………….. the services were completed,

in the total value of …….…………………………………………….EUR (excluding VAT),

and dully respected our requirements and complied with the contractual provisions, and we evaluate the Tenderer's work as a professional, quality and conducted the performed service in accordance with the regulations.

Contact person of the contracting authority: ………………………………………………………………

Telephone …………………………………………………..

E-mail …………………………………………………

Place and date: ………………………………………

Stamp and signature of the contracting authority

The Contracting authority reserves the right to verify the provided data.

Team Competences (see 12.4.)

The Tenderer  _______________________________________________ (name and address), in the process of awarding a public contract »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project« nominates the following team that fulfills the conditions from the tender documentation:

(please, fill in the form in continuing)

| Role | Nominated person (name and surname, job title) | Experience in co-ordination of cross-national telephone surveys (in years) | Experience in co-ordination of cross-national telephone business surveys (number) | Experience in the implementation of business surveys (in years) | Experience in operating as a team leader in surveys (in years) | Proficiency level in English |
| --- | --- | --- | --- | --- | --- | --- |
| Central coordinator |  |  |  |  |  |  |
| Team leader Denmark |  | / |  |  |  |  |
| Team leader Finland |  | / |  |  |  |  |
| Team leader France |  | / |  |  |  |  |
| Team leader Germany |  | / |  |  |  |  |
| Team leader Greece |  | / |  |  |  |  |
| Team leader Norway |  | / |  |  |  |  |
| Team leader Slovenia |  | / |  |  |  |  |
| Team leader UK |  | / |  |  |  |  |

I declare that the nominated team fulfills all criteria related to the teams as set out in 12.4.

Place and date:                                            Stamp: 			Signature of the Tenderer:

Mandatory annex: CVs of staff nominated to work on carrying out the contract, preferably in the  Europass format.

# Sample contract

University of Ljubljana, School of Economics and Business, Kardeljeva ploščad 17, 1000 Ljubljana, Slovenia, represented by dean prof. dr. Metka Tekavčič,

Identification number for value-added tax: SI 28186745,

Registration number: 1626922000

(hereinafter: Contracting Authority)

and

Tenderer: __________________________________________________________________

Represented by:_____________________________________________________________

Registration number:________________________________________________________

VAT number:___________________________________________

Banking account (IBAN): ____________________________________________________, opened at bank (with SWIFT) ___________________________________________________

(hereinafter: Contractor)

Are concluding

CONTRACT FOR SERVICES OF SURVEY RESEARCH

GENERAL PROVISIONS

Article 1

The Contracting Authority has conducted a public procurement procedure  »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project«, which was published on the Public Tender Portal under notice number JN___________ and the European Union Portal under number ___________________.  The  Contractor was chosen as economically advantageous tender service provider based on the decision to award the contract dated __________ .

Procurement documentation and tender documentation of the Contractor are an integral part of this contract.

OBJECT OF THE CONTRACT

Article 2

The object of the contract is the implementation of a telephone business survey using the CATI (Computer Assisted Telephone Interviewing) method (hereinafter: survey). The  Contractor will conduct the survey by obtaining complete interviews at least in the following extent:

- 215 complete interviews for each of the following countries: Denmark, Finland, Greece, Norway and Slovenia and

- 310 complete interviews for France, Germany and the United Kingdom.

The Contractor will conduct the survey based on the questionnaire and the sample as provided by the Contracting Authority. The object of the contract is also providing additional information regarding survey implementation and interpretation of the data or providing other information required by the Contracting Authority for the period of five months after submitting the final technical report.

The scope and the method of the survey and the reporting on the obtained responses are detailed in the tender documentation (in the requirements for tenderers including all the changes and clarifications and in other tender documents), based on which this contract was awarded.

In addition to the activities specified in this contract, the contractor is required to conduct also other activities that are required for obtaining relevant data, i.e. the data that allows the Contracting Authority the use of the data in accordance with the purpose.

Article 3

The Contractor is obliged to conduct a pilot survey in which it will assure at least 25 complete interviews overall, with at least three complete interviews per each of the countries listed in Article 2 of this contract.

The Contractor shall prepare and submit report, which will summarize the findings of the pilot survey and inform the Contracting Authority about the findings.

The Contracting Authority reserves the right to modify and complement the questionnaire, in any manner that does not impact the questionnaire length.

Modification of the questionnaire is not considered a change of scope of service.

Article 4

The object of the contract includes also the type and method of processing of personal data and defining the rights and obligations of the parties in line with this contract and with the provisions of Personal Data Protection Act (Uradni list RS, št. 94/07 –, ZVOP-1) and the Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data, and repealing Directive 95/46/EC (General Data Protection Regulation-  GDPR).

CONTRACT VALUE OF SERVICE

Article 5

The value of the contract is determined based on the tender of the Contractor and is ___________ EUR without the value added-tax, and ___________ EUR including the value-added tax.

The value of the contract with the value-added tax includes all costs, taxes and any discounts, so that the Contracting Authority is not charged any costs connected to the object of the public contract, such as labour costs, overhead costs, the costs of providing necessary technical equipment, availability, travel expenses, cost of reporting, cost of other accompanying tasks necessary for effectively carrying – out the services and all other elements that affect the calculation of the price.

The Contractor agrees to undertake any needed coordination with the Contracting Authority and other stakeholders.

OBLIGATIONS AND RESPOSNIBILITIES OF THE CONTRACTOR

Article 6

The Contractor undertakes to provide services set out in this contract on time, according to quality standards, diligently and according to the rules of the profession and in line with the applicable regulations. It undertakes to ensure that the execution of the services will be cost-efficient and in line with the provisions of this contract and other possible agreements between the parties.

The Contractor is obliged to:

- Fulfil his obligations conscientiously and fairly, with the professional diligence;

- Ensure that the staff of the Contractor will be properly trained to carry out the contract obligations;

- Have a sufficient number of staff or contractual employees to carry out the public contract the entire time;

- Cooperate with the representatives of the Contracting Authority;

- Use advanced technologies and methods to perform his duties from the contract;

- Carry out its service in line with the submitted tender, this contract and requirements of the Contracting Authority;

- Carry out its duties within the deadlines specified in the tender documentation for awarding the contract and within the deadlines agreed with the Contracting Authority;

- Provide the contracting authority the necessary information regarding the object of this contract also after the completion of its tasks;

- Comply with the legal obligations and Contracting Authority's rules for safeguarding and protection of the personal data and professional secrecy and will destroy all personal data and information about the answers of respondents. The Contractor will forward the record of destruction to the Contracting Authority after the survey is completed;

- Not to analyse the results of the survey by itself, except in the scope set out in this contract;

- Immediately and timely inform the Contracting Authority about any circumstances that could impede or make it impossible to carry out the service correctly and in line with quality standards.  It will search for alternative ways of work in cooperation with the Contracting Authority;

- Allow the Contracting Authority to undertake adequate supervision;

- Protect Contracting Authority's interests and warn it in writing of any obstacles in carrying out of the contractual obligations;

- Inform the Contracting authority if it is in conflict of interests and suggest the management of such a conflict;

- Fulfil all other obligations based on this contract.

In case of the replacement of the nominated staff of the Contractor, the new staff must fulfil all the personnel qualification requirements. The Contractor must inform the Contracting Authority about any intended change of nominated staff. For any change of the nominated staff, the Contractor must obtain a prior written consent of the Contracting Authority.

Any additional staff to provide the services as well as replacement in nominated staff is considered a change of staff. The Contracting Authority has the right to check the actual situation at any time. The Contracting Authority reserves the right to prohibit certain staff from carrying out the subject matter of this contract without giving reasons.

The Contracting Authority can refuse to accept the performed services if they do not meet the requirements of the Contractor’s tender, tender documents or professional standards.

In the event that the contractor fails to fulfil the contractual obligations in the manner stipulated in the public procurement contract, the Contracting Authority shall initiate appropriate procedures for its termination and invoke the performance guarantee.

Article 7

The Contractor will use the information provided by the Contracting Authority solely for the performance of the services set out in this contract.

The Contractor shall keep the information provided by the Contracting Authority confidential. The information will only be used by those employees of the Contractor who will be involved in the execution of the work under this contract, whereby the Contractor is obliged to inform them and to warn them of the trade secret clause.

Article 8

The Contractor undertakes to carry out all work under this contract within 4 months after the signing of the contract. Individual activities will be performed by the Contractor within the deadlines specified in the technical specifications of the procurement documents (instructions to tenderers).

OBLIGATIONS OF THE CONTRACTING AUTHORITY

Article 9

The Contracting Authority undertakes to:

- make available to the Contractor all the necessary data, information, and documents needed to carry out the services under this contract within 8 (eight) days from entering of the contract  in force or the performance of the individual service agreed upon with this contract;

- cooperate with the Contractor in order for him to provide the services in a timely and complete manner and in mutual satisfaction;

- promptly inform the Contractor of any changes that may affect the performance of the services under this contract;

- pay for confirmed and performed services within the agreed deadlines;

- actively cooperate with the Contractor so it will be able to carry out the services under this contract in line with quality standards.

BILLING AND PAYMENT OF PROVIDED SERVICES

Article 10

The Contractor shall bill the service and issue an invoice no later than 10 days after the completion of all services under this contract. The Contractor issues the invoice electronically.

In case of late payment, the Contractor may charge default interest in accordance with the regulations in force.

The Contracting Authority will pay the invoice within 30 days of the receipt of the invoice. The day on which the Contracting Authority submits the payment order to the organization with which it has its account shall be considered as the day of payment and fulfilment of the Contracting Authority’s obligation.

The Contracting Authority undertakes to transfer the payment for invoice for the performed and confirmed services to the transaction account of procurement service provider no. _____________________, opened at ____________________.

In case of late payment by the Contracting Authority, the Contractor may charge statutory default interests.

Should the subcontractor request direct payment in accordance with the Instructions to the tenderers, in that case the bills of subcontractors, previously confirmed by the main contractor, are mandatory appendices to the bill of the main contractor. The deadlines for direct payments to subcontractors are the same as for the payments to the main contractor. In case the subcontractor does not require direct payment by the Contracting Authority, the Contractor must, within 60 days from the payment of the final bill, provide the Contracting Authority with a written statement from the Contractor and subcontractor stating that the subcontractor has received payment for the services performed in this public contract. If the statement is not submitted, the Contracting Authority will initiate the minor offense proceeding according to the provisions of the Public Procurement Act.

In the event that the subcontractor requests direct payments, the Contractor agrees to direct payments by signing this contract.

The Contracting Authority reserves the right to reduce the scope of the services provided without giving any reasons. In the case of reducing the scope of contracted works, the Contractor is entitled to reimbursement for the services already provided.

PERFORMANCE GUARANTEE

Article 11

The Contractor must, within 12 (twelve) days after concluding the contract, provide the Contracting Authority with a performance guarantee, namely a bill of exchange with a bianco promissory note of 5% of the value of the contract excluding VAT, as a guarantee for quality and timely execution of the works. The Contracting Authority can redeem it:

- in the event of the Contractor’s withdrawal from the contract before or during the carrying-out of the tasks because of the contractor's fault,

- in case of insufficient quality of performed works,

- in case of late or untimely performance of the services,

- for payment of the costs and damages arising from late or low-quality performance of services,

- in the event of a mutually extended deadline, if  the Contractor fails to deliver the extension of the validity of the performance guarantee by the deadline specified in the annex to the contract,

- if the Contractor breaches the confidentiality of the data,

- in other cases of breaching the contractual provisions.

PROTECTION OF PERSONAL DATA AND BUSINESS SECRETS

Article 12

When carrying out  their contractual tasks, the contracting parties undertake to fully comply with the provisions of this contract, ZVOP-1, and GDPR, regardless whether they come in contact with the personal data when directly performing services in the field or at the location of the Contractor or Contracting Authority, or while monitoring the implementation of the provisions of this contract, through written documentation or in any other direct or indirect way.

The Contractor is obliged to ensure that the service under this contract is performed in accordance with the legislation valid in the country where the research is conducted. The Contractor is obliged to inform the Contracting Authority of any obligations of the Contracting Authority that would arise in other countries as a result of contracting works under this contract.

The Contractor is obliged to protect personal data which the Contractor will be acquainted with or will process in the course of this contract in accordance with applicable law.

For the purpose of carrying out the tasks from this contract, the Contracting Authority will not provide the Contractor with personal information, nor will the Contracting Authority receive personal information from the Contractor.

The Contractor will process personal and other data with which it will become acquainted in the course of this contract, only for the purpose of carrying out the object of this contract or survey and for no other purpose.

In the event of termination of contract / termination of the validity of the contract or upon special request of the Contracting Authority, the Contractor will immediately  destroy any personal data that it processes and the supporting documentation.

Article 13

The Contractor may only delegate the processing of personal data to third parties who are subcontracted in accordance with the procurement documentation. The subcontractor performing the processing must be subject to the same data protection obligations as the Contractor under this contract.

The Contractor will assist the Contracting Authority in fulfilling all obligations under the law on personal data protection.

The Contractor will immediately inform the Contracting Authority if it establishes that a certain instruction is contrary to the provisions of the applicable regulation concerning the protection and processing of personal data. The Contractor will also immediately inform the Contracting Authority upon detection of breaches of personal data protection.

Article 14

Throughout the duration of this contract, The Contractor undertakes to provide the appropriate procedures and measures required by the national law of the country in which the services under this contract are provided and by the GDPR.

Article 15

The Contractor may entrust individual tasks related to the processing of personal data to a subcontractor who is registered to perform such activity only with the prior written consent of the Contracting Authority. The subcontractor must perform the duties in the same way as the Contractor under this contract.

For each subcontractor / contract data sub-processor, the Contractor specifies in a written contract for the processing of personal data which databases or what types of personal data the subcontractor may access, categories of data subjects, deadlines for the subcontractor to  erase personal data, what powers the sub-processor has (it may not process personal data for any purpose other than the purpose set out in this contract) and what measures and procedures it must take or implement to protect personal data. For each processing of personal data the contracting sub-processor must ensure procedures and measures for the protection of personal data that are as stringent or more stringent as those performed by the Contractor under this contract.

The performance of the subcontractor's obligations regarding processing personal data in accordance with this contract shall be the responsibility of the Contractor as if it had performed the processing itself and shall be fully responsible to the Contracting Authority for the fulfilment of the obligations of its subcontractor /contracting sub-processor.

In the event of a dispute between the Contractor and the sub-contractor, the subcontractor is obliged to immediately or upon the request of the Contractor return to the Contractor or the Contracting Authority the personal data it has processed. Any copies of the personal data must be immediately destroyed or forwarded to a state authority competent to detect or prosecute criminal offenses under the law, to a court or other state authority, if required by law.

Article 16

The Contractor is obliged to protect the information that he would become aware of when performing the services, subject to this contract as professional secrecy.

The provisions of professional secrecy shall bind the Contractor, its employees, partners or subcontractors also after the termination of this contract.

WITHDRAWING FROM THE CONTRACT

Article 17

If the Contractor does not carry out the work in accordance with this contract, the Contracting Authority may require the replacement of the staff nominated for the performance of the contract or withdraw from the contract and demand compensation for the damage incurred and invoke the financial performance guarantee. The withdrawal from the contract shall be made in writing, on the basis of a prior written notice, within the time limit specified by the Contracting Authority in the notice of withdrawal. The period shall begin after the receipt of the written notice.

The contract shall be terminated during the execution of the contract if the court finds with a final decision the Contractor’s or subcontractor’s breach of the obligation referred to in the second paragraph of Article 3 of the Public Procurement Act or if the Contracting Authority is informed that a competent public authority identified at least two infringements by the Contractor or its subcontractor with respect to remuneration for work, working time, rest, performing work under civil law contracts, despite the existence of elements of employment or undeclared employment, and for which it was fined for a misdemeanour with a final decision or several final decisions. The contract shall be terminated by signing the service contract for the subject of the contract with the successful Tenderer in the event that the contracting authority does not initiate the new procurement procedure, the contract is terminated after 30 days from the notification of the infringement.

The Contracting Authority may at any time, without giving reasons, withdraw from this contract with a two months' notice. The termination takes effect on the day on which the Contracting Authority has notified the Contractor in a demonstrable manner about the withdrawal from the contract.

ANTI-CORRUPTION CLAUSE

Article 18

A contract where any person promises, offers or gives any illicit advantage in the name or on behalf of another contracting party, to a representative or intermediary of a public sector body or organization for:

- obtaining a business or

- to conclude a transaction under more favourable terms, or

- to waive due control over the performance of contractual obligations, or

- other conduct or omission which causes damage to the public sector body or public organization or makes it possible to obtain an undue advantage for a representative of the body, an intermediary of a public sector body or organization, another contracting party or its representative, agent, or intermediary

is null. If the contract has not entered in force yet, the contract shall be deemed not to have been concluded.

REPRESENTATIVES OF THE CONTRACTING PARTIES

Article 19

Any questions arising in connection with the implementation of this contract will be dealt with by the authorized representative of the Contracting Authority _______________.

An expert for Procurement Service Provider is ____________________________.

DISPUTE SETTELMENT

Article 20

The parties agree that all disagreements regarding this contract will be settled amicably. If the disagreement cannot be resolved amicably, the court having jurisdiction over the Contracting Authority shall have jurisdiction over the dispute.

FINAL PROVISIONS

Article 21

The contract is concluded when it is signed by both parties and enters into force when the Contracting Authority receives the performance guarantee. The contract is concluded for a period of 9 months

Article 22

This contract is drawn-up in 4 (four) identical copies, of which each party receives two copies.

In: ________________ Date: __________		In:________________ Date: __________

Procurement Service Provider	University of Ljubljana, 
School of Economics and Business

________________________				____________

Tender pro forma invoice – final bid

The Tenderer _______________________________________________________________,

who in the process of awarding a public contract »Izvedba računalniško podprtega telefonskega anketiranja podjetij (CATI) v več evropskih državah za projekt GLOBALINTO - A telephone business survey (CATI) in several European countries for the GLOBALINTO project«, offers an offer, quotes the bid price with the following elements:

| Country | Price in EUR without VAT |
| --- | --- |
| Survey implementation in Denmark |  |
| Survey implementation in Finland |  |
| Survey implementation in France |  |
| Survey implementation in Germany |  |
| Survey implementation in Greece |  |
| Survey implementation in Norway |  |
| Survey implementation in Slovenia |  |
| Survey implementation in the UK |  |
| Other services not included elsewhere |  |
| Total in EUR without VAT |  |

Place and date:                                                       stamp and signature of the authorised person

ICC & ESOMAR (2016). ICC/ESOMAR International Code on Market, Opinion and Social Research and Data Analytics, available at https://www.esomar.org/uploads/pdf/professional-standards/ICCESOMAR_Code_English_.pdf

ESOMAR & WAPOR (2014). ESOMAR/WAPOR Guideline on Opinion Polls and Published Surveys (2014), available at https://www.esomar.org/uploads/public/knowledge-and-standards/codes-and-guidelines/ESOMAR-WAPOR-Guideline-on-Opinion-Polls-and-Published-Surveys-August-2014.pdf

European Statistical System Committee (2018). The European Statistics Code of Practice. Luxembourg: Publications Office of the European Union, available at https://ec.europa.eu/eurostat/web/products-catalogues/-/KS-02-18-142

The form is to be copied and completed.

The Tenderer has to submit certificates for at least three references as listed in 12.3..

Please, provide language skills assessment in accordance with Common European Framework of Reference for Languages.