Risk Management Strategy for SISPBO – patents and SPC

Version 0.1 – 23/03/2022

| Status | DRAFT |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Approved by owner | SISPBO Project Board |  | SIPO |  |  |
| Authors | MP | Matjaž Praprotnik | SIPO | Project Manager |  |
| Contributors |  |  |  |  |  |

| Version | Date | Revision | Revised By |
| --- | --- | --- | --- |
| 0.1 | 23/03/2022 | First Draft | MP |

Table of contents

1.	Introduction	3

1.1	Definition of Risk	3

1.2	Objectives of Risk Management	3

1.3	Scope of this Risk Management Strategy	3

1.4	Responsibility of this Risk Management Strategy	4

2.	Risk Management Procedure	4

2.1	Identify	4

2.2	Assess	5

2.3	Plan	8

2.4	Implement	8

2.5	Communicate	9

3.	Tools and Techniques	9

4.	Records	9

5.	Reporting	9

6.	Timing of Risk Management Activities	10

7.	Roles and Responsibilities	10

8.	Proximity	10

8.1	Categorising Risk Proximity	10

8.2	Risk Proximity Actions	10

9.	Early Warning Indicators	11

10.	Risk Tolerances	11

11.	Risk Budget	11

Appendix A – Risk Register	12

# Introduction

## Definition of Risk

Risk is a set of events that, should they occur, will have an effect on achieving the project objectives. Risk is an uncertain event that, if it occurs, will have a positive or negative effect on a project objective.

## Objectives of Risk Management

Good risk management is about identifying what might go wrong, what the consequences might be of something going wrong and finally, deciding what can be done to reduce the possibility of something going wrong. If it does go wrong, as some things inevitably will, making sure that the impact is kept to a minimum and making effort to try turn situation to an opportunity.

Risk management should ensure that an organisation makes cost effective use of a risk framework that has a series of well-defined steps. The aim is to support better decision making through a good understanding of risks and their likely impact.

Risk management should be a continuous and developing process, which runs throughout the organisation’s strategy and the implementation of that strategy, methodically addressing all risks surrounding the council’s activities past, present and future.

The risk management objectives are to:

- Ensure that risk management is clearly and consistently integrated and evidenced during the project.

- Manage risk in accordance with best practice.

- Anticipate and respond to changing social, environmental and legislative requirements.

- Inform policy and operational decisions by identifying risks and their likely impact.

- Raise awareness of the need for risk management by all those connected with the project.

These objectives will be achieved by:

- Clearly defining the roles, responsibilities and reporting lines within the organization of project for risk management.

- Including risk management issues when writing reports and considering decisions.

- Reinforcing the importance of effective risk management as part of the everyday work of employees and members of project group.

- Maintaining a register of risks linked to project objectives.

- Maintaining documented procedures of the control of risk and provision of suitable information, training and supervision.

- Preparing contingency plans to secure business continuity where there is a potential for an event to have a major impact upon the organisation’s ability to function.

- Monitor arrangements continually and seek continuous improvement.

## Scope of this Risk Management Strategy

This Risk Management Strategy described in this document is for SISPBO patents and SPC project and relates specifically to procedures related to the development of SISPBO applications, provision of methodology documentation and the presentation of that information to the general public as a whole.

## Responsibility of this Risk Management Strategy

The responsibility for the creation, maintenance and periodic review of this Risk Management Strategy is held by Project Manager. If necessary, it can be reviewed on a monthly basis and changed ratified through Project Board.

# Risk Management Procedure

The Risk Management Procedure encompasses 5 activities/steps according to PRINCE2 methodology:

Figure 1 – Risk Management Activities/Steps

## Identify

All parties involved in project (detailed in Roles and Responsibilities below) should identify events that might affect project and its objectives. This should focus on areas, which may affect costs, timescales, and quality of deliverables, maintainability and usability of products. Risks needs to be identified and monitored. Recommended techniques to identify risks are:

- Review Lessons: use lessons, risk and issue logs from previous or similar projects;

- Risk Categories: risk will be categorized in the following categories:

| Risk Category | Description |
| --- | --- |
| Financial | Operational & Maintenance Costs, Procurement Costs. |
| Governmental | Change of Government/Policy, Governmental Priorities. |
| Legal | New or Change legislation impacts activity. |
| Objectives | Objectives delivery, Scope. |
| Personnel Risks | Skill Shortage, Motivation, Commitment. |
| Interdependencies | Interdependencies on other projects and their deliverables. |
| Sponsorship | Project board support and communications. |
| Resources | Availability of human and other resources. |
| Technical | Scalability, Integration, Security, Standards, Compatibility, Performance, Inadequate Design, Infrastructure Failure. |
| Human Interface | Communications between members of project group, human factors. |
| Organisational Structure | Business Structure, Business Planning Process, Staff Development Process, Change Management Procedure. |
| Supportability | Support issues. |
| Implementation | Implementation risks, complexity. |
| Flexibility | Flexibility of project group and other stakeholders. |
| Maintenance | Maintenance risks. |

Table 1 - Risk Catego

Table 2 - Risk categories

- Brainstorming: group brainstorming to identify risks, which may not be recognised by an individual.

- Project Schedules: check for areas of the project falling behind schedule and approval target dates.

- Project Finances: check if project is running to budget within tolerance and for any cost not forecasted.

- Project Performance: check if number of issues is higher than expected, if there are high percent of unresolved issues, average time for resolving issues and product quality.

## Assess

Assess Risk covers two actions: Estimating and Evaluating Risk. Estimating is about assessing the exposure, the probability and the impact for each threat. Evaluating is to group all the risks together and get an overall Risk Value for the whole project. Estimate deals with one risk at a time, and evaluate groups all risks together to give one Risk Value for the whole project.

In this document described Risk assessment process, which is used in the SISPBO project, is in line with the general risk assessment process that is being used in the SIPO and was introduced with upgrade to the newest version of ISO 9001 standard.

### Estimating:

- Risk Scales

Following the identification of risks, they will then be included in the risk register, which will identify the risk owner and the steps being taken to mitigate the risk.

Risks will be categorised against the potential impact to the project:

- Very Low impact – 1;

- Low impact – 2;

- Medium impact – 3;

- High impact – 4;

- Very High impact – 5.

Risks will also be categorised against the probability of the risk being encountered:

- Very Low probability – 1;

- Low probability – 2;

- Medium probability – 3;

- High probability – 4;

- Very High probability – 5.

- Risk Actions

Risk actions are described according to Priority (Exposure) which is based on product of Impact X Probability and has following values:

- 1, 2, 3, 4, 5, 6 – Low priority;

- 8, 9, 10, 12 – Medium priority;

- 15, 16 – High priority;

- 20, 25 – Extreme priority.

| Risk Priority | Risk Action | Impact/Probability | Frequency of Review |
| --- | --- | --- | --- |
| Low (1,2,3,4,5,6) | Monitor as necessary – ensure being properly managed, less important but could still have effect on project. | Moderate/Unlikely (2) Minor/Unlikely (1) Minor/Likely (2) | Monthly |
| Medium (8,9,10,12) | Monitor as necessary –important, could have serious effect on project. | Major/Unlikely (3) Moderate/Likely (4) Minor/Very Likely (3) | 14 days |
| High (15,16) | Key risk – may potentially affect project | Major/Likely (6) Moderate/Very Likely (6) | 1 week |
| Extreme (20,25) | Key risk – serious threat to project | Major/Very Likely | Immediate |

Table 3 - Risk Actions

|  |  |  | Probability |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Very Low | Low | Medium | High | Very High |  |
|  | Impact | Very High | 5 | 10 | 15 | 20 | 25 |  |
|  |  | High | 4 | 8 | 12 | 16 | 20 |  |
|  |  | Medium | 3 | 6 | 9 | 12 | 15 |  |
|  |  | Low | 2 | 4 | 6 | 8 | 10 |  |
|  |  | Very Low | 1 | 2 | 3 | 4 | 5 |  |

Table 4 - Risk Matrix

### Evaluating:

The objective of Evaluate is to assess all the risks together and get an overall impact of risks for the whole project. From a Project Board point of view, such information is of the highest importance. Project Board is notified about risk status in each project board meeting.

## Plan

### Objective of Risk Planning

The primary objective of this step is to prepare management responses using Risk Response Treatment for each of the identified threats and opportunities in order to reduce or remove the threat. This should leave the project prepared with an action plan should any risk materialise.

Concentration should be on ‘red’ risks as these have the greatest chance of arising and are likely to affect the project most severely. Consideration should be given to ‘amber’ risks and ‘green’ risks in order to:

- Keep the risk at as low a level as is practical;

- Be prepared to respond to the risk should its severity level increase during the project;

- Ensure that ‘green’ or ‘amber’ risks do not increase the chance of a ‘red’ risk being encountered.

### Risk Response Treatment

For each risk, treatment strategy should be devised. The treatments are:

- Accept: Do nothing about the risk, and accept the possible consequences. For opportunity, accept and implement opportunity.

- Avoid:  Do not perform the activity that is causing the risk. For example, if a feature in a software development project looks like it might cause delays; it could be chosen not to develop that feature.

- Mitigate: Devise a plan to reduce either the probability or the impact of the risk. For example, you adding extra resources to the project.

- Transfer: Make another party responsible for the risk.

- Reject: Only for opportunities, reject the opportunity.

Treatment strategy will depend upon the severity of the risk. When avoid, mitigate or transfer are chosen, details of how this will be accomplished must be provided.

For each risk, a contingency plan should also be defined. This is a pre-defined set of actions that will be undertaken if the risk is triggered. An example contingency plan would be, “Schedule an immediate meeting of the Project Board to resolve the problem.”

## Implement

The primary objective of this step is to ensure the planned risk responses are implemented, their effectiveness monitored and corrective action taken where responses do not provide effective solutions.

To ensure this is carried out efficiently, there will be a sole Risk Owner. This is a named individually who is responsible for the management, monitoring and control of all aspects of a particular risk.

A risk will be assigned to a single individual.

An individual may be responsible for more than one risk but consideration should be given to their workload and abilities to ensure any individual is not allocated more risks than they can practically manage.

## Communicate

Risks will be communicated outwards as part of:

- Checkpoint Reports;

- Highlight Reports;

- End Stage Reports;

- End Project Reports;

- Lessons Reports – at End Stage and End Project.

Inwards communications of risks, in particular new perceived risks should be communicated to the Project Manager for assessment ad-hoc.

The guidelines for reporting come from the Communication Management Strategy document.

# Tools and Techniques

Project risk will be managed through Risk Register in SIPO JIRA. Each Risk Register form will detail the status of a single risk and will have a unique, sequential risk identifier.

Access to Risk Register forms will be restricted to those defines in the Roles and Responsibilities, below and to the Risk Owner

# Records

Appendix A – Risk Register details contains the format of the Risk Register and descriptions for each Risk Register field. Risk Register record is based on JIRA Risk register plugin and PRINCE 2 recommendations.

# Reporting

Individual risk overviews will be entered on the Risk Summary which will be readily available for authorised individuals and which will be communicated to the Project Board

The Risk Summary will include:

- Project Name;

- Risk Identifier

- Summary of risk description;

- Risk Impact;

- Risk Probability;

- Current risk exposure;

- Previous risk exposure;

- Date registered;

- Risk Owner.

Access to Risk Summary will be restricted to those defined in the Roles and Responsibilities below and to the Risk Owner.

# Timing of Risk Management Activities

The Risk Register will be created on approval of this Risk Management Strategy. It will be updated:

- On planning the next stage;

- On authorizing a work package;

- On any updates of the project plan;

- Upon any updates of the Business Case;

- On the production of any exception plan;

- On review of any stage status.

It will be closed when approval for project closure has been given by the Project Executive

# Roles and Responsibilities

In details, project roles are described in SISPBO patents and SPC -  SCD  document. The following table describes responsibilities for those roles concerning risk management.

| Project Role | Responsibilities |
| --- | --- |
| Executive | Be accountable for all aspects of risk management and ensure an approved project Risk Management Strategy exists. Ensure risks associated with Office are identified, assessed and controlled |
| Senior User (business) | Ensure all risks to the users are identified, assessed and controlled. |
| Senior Supplier (technical) | Ensure risks relating to the supplier aspects are assessed and controlled. |
| Project Manager | Create the Risk Management Strategy. Create and maintain the Risk Register. Ensure all project risks are being identified, assessed and controlled throughout the project lifecycle. |

Table 5 - Roles and Responsibilities

# Proximity

## Categorising Risk Proximity

Risk events will be categorised as:

- Imminent – likely to be encountered immediately, typically within one week or less;

- Within the stage – likely to be encountered during the current stage of the project;

- Next stage – likely to be encountered during the next planned stage of the project;

- Within the project – likely to be encountered before the project is closed;

- Beyond the project – likely to be encountered after project closure.

## Risk Proximity Actions

Imminent risks should be noted separately within reporting to highlight the risk to project members to ensure it is being monitored adequately.

On completion of a stage, ‘within the stage’ risks should be assessed to determine if they were encountered. If they were not encountered their relevance to the next planned stage should be determined and their proximity classification modified accordingly.

On completion of a stage, ‘next stage’ risks should be assessed to determine if they are still applicable to the next stage (i.e. the stage to be started) and, if appropriate, their proximity should be modified to ‘within the stage’.

‘Within the project’ risks should be reviewed at stage end to determine if they fall into the ‘next stage’ category (i.e. the stage after the stage to be started).

‘Beyond the project’ risks should be reviewed at stage end to determine if they are still legitimate risks. If the project is at closure stage, these risks should be highlighted in the project closure documentation.

# Early Warning Indicators

There are several early warning indicators, which should be monitored during the life of the project:

- Forecast project spend / timescales exceeding approved tolerance – should the forecast total spend exceed the project budget and allowed tolerance, it is clear there is a genuine risk of overspend (or non-completion) of the project. This should be regularly monitored by the project manager and senior supplier to ensure spend is within allowed limits

- Forecast stage spend / timescales exceeding approved tolerance – the implication is that the stage has either been incorrectly estimated, incorrectly defined or has encountered unforeseen problems.

- Product quality not meeting quality requirements – have there been shortcuts in the production of products, which detrimentally affect product quality. In particular, has spent to date fallen below the forecast spend to date or the products been delivered earlier than planned.

These should be regularly monitored by the Project Manager/Senior Supplier to ensure each stage is performing according to planned cost, timescales and quality.

# Risk Tolerances

Risks are scored according to exposure.  High risk should be noted to SIPO management for information. Extreme risks should be escalated to SIPO management immediately.

# Risk Budget

There is no specific risk budget. Project tolerance will be employed where necessary to minimise the impact of risks.

It should be noted that there might be some risks defined during the project, which require a separate budget, e.g. insurance against risk encounter or insurance against financial implications of risks.

# Appendix A – Risk Register

| Field Name | Field Description |
| --- | --- |
| Project Name: | Name of project in JIRA (Key) |
| Labels: | Additional labels (not required) |
| Impact: | Impact of risk to project. These should be recorded in accordance with the project’s chosen scales (Minor, Moderate, And Major). |
| Probability: | Probability of risk. These should be recorded in accordance with the project’s chosen scales (Unlikely, Likely, Very Likely). |
| Exposure: | Risk Priority (Exposure). Automatically according to impact and probability (Risk Matrix). |
| Treatment: | Treatment strategy. These should be recorded in accordance with the project’s chosen treatment strategies (Avoid, Accept, Transfer and Mitigate for Risks, Issues and Threats. Accept and Reject for Opportunities. |
| Treatment plan: | Description of treatment plan. |
| Contingency plan: | Description of contingency plan. |
| Realization: | None, Realized, Not realized. |
| Risk Description: | Description of risk. |
| Risk Category: | Risk category |
| Risk Type | Risk Type: Issue, Opportunity, Threat. |
| Proximity: | How close to the present time the risk event is anticipated to happen |
| Assignee: | Risk Owner - Person responsible for managing the risk |
| Reporter: | Risk Reporter - Person who raised the risk |
| Updated: | Date of last change in recording. |
| Created: | Date the risk was identified. |
| Risk Status | Active or Closed. |

Table 6 - Risk Register Record

Definition is based on PRINCE2 definition taken from MOR (Management Of Risk) method

Source: http://prince2.wiki/Risk

Source: ECP Risk Template