DRAFT CONTRACT

for

Inspection of Reactor Vessel Flange Sealing Surfaces and Reactor Vessel Head Flange Grooves Sealing Surfaces and FOSAR and Visual Re-examination of Reactor Vessel Internal component W15 and TSSB during Outage 2024

concluded on __________________ by and between:

NUKLEARNA ELEKTRARNA KRŠKO d.o.o.

Vrbina 12, 8270 Krško, Slovenia,

represented and duly authorized by

Mr. Gorazd Pfeifer, President of the Management Board and 
Mr. Saša Medaković, Member of the Management Board

(hereinafter referred to as "PURCHASER" or "NEK" or "NPP Krško")

on one part

and

……………………………………………………………………

represented and duly authorized by

Mr. …………………………………………….

(hereinafter referred to as "SELLER" or “Contractor”)

on the other part

Whereas, SELLER represents that it is fully qualified to provide PURCHASER with:

Inspection of Reactor Vessel Flange Sealing Surfaces and Reactor Vessel Head Flange Grooves Sealing Surfaces and FOSAR and Visual Re-examination of Reactor Vessel Internal component W15 and TSSB in NPP Krsko during Outage 2024

and shall do so in accordance with the terms and conditions herein specified, and

Whereas, the representatives of SELLER and PURCHASER possess proper and sufficient authority to agree, and

Now therefore, SELLER and PURCHASER have agreed as follows:

Subject of the Contract:

Inspection of Reactor Vessel Flange Sealing Surfaces and Reactor Vessel Head Flange Grooves Sealing Surfaces and FOSAR and Visual Re-examination of Reactor Vessel Internal component W15 and TSSB in NPP Krsko during Outage 2024

(hereinafter referred to as “Inspection of RV and RVCH Flange Sealing Surfaces and FOSAR Activities”)

The following documents shall constitute the Contract:

- PART I:   General Terms and Conditions (this Document)

- PART II:  NEK Technical Specification No. IN 8230647, Rev.0 for Inspection of Reactor Vessel Flange Sealing Surfaces and Reactor Vessel Head Flange Grooves Sealing Surfaces during 2024 Outage (hereinafter referred to as “TS IN 8230647”) and

Technical Specification No. ISI 04/23, Rev.0 for FOSAR and Visual Re-examination of Reactor Vessel Internal components W15 and TSSB per MRP-227 and TB-19-5, Rev.2 in NPP Krsko during Refueling Outage 2024

(hereinafter referred to as “TS ISI 04/23”)

- PART III: Quotation   No. …………………. dated ………………….

PART I - GENERAL TERMS AND CONDITIONS

TABLE OF CONTENTS

0	DEFINITIONS AND ABBREVIATIONS	4

1	SELLER'S SCOPE OF SERVICES AND DELIVERY	6

2	PURCHASER'S RESPONSIBILITIES	8

3	QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS	8

4	DELIVERABLES TO BE PROVIDED TO PURCHASER	8

5	SCHEDULE REQUIREMENTS	8

6	DELIVERY TERMS AND CONDITIONS	10

7	PRICE	10

8	PAYMENT TERMS AND SCHEDULE	12

9	INSPECTIONS, TESTS	15

10	LIQUIDATED DAMAGES	15

11	SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION	17

12	WARRANTY	17

13	T A X E S	18

14	LICENSES, PERMITS, AND AUTHORIZATIONS	19

15	INSURANCE AND INDEMNITY	19

16	LIABILITY	20

17	PROPRIETARY INFORMATION	22

18	CLAIMS	23

19	ARBITRATION	24

20	SUBSTANTIVE LAW	24

21	FORCE MAJEURE	25

22	SUSPENSION OF WORK AND TERMINATION	26

23	CHANGES	31

24	ANTI-CORRUPTION CLAUSE	32

25	SOCIAL CLAUSE	33

26	OTHER PROVISIONS	33

27	ASSIGNMENT	36

28	ENTIRE AGREEMENT	36

29	LANGUAGE	36

30	EFFECTIVE DATE OF CONTRACT	36

31	NOTICES	37

32	ATTACHMENTS	38

# DEFINITIONS AND ABBREVIATIONS

As used throughout the Contract, the following terms shall have the meaning set forth hereinafter:

PURCHASER shall mean NUKLEARNA ELEKTRARNA KRŠKO (NPP Krško), Vrbina 12, 8270 Krško, Slovenia, represented by	
Mr. Gorazd Pfeifer, President of the Management Board

and 
Mr. Saša Medaković Member of the Management Board

SELLER or CONTRACTOR shall mean

………………………………………………………………………………………………

PARTY or PARTIES shall mean PURCHASER or/and SELLER as herein under referred to individually or collectively.

CONTRACT shall mean the agreement between PURCHASER and SELLER consisting of General Terms and Conditions of the Contract (PART I), NEK

Technical Specifications No. IN 8230647, Rev.0 and ISI 04/23, Rev.0 (PART II), and Quotation ………………….. dated ………………….. (PART III).

The Contract documents are complementary, and what is called for by anyone of them shall be binding as if called for by all. Any conflicts in the Contract documents shall be reasonably resolved by the PURCHASER after mutual discussion between SELLER and PURCHASER. The validity dates of documents and any data listed in this Contract shall be the date of the Contract signature of both Parties.

SCOPE OF SERVICES AND DELIVERY/PROJECT as defined in Technical Specifications No. IN 8230647, Rev.0 and ISI 04/23, Rev.0 and other contractual documents.

TECHNICAL REPRESENTATIVES shall mean the PURCHASER’s and the SELLER’s designated representatives through whom all technical, commercial, Quality Assurance and matters shall be channelled.

COMMERCIAL REPRESENTATIVES shall mean the PURCHASER’s and the SELLER’s designated representatives through whom commercial matters will be evaluated.

TS IN 8230647 shall mean Technical Specification No. IN 8230647, Rev.0 for Inspection of Reactor Vessel Flange Sealing Surfaces and Reactor Vessel Head Flange Grooves Sealing Surfaces during 2024 Outage.

TS ISI 04/23 shall mean Technical Specification No. ISI 04/23, Rev.0 for FOSAR and Visual Re-examination of Reactor Vessel Internal components W15 and TSSB per MRP-227 and TB-19-5, Rev.2 in NPP Krsko during Refueling Outage 2024.

QUOTATION shall mean SELLER’s Quotation No.: ………… dated ………….

PLANT, SITE, NEK, NPP Krško shall mean Nuclear Power Plant Krško.

APPROVED shall mean the status of any document to be furnished by the SELLER to PURCHASER under the Contract which is approved by PURCHASER with or without comments but which is not rejected by PURCHASER. The date for the resolution of PURCHASER’s comments shall be mutually agreed upon prior to the approval. In no circumstances the approval can relieve SELLER from the responsibility for failures within SELLER’s Scope of Services and Delivery.

HARDWARE shall mean all equipment, spare parts, consumables and materials together with required software needed for the completion of the Project and as defined in the contractual documents.

TOTAL CONTRACT PRICE shall mean all-inclusive total price to be paid to the SELLER as per Art. 7.1 of the Contract.

QA shall mean Quality Assurance.

FOSAR shall mean Foreign Object Search and Retrieval as defined in NEK Technical Specification No. ISI 04/23, Rev.0.

RB shall mean Reactor Building.

FHB shall mean Fuel Handling Building.

RV shall mean Reactor Vessel.

RVCH shall mean Reactor Vessel Closure Head.

# SELLER'S SCOPE OF SERVICES AND DELIVERY

SELLER shall perform the Inspection of RV and RVCH Flange Sealing Surfaces and FOSAR Activities during 2024 Outage fully in accordance with NEK Technical Specifications IN 8230647, Rev.0 and ISI 04/23, Rev.0. and SELLER’s Quotation No. ………………….. dated …………

1.1	Base Scope of Services and Delivery

1.1.1  Base Scope of the Inspection of RV and RVCH Flange Sealing Surfaces shall include:

- inspection of the RV Flange Sealing Surfaces by visual testing and laser scanning,

- inspection of the RVCH Flange Grooves Sealing Surfaces by visual testing and laser scanning,

- visual inspection of used RVCH O-rings during their removal.

Detailed description of the Base Scope of the Inspection of RV and RVCH Flange Sealing Surfaces is given in TS IN 8230647.

1.1.2  Base Scope of the FOSAR Activities shall include visual inspection and retrieval of a foreign object of:

- containment refueling cavity,

- RV bottom

- bottom part of lower internal,

- RV flange surface,

- Lower internals lower core plate.

Detailed description of the Base Scope of FOSAR Activities is given in TS ISI 04/23.

1.2	Optional / Additional Scope of Services and Delivery

1.2.1  Optional Scope of the Inspection of Reactor Vessel and Reactor Vessel Head Flange Sealing Surfaces

a. Inspection and analysis of the most affected sealing flange zones by swab sampling or replicas or other applicable examination method based on which degradation and corrosion processes of specified sealing surfaces is monitored.

b. Cleaning of the RV sealing flange by underwater cleaning machine.

The above Optional Scope shall be performed during 2024 Outage at the price given in Art. 7.2 of this Contract, against PURCHASER written authorization provided to SELLER to perform such proposed Optional Scope.

1.2.2  Additional Scope of the FOSAR Activities

The additional Scope of FOSAR activities will be requested in case of occurrence of relevant conditions on fuel elements (broken fuel rods). It shall apply to inspection of reactor internal and FHB refueling channel as well as retrieval of foreign parts. It shall be performed during 2024 Outage at the price given in Art. 7.3 of this Contract, against PURCHASER written authorization provided to SELLER to perform such proposed Additional Scope.

Subcontractors

For a part of the Scope of Services and Delivery SELLER may engage the subcontractors which have been listed in the Quotation and accepted by PURCHASER. If SELLER upon signature of this Contract wants to change or select new subcontractor(s), this shall be subject to PURCHASER approval, which shall not be unreasonably withheld. Based on the law of ZVISJV (Act on Protection against Ionizing Radiation and Nuclear Safety) and based on “Pravilnik o dejavnikih sevalne in jedrske varnosti (JV 5)” Art. 67, PURCHASER is responsible for establishing surveillance on SELLER and its subcontractors to ensure high quality and nuclear safety for the public.

SELLER shall ensure that all subcontractors meet high standards of competence, experience and capacity in relation to the tasks to be entrusted to them and that they fully comply with the TS IN 8230647 and TS ISI 04/23 requirements and the contractual documents.

Since SELLER retains full responsibility for all aspects of subcontractors’ performance including quality and schedule, SELLER shall ensure that adequate periodic audit and surveillance of the subcontractors is maintained. SELLER shall identify to all subcontractors all applicable Quality Assurance and Quality Control requirements imposed by PURCHASER’s specifications on SELLER and shall ensure compliance thereto. All subcontractors shall be on SELLER’s Approved Suppliers List. NEK’s right of access to SELLER’s subcontractors’ facilities for the purpose of inspection or audit shall be imposed by SELLER’s documents.

SELLER shall not subcontract any portion of the Work without the written approval of PURCHASER Responsible Engineer, which shall not be unreasonably withheld. The absence of any reply from the PURCHASER within three (3) weeks is considered as approval under the condition that SELLER sends prior notification to PURCHASER within two weeks. Subcontractors performing augmented quality service will need to have either quality assurance program approved by PURCHASER or work in conjunction with SELLER Quality Assurance Program.

Full overall responsibility always remains on SELLER’s side concerning participation of SELLER’s subcontractors.

# PURCHASER'S RESPONSIBILITIES

PURCHASER’s responsibilities for the Inspection of RV and RVCH Flange Sealing Surfaces are given in TS IN 8230647, Section 11.

PURCHASER’s responsibilities for the FOSAR Activities are given in TS ISI 04/23, Section 11.0.

# QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS

The services to be performed under this Contract are classified as safety related (SR).

SELLER shall meet quality assurance, design, material, technical and all other requirements as well as procedures, codes and standards as stated in TS IN 8230647 (for the Inspection of RV and RVCH Flange Sealing Surfaces) and TS ISI 04/23 (for FOSAR Activities).

# DELIVERABLES TO BE PROVIDED TO PURCHASER

SELLER shall submit to PURCHASER all deliverables/documentation as stated in TS IN 8230647, Section 2 (for the Inspection of RV and RVCH Flange Sealing Surfaces), TS ISI 04/23, Section 10 (for FOSAR Activities) and SELLER’s Quotation.

# SCHEDULE REQUIREMENTS

The Scope of Services and Delivery as per Art. 1 above shall be performed during NEK 2024 Outage scheduled to start on 1st April 2024 and shall be harmonized with NEK outage schedule.

## Inspection of the Reactor Vessel and Reactor Vessel Head Flange Sealing Surfaces

As stated in TS IN 8230647, Section 9.

5.1.1 The Reactor Vessel Flange Inspection and Underwater RV Flange Cleaning (if any) shall be performed on the critical path of NEK Outage, which means at any time of the outage day and it is scheduled for 17th April 2024.

5.1.2 The Reactor Vessel Head (RVCH) Flange Groove Sealing Surfaces Inspection shall not be performed on the critical path and is scheduled to be performed within the period from 11th till 16th April 2024.

The RVCH removal is scheduled for 5th April 2024 when sealing flange swab samples can be taken.

The exact starting date of the Reactor Vessel and Reactor Vessel Head Flange Sealing Surfaces Inspection shall be confirmed by NEK one (1) month in advance.

5.2	FOSAR Activities

As stated in TS ISI 04/23, Section 9.0.

| Key milestones | INSPECTION ACTIVITY | OUTAGE 2024 SCHEDULE |
| --- | --- | --- |
| 1 | Transportation of equipment to RB and FHB | 5th April at 8:00 |
| 2 | Setup of equipment | 5th April at 14:00 |
| 3 | Visual Examination of Reactor Vessel Internals (Upper Internal) | 6th April at 04:00 |
| 4 | FOSAR activity on Reactor Vessel and visual examination of TSSB and W15. Alignment and interfacing components UCP guide pin on RVLI. | From 10th April from 14:00 to 18:00 |
| 5 | Visual inspection of RPV flange seal surfaces (FOSAR scope) with potential cleaning of RPV flange (suction device) | From 10th April from 19:00 to 21:00 |
| 6 | Containment refueling cavity | From 15th April at 08:00 to 16th April at 18:00 |
| 7 | Lower Core Plate of the Lower Internals | 19th April from 15:00 to 19:00 |
| 8 | Transportation of equipment from RB and decontamination | From 19th April at 19:00 to 21th April at 15:00 |

Actual start of activities will be communicated by PURCHASER 14 days in advance before the actual start of the outage and confirmed at the actual start of the Outage 2024.

# DELIVERY TERMS AND CONDITIONS

All equipment, material, parts, components, as well as all other deliverables of SELLER Scope of Services as stated in Art. 1 above shall be delivered DAP NPP Krško site as per ICC Incoterms 2020.

Delivery of shipping documents

As soon as possible, but not later than on three days before the day of delivery of goods, in order to ensure timely receipt and customs clearance, SELLER or its forwarding agent shall send to PURCHASER the following information and documents:

- estimated time of arrival of shipment at NEK site

- shipping invoice with description of goods, quantity, unit and total price per each item and total price

- packing list

- copy of AWB or RWB or B/L, etc. (relative to means of transportation)

The use of EUR-1 Form for optimizing of customs formalities shall be mandatory whenever feasible.

Temporary Import to NPP Krško site

SELLER shall organize and perform at its cost all transportation and insurance of all temporarily imported equipment, instruments, material, etc. necessary to perform SELLER’s Scope of Services and Delivery under this Contract to NPP Krško site, return without delay from NEK site and insurance of them also during the stay at NEK site.

# PRICE

7.1 	The fixed and firm Total Contract Price for the whole contractual Base Scope of Services and Delivery as per Art. 1.1 above under the terms and conditions of this Contract is:

EUR/USD  …………………….(excl. VAT)

(in words: …………………………..Euros/Dollars)

All labor, materials, equipment, parts, components, and services like engineering and documentation as well as living, traveling and similar costs of SELLER's personnel, etc. necessary for SELLER to fulfill its obligations as stated in Art. 1. of this Contract are included in the above Total Contract Price.

## Fixed Total Price for the Base Scope of Inspection of RV and RVCH Flange Sealing Surfaces as per Art. 1.1.1 above is:

- EUR/USD ……………………… (excl. VAT)

- (in words: ……………………………..Euros/Dollars)

The price structure is given below:

| Item | Scope of Services and Delivery Description | Fixed Price (in EUR/USD) |
| --- | --- | --- |
| a. | Inspection of the RV Flange Sealing Surfaces by visual testing and laser scanning |  |
| b. | Inspection of the RVCH Flange Grooves Sealing Surfaces by visual testing and laser scanning |  |
| c. | Visual inspection of used RVCH O-rings during their removal |  |
|  | TOTAL PRICE for BASE SCOPE as per Art. 1.1.1 above |  |

## Fixed Price for the Base Scope of FOSAR Activities as per Art. 1.1.2 above is:

- EUR/USD ……………………… (excl. VAT)

- (in words: ……………………………..Euros/Dollars)

7.2   Prices for the Optional Scope of Inspection of RV and RVCH Flange Sealing Surfaces

- The fixed price for the Inspection and analysis of the most affected sealing flange zones as per Art. 1.2.1.a:

- EUR/USD ……………………… (excl. VAT)

- (in words: ……………………………..Euros/Dollars)

- The fixed price for the Cleaning of the RV sealing flange by underwater cleaning machine:

- EUR/USD …………………. (excl. VAT)

- (in words: ……………………………..Euros/Dollars)

7.3	Prices for the Additional Scope of FOSAR Activities as per Art. 1.2.2 of this Contract

- The fixed daily rate is:

EUR/USD ............................... per day (one shift) (excl. VAT)

(in words: …………………………………………………….. Euros/Dollars)

- The fixed price for the rental equipment is:

EUR/USD …………….. per day (one shift) (excl. VAT)

(in words: …………………………….. Euros/Dollars)

The results of the additional FOSAR scope will be documented together with the preliminary and final test report for the basic FOSAR scope. There will be no additional costs for the preparation of the preliminary and final test report.

# PAYMENT TERMS AND SCHEDULE

Payment under this Contract will be made by means of a bank transfer, net due thirty (30) days upon completion of respective milestone as defined above and receipt of the appropriate invoice and other documents defined in NEK Technical Specifications.

8.1.	Payment schedule

8.1.1 Payment of the Total Price as per Art. 7.1.1 for the Base Scope of Inspection of RV and RVCH Flange Sealing Surfaces shall be made according to the following schedule:

- 40% of the Total Price in the amount of EUR …………………… upon the mobilization of equipment and personnel, preparation of the documentation and submittal of Repayment Guarantee.

- 50% of the Total Price in the amount of EUR …………………… upon completion of the on-site services and PURCHASER’s receipt of the Preliminary Report.

- 10% of the Total Price in the amount of EUR ………………… upon PURCHASER’s receipt and approval of the Final Report.

8.1.2   Payment of the Price as per Art. 7.1.2 for the Base Scope of FOSAR Activities shall be made according to the following schedule:

- 40% of the Price in the amount of EUR …………………… upon the mobilization of equipment and personnel, preparation of the documentation and submittal of Repayment Guarantee.

- 50% of the Price in the amount of EUR …………………… upon completion of the on-site services and PURCHASER’s receipt of the Preliminary Report.

- 10% of the Price in the amount of EUR ………………… upon PURCHASER’s receipt and approval of the Final Report.

8.1.3   Payment of the Price for the Optional Scope of Inspection of RV and RVCH Head Flange Sealing Surfaces as per Art. 7.2 above shall be made according to the same schedule as defined in Art. 8.1.1 above for the Base Scope of RV and RVCH Flange Sealing Surfaces.

8.1.4   Payment of the Price for the Additional Scope of FOSAR Activities as per Art. 7.3 above shall be made upon completion of the service as per Art. 1.2.2.

8.2 	Payments of Subcontractors (if any)

If the Bidder engages a subcontractor who wants to be paid directly and they submit the Attachment C - Subcontractor’s Data and Bidder’s Consent for Direct Payment, NEK is obliged to pay the subcontractor directly.

Beside the invoice submitted by the SELLER to the PURCHASER with total amount of the payment due including the value of subcontractor work specified separately, the SELLER shall also approve and submit the invoice and specifications of its subcontractors for each payment milestone.

The SELLER authorizes the PURCHASER to make direct payments to the subcontractors for their services and supplies, based on the approved invoices addressed to SELLER.

If a subcontractor is replaced after the conclusion of the Contract or if the SELLER concludes a contract with a new subcontractor which is subject to direct payment, the SELLER that concluded the Contract with the PURCHASER must submit to the latter, within 5 days of change:

- The statement that all non-disputed liabilities have been settled to the original subcontractor;

- authorization for the payment of provided and delivered work or products directly to the new subcontractor, and

- the consent of the new subcontractor to the acceptance of direct payment

The payment will be made in accordance with the payment terms and conditions above and based on the signed Subcontractor’s Data and SELLER’s Consent for Direct Payment in the form and content according to Attachment C.

8.3	Guarantees

8.3.1   Bank Repayment Guarantees

The Bank Repayment Guarantee to the amount of 40% of the Total Price for the Inspection of RV and RVCH Flange Sealing Surfaces as per Art. 7.1.1. and Art. 7.2 (if any) shall be submitted to PURCHASER together with the invoice for the first payment instalment in the form and content as defined in Attachment A with a validity until 30 days upon approval of the Final Report for the relevant services.

The Bank Repayment Guarantee to the amount of 40% of the Total Price for the FOSAR Activities as per Art. 7.1.2. shall be submitted to PURCHASER not later than three (3) weeks after the Contact signature together with the invoice for the first payment instalment for the relevant scope in the form and content as defined in Attachment A with a validity until 30 days upon approval of the Final Report for the relevant services.

Should SELLER fail to perform its obligations as per Art. 1 PURCHASER will be entitled to demand of the relevant Bank Repayment Guarantee in the form and content as in Attachment A, issued by a first class bank not later than (3) weeks after the Contract signature with a validity until approval of the Final Report.

However, the amount so collected shall be reimbursed by PURCHASER to SELLER in case the latter finally successfully completes his Scope of Services. In such a case, should PURCHASER have borne extra costs due to the above mentioned delay, SELLER commits to reimburse such extra costs to the PURCHASER in a fair way under best business practice. PURCHASER shall make every effort to mitigate such costs.

The Repayment Guarantee shall be issued by a first class bank.

8.3.2   Bank Guarantee for Good Performance during Warranty Period

The Bank Guarantee for Good Performance during Warranty Period to the amount of 5% of the Total Price for the Inspection of RV and RVCH Flange Sealing Surfaces as per Art. 7.1.1. and Art. 7.2 (if any) shall be submitted to PURCHASER together with the invoice for the last payment instalment in the form and content as defined in Attachment B with a validity of thirty (30) days after the end of the Warranty period as stated in Art. 12.2 below.

# INSPECTIONS, TESTS

All tests and inspections shall be performed in accordance with TS IN 8230647 (for the Inspection of RV and RVCH Flange Sealing Surfaces) and TS ISI 04/23 (for the FOSAR Activities).

# LIQUIDATED DAMAGES

## Liquidated Damages for Delay in the Inspection of RV and RVCH Flange Sealing Surfaces

In case of delay in performance of the Inspection of RV and RVCH Flange Sealing Surfaces according to NPP Krško Outage 2024 Schedule as defined in Art. 5.1 of the Contract, due to reasons solely attributable to SELLER, SELLER shall pay to PURCHASER liquidated damages as follows:

- 18.000 € per entire hour of delay in the performance of services stated in Art. 5.1.1 of the Contract, starting after the first hour of delay;

- 5.000 € per entire day of delay in the performance of services stated in Art. 5.1.2 of the Contract, starting after the first day of delay.

- PURCHASER shall claim payment of liquidated damages only after the additional grace period granted by PURCHASER which shall last as long as the delay does not jeopardize the other outage activities.

In any case, the payment of the liquidated damages shall be the sole and exclusive remedy available to the PURCHASER and the exclusive liability of the SELLER for all claims arising from the delay with Contract requirements and shall not exceed 10% of the Total Price (excl. V.A.T.) as stated in Art. 7.1.1.

## Liquidated Damages for Delay in FOSAR Activities

In case of delay in completion of the FOSAR Activities according to NPP Krško Outage 2024 Schedule as specified in the Contract, due to reasons solely attributable to SELLER, SELLER shall pay to PURCHASER liquidated damages as follows:

- 18.000 € per entire hour of delay as per key milestones 3 through 7 of Art. 5.2. PURCHASER shall claim payment of liquidated damages only after the additional grace period granted by PURCHASER which shall last as long as the delay does not jeopardize the other outage activities.

In any case, the payment of the liquidated damages shall be the sole and exclusive remedy available to the PURCHASER and the exclusive liability of the SELLER for all claims arising from the delay with Contract requirements and shall not exceed 10% of the Total Price (excl. V.A.T.) as stated in Art. 7.1.2.

## Liquidated Damages for Violation of Safety at Work (SaW), Fire Protection (FP) and Foreign Material Exclusion (FME) Rules and Regulations

SELLER shall pay liquidated damages for the violation of the Safety at Work (SaW), Fire Protection (FP) and Foreign Material Exclusion (FME) rules and regulations, as follows:

•   1000 € for each and every proven evidence of violation of SaW, FP and FME program rules and regulations

•       2000 € for each repeated case of violation of SaW, FP and FME rules and regulations

In cases of repeated and proven evidence of violation of the above rules and regulations, disobedience of NEK rules of behavior or instructions and warnings from NEK guards and technical personnel. PURCHASER shall order the violator to leave NEK Site and ask the SELLER for immediate replacement worker.

Violators will also be removed from NEK site in cases of violating the provisions of:

•	Act on Protection against Ionizing Radiation and Nuclear Safety

•	Slovenian Law on Safety and Health at Work

•	NEK outage manual safety provisions

•	Provisions of Security Vetting procedures for unescorted access to NEK

# SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION

In order to ensure safety and health at work, SELLER shall follow the provisions of the Law on Safety and Health at Work (Official Gazette of RS No.43/11), ADP procedure 1.1.033 Safety and Health at Work at NPP Krško and in compliance with provisions of a separate written Agreement concluded in accordance with Art. 39 of the Law on Safety and Health at Work of the Republic of Slovenia.

SELLER shall make sure that the performance of Work be in accordance with internal procedures and instructions issued by responsible PURCHASER’s employees.

In order to fulfill the provisions of the Act on Protection against Ionizing Radiation and Nuclear Safety, the contractual parties shall adhere to the Agreement on Protection against Ionizing Radiation (applicable for suppliers performing services in the controlled area). Based on the provisions of this Agreement, SELLER shall provide all necessary data and signed statements of workers by which they allow transferring the information on their personal dose rates for further use.

SELLER shall test his subcontractor workers on their knowledge of safety rules and document such in-house testing by signing Statement on Complying with Act on Ionizing Radiation Protection and Nuclear Safety.

# WARRANTY

## SELLER warrants that all services he provides shall be in full conformity with the Contract; shall comply with all applicable codes, standards, laws, rules, and regulations; shall be performed in a highly professional and workmanlike manner which would be exercised by  those who perform similar services at the time the  services are  performed and shall be free from defects in design, material and workmanship; shall conform to applicable specifications, and shall be free from all liens and encumbrances and shall achieve the design, performance and functional requirements as stipulated in TS IN 8230647 (for the Inspection of RV and RVCH Flange Sealing Surfaces) and TS ISI 04/23 (for FOSAR Activities) and other contractual documents. Warranties shall survive acceptance or payment for any and all services required pursuant hereto but shall end with the elapse of the pertinent warranty period as per Art. 12.3.

12.2	The warranty mentioned in the paragraph 12.1 above for the Inspection of RV and RVCH Flange Sealing Surfaces and for the FOSAR Activities shall be 18 months from the date of PURCHASER’s approval of the relevant Final Report.

Fresh warranty period shall commence following the remedy. The duration of the fresh warranty shall be twelve (12) months after the remedy. SELLER shall, however, have no warranty obligations anymore after thirty (30) months following the starting date of the warranty period as stated in the first paragraph of this Article.

The Contract shall remain in effect until the expiration of the warranty period.

12.3	SELLER shall remedy at his own cost all deficiencies related to the performed services or supplied Hardware not attributable to PURCHASER detected and reported in writing claim to SELLER by PURCHASER provided that such PURCHASER’s claim has been received by SELLER within the warranty period. The reporting shall be made within thirty (30) days after the detection of the fault or deficiency. The remedy shall be made at SELLER’s discretion by re-performance of the defective services or supply of replacement of defective Hardware (if any).

12.4 	If SELLER does not fulfill his obligations under Art. 12.3 above within a mutually agreed period of time, SELLER shall correct the defect/reperform service within a reasonable time following PURCHASER’s written notice of the defect. If the PURCHASER fails immediately to notify the SELLER of a defect, which may cause damage to the Products/ the Services, SELLER shall not be liable for any damage, which could have been avoided if the notice had been given immediately.

12.5 	The express warranties and remedies set forth in this Art. shall constitute the sole and exclusive warranties, guarantees and remedies made to the PURCHASER and are exclusive and in lieu of all other warranties, guarantees and remedies of any kind. Any further rights and claims arising from warranty are excluded.

# T A X E S

  - SELLER shall be responsible for the payment of all taxes, duties, tariffs, fees and other like charges of SELLER arising from or in connection with the subject matter of the Contract except for the taxes stated in the Art. 13.2.

  - Regardless of the Art. 13.1 PURCHASER shall be responsible for the payment of customs duties and relevant Slovenian VAT in case that per the Delivery Terms and Conditions of this Contract.

# LICENSES, PERMITS, AND AUTHORIZATIONS

N/A.

# INSURANCE AND INDEMNITY

## PURCHASER’s Insurance at PURCHASER’s Cost

PURCHASER represents that it is the responsible operator of the Plant. Therefore, in no event and under no circumstances shall SELLER, its subcontractor, suppliers, directors, agents and the personnel employed by any of them, (hereinafter collectively referred to as the “Indemnified Parties”), irrespective of their activities under this Contract be considered as being the nuclear operator of the Krško Nuclear Power Plant. For its own protection and the protection of the Indemnified Parties, the PURCHASER has in effect and shall maintain in force Material Damage Insurance Policy including machinery break down covering also nuclear and fire perils, and Third Party Liability Insurance Policy against liability and risks arising out of or resulting from a Nuclear Incident (as defined in the Convention on Third Party Liability in the Field of Nuclear Energy of 29th July 1960, as amended by the Additional Protocol of 28th January 1964 and by the Protocol of 16th November 1982 - the Paris Convention) provided in accordance with Slovenian Nuclear Liability Legislation and available within the Slovenian Insurance Market.

## SELLER’s Insurance at SELLER’s Cost

Equipment Insurance. SELLER shall procure and maintain in full force and effect, until their removal, insurance of SELLER’s materials, equipment, tools and other objects on Site.

Liability Insurance. SELLER shall procure and maintain in full force and effect until leaving the Site insurance against damage to or loss of the property of PURCHASER and damage or loss and injury to third parties (including without limitation PURCHASER’s subcontractor and suppliers and its or their employees), occasioned by any negligent act or omission of SELLER, its subcontractor and suppliers and its and their employees.

Personnel insurance. SELLER in respect of all personnel employed by SELLER and its subcontractors for work on Site shall procure and maintain such insurance against occupational injury as is lawfully required from employers in the relevant jurisdiction(s).

Insurance arranged in pursuance of the above Art.s shall be with a recognized international insurer. SELLER upon request shall submit to PURCHASER certificates of insurance policies.

# LIABILITY

## SELLER's Liability and Indemnity. SELLER shall be liable in respect of, and hereby agrees to indemnify and hold PURCHASER and its subcontractor and all of its or their officers, agents, servants and employees ("Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of PURCHASER and of damage to the property of, and injury (including death) to, any third party (such term including employees of PURCHASER's and SELLER's subcontractor and suppliers of any tier) to the extent that such claim, loss, damage, liability or expense arises out of or results from negligent acts or omissions attributable to SELLER, its subcontractor and suppliers of any tier and their respective directors, officers, agents, servants or employees during their performance of the Work or from negligent defects in design, workmanship and material of the Scope of Services and Delivery.

## PURCHASER’s Liability and Indemnity. PURCHASER shall be liable in respect of, and hereby agrees to indemnify and hold SELLER, its subcontractor and suppliers and all of its or their directors, officers, agents, servants and employees (hereinafter referred to as the "Seller Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of and/or injury (including death) to the Seller Indemnitee or any third party which arises out of or results from acts or omissions attributable to PURCHASER or its subcontractors, or any of its or their respective directors, officers, agents, servants or employees.

16.3	Liability for third party damages due to a nuclear incident shall be governed by the applicable law.

The SELLER and its affiliates, Sub‐contractors of every tier or kind, including licensors and suppliers of information and services (including directors and employees of the foregoing), shall under no circumstances and at no time be liable for any loss or damage resulting directly or indirectly from a Nuclear Incident occurring at the site of NPP Krsko, including any loss or damage to the NPP Krsko or damage to property at the site of NPP Krsko (hereinafter »Nuclear Damage«). The PURCHASER undertakes to indemnify the SELLER, its affiliates and its Sub‐contractors of every tier or kind, including licensors and suppliers of information and services (including directors and employees of the foregoing) against any claims by third parties, including insurers, for any Nuclear Damage. Further the PURCHASER represents that the insurers of the NPP shall have no rights of recourse or subrogation against SELLER and its Sub‐contractors for Nuclear Damage. The PURCHASER waives any rights and claims against the SELLER with respect to Nuclear Damage.

## Definition. For purposes of this Contract, "Nuclear Incident" shall have the meaning assigned to it by the Paris Convention on Third Party Liability in the field of Nuclear Energy of 1960 as amended by the Protocol of 1964 and 1982, including any nuclear risks such as contamination as provided with Slovenian Nuclear Liability legislation.

## A party to the Contract who employs a subcontractor to perform its obligations under the Contract shall be liable to the other party, as for its own actions, for the non-performance or improper performance of the party’s obligations by the subcontractor. The limitations and exclusions of liability under this Art. shall also apply to acts and omissions of SELLER’s employees, officers and SELLER’s subcontractors and suppliers of any tier and their employees and officers.

## Damages, to which parties to the Contract are entitled in accordance therewith, shall be paid against the indemnified party’s invoice sixty (60) days net.

## The total and cumulative liability of the SELLER, including any claim, warranty, indemnity, cost and expenses of any kind arising out of or resulting from any cause whatsoever, whether based on contract, tort (including negligence), termination, rescission, strict liability or otherwise shall in no event exceed 100% of the Total Contract Price. In no event and under no circumstances shall SELLER and PURCHASER be liable for unavailability of plant, plant outage, plant shutdowns or services interruptions, loss of use of equipment or replacement power, costs of capital, loss of opportunities, loss of profits or revenues or loss of use thereof, arising at any time, whether founded on contract, indemnity, tort (including negligence), strict liability or otherwise as well as any indirect or consequential losses or damages of any nature.

The limitations under the Art. 16.7 shall not apply for damages which are caused wilfully or by gross negligence on the part of SELLER, its subcontractors and all of their directors, officers, agents, servants and employees.

## SELLER shall only be liable for damages occurring up to the end of the pertinent Warranty Period if such damages are reported to the SELLER immediately after occurrence or discovery of the damage.

# PROPRIETARY INFORMATION

## PURCHASER’s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by PURCHASER in connection with the Scope of Services and Delivery under this Contract shall remain PURCHASER' s property. SELLER agrees not to use or release to any third party such Information except for purposes of performance of SELLER’s obligations under the Contract unless prior written consent of the contrary is given by the PURCHASER. With respect to such information being disclosed to a subcontractor of SELLER, SELLER shall cause the subcontractor to execute such undertakings as are necessary to give effect to this provision. SELLER shall give PURCHASER a receipt for property furnished by PURCHASER and shall be responsible for safekeeping and return to PURCHASER upon request, upon termination of the Contract, or upon termination of the services to which such property applies.

## SELLER ‘s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by SELLER or its subcontractor in connection with the Scope of Services and Delivery under this Contract shall remain SELLER 's or its subcontractor's proprietary information.

PURCHASER agrees to use such information only for purposes of verification of the design of the Scope of Services and Delivery, for commissioning, operation, testing, analyses, maintenance, and repairs and the installations at Site and the design and execution of any modification therein or extension thereof and agrees to disclose such information to third parties only for obtaining licenses, permits and other official approvals or as required by mandatory law.

In case of disclosure to third parties, PURCHASER shall cause the party to which information is to be provided to execute such undertakings as are necessary to give effect to this provision, save in the case of disclosure to public authorities where PURCHASER shall limit as far as practicable the scope of information so furnished.

SELLER’s proprietary information may not be disclosed to any competitor of SELLER in the field of design and/or construction without SELLER’s prior approval.

The ownership for SELLER's software shall remain with SELLER. SELLER grants the PURCHASER a non-exclusive, non-transferable, personal right to use the software and firmware supplied under the Contract for operation, maintenance and repairing the deliveries of the SELLER under this Contract.

SELLER shall have the right to call for arbitration in the event PURCHASER violates Section 17.2, and also to seek and receive provisional ruling awaiting the valid arbitral decision.

17.3	The provision of this Art. 17 shall not apply to Information, notwithstanding any confidential designation thereof, which is known to the receiving Party without any restriction as to disclosure or use at the time it is furnished, which is or becomes generally available to the public without breach of any agreement, or which is received from a third party without limitation or restriction on said third party or to the receiving Party at the time of disclosure.

The confidentiality undertakings of this Art. 17 shall survive expiration or termination of the contract for 36 months.

# CLAIMS

Any claim of a Party to the Contract shall be in writing, justified in detail and shall be immediately submitted by the Party through a letter or fax, to the authorized representative of the other Party and in no event later than thirty (30) days after discovery of basis for such claim. In case the basis of the claim is of such a nature that it requires longer claim submittal period, then this period will be adequately prolonged. The claiming Party will inform the other Party thereof in advance. No claim shall be valid under the Contract if submitted to the other party 30 days after the expiry of the respective warranty period. The Party against whom the claim has been made shall notify the claiming Party of its acceptance or dismissal of the claim within thirty (30) days after the receipt of the claim. If no such notification is received by the claiming Party within the said time, the claim is deemed to have been accepted by the other Party.

All claims shall be resolved satisfactorily within mutually agreed time period.

# ARBITRATION

19.1   Any differences or disputes arising from or in connection with this Contract shall be settled by an amicable effort on the part of both the Parties to the Contract. An attempt to arrive at a settlement shall be deemed to have failed as soon as one of the Parties to the Contract so notifies the other Party in writing.

19.2	If an attempt by the parties to arrive at a settlement has failed, any differences or disputes arising out of or in connection with the Contract shall be finally settled in accordance with the Arbitration Rules of the International Chamber of Commerce (Paris) by three arbitrators appointed in accordance with the said Rules.  Any such arbitration shall take place in Zurich (Switzerland) and shall be conducted in the English language. The procedural law of this place shall apply where the Rules are silent.

19.3   Any arbitral award shall be rendered in writing and be final and binding upon the Parties. To enforce compliance with such arbitration   decision, it may be entered in the appropriate court in either SELLER’s country or Slovenia, assuming the country otherwise has jurisdiction over the Parties. The arbitral tribunals shall decide on the matter of costs of the arbitration.

19.4   All disputes shall be settled in accordance with the provisions of this Contract.  Arbitration under this Art. is the sole remedy for disputes arising out of the Contract, its performance or the enforcement thereof.

19.5   Performance under this Contract shall continue if reasonably possible during any disagreement or court proceeding, and no funds payable to either Party under the Contract shall be withheld on account of such disagreement or proceeding.

# SUBSTANTIVE LAW

All differences, disputes or claims shall be settled in accordance with the provisions of the Contract, otherwise in accordance with the substantive law in force in Switzerland, without reference to any Swiss conflict of laws and connexity rules incompatible with such choice of law.

# FORCE MAJEURE

21.1	Neither Party to the Contract shall be considered to be in default in the performance of its obligations to the extent that the performance of any such obligation is hindered, prevented or delayed by a Force Majeure circumstance, occurred after entering into the obligations, and which could not be foreseen by the Party in entering into obligations.

21.2	A force majeure circumstance shall mean any circumstance existing which is beyond a Party’s reasonable control and which is not a result of its fault or negligence, including but not limited to: acts of God, such as storm, flood,  or earthquake; acts or omissions of civil or military authority,; war (declared or undeclared), acts or omissions of governmental authority, such as quarantine, embargo, priorities of trade, delay or failure to issue Construction Permit; civil disturbances, such as revolution, rebellion, riots, or insurrection; sabotage, transport accident, fuel or energy shortage, or any other circumstances beyond reasonable control of the Party, which may interfere with the commencement or progress of the Scope of Services and Delivery. The deficiency of labour force and/or defects in material and/or strike of local character with SELLER’s suppliers and subcontractors will not be deemed as Force Majeure.

21.3 	Upon the discovery of the occurrence of any such Force Majeure circumstance, the Party affected by it shall within thirty (30) days of becoming known notify the other Party thereof, and of its estimated effect, by a registered letter, shall use diligent efforts to eliminate such circumstance and mitigate its effects, and shall keep the other Party fully informed of the progress of its efforts. In the notice of the Force Majeure circumstance, the Party shall indicate the cause of the Force Majeure circumstance, its beginning date and anticipated duration with the confirmation by a competent authority, such as Chamber of Commerce, of the validity of the notice. The affected Party shall also notify in the same way the other Party of the termination of the Force Majeure circumstance. However, this communication is dispensed with if the impact of the conditions of Force Majeure on compliance with the contractual obligations becomes obvious to the other Party in any other way. If the circumstances of Force Majeure also affect the postal routes, the thirty (30) days period for notification shall be deemed to apply only after termination of the obstacles in postal transmission.

21.4	The time for the performance of the obligation of the affected Party shall be extended by a time equal to the duration of the Force Majeure circumstance. Any exceptions to the above shall be mutually agreed upon by the Parties.

21.5	If either Party is prevented from performance of the Contract for a continuous period in excess of three weeks because of Force Majeure either Party may suspend the Scope of Delivery. If furthermore a Force Majeure impediment exceeds one (1) month individually or three (3) months in aggregate due to Force Majeure the Contract may be terminated by either Party provided that neither Party is entitled to any profit on the account of the other Party. The termination shall take effect 30 days after receipt of the notice of termination by the other Party. In case the Scope of Services and Delivery is suspended or terminated, the SELLER shall be paid for the Scope of Services and Delivery performed up to the date of suspension or termination.

21.6   Under Force Majeure circumstances, each Party bears its own costs.

# SUSPENSION OF WORK AND TERMINATION

  - Suspension of Work and Termination of Contract by PURCHASER for Default

PURCHASER shall have the right to suspend the Work or any portion of the Work or to terminate the Contract for material default, except for a case of Force Majeure as defined in Art. 21, which shall include the following:

- Significant discontinuances and disturbances of SELLER in the progress of the Work which seriously delays the Project Time Schedules provided that termination of Contract may only be possible if the cap of liquidated damages set forth in Art. 10 is reached, and failure of SELLER to initiate within a reasonable time after PURCHASER's notice to do so the corrective measure to minimize such delays.

- SELLER’s insolvency or bankruptcy, or other financial inability to carry on the Work.

- Failure on the part of SELLER to observe any material requirements of the Contract (not limited to schedule, quality and technology of work), having a direct consequence on the performance of the Contract.

- Collusion for the purpose of illegally procuring a contract or perpetrating fraud on PURCHASER in the construction of the Work under this Contract.

PURCHASER shall give SELLER written notice of any default which may be a basis for suspension or termination hereunder, and shall provide SELLER the opportunity to cure or institute acceptable action to cure such default in a period not to exceed thirty (30) days from receipt of such notice. Such suspension or termination notice, if issued, will be by a written order to SELLER whereupon SELLER shall immediately comply therewith.

When the Work is suspended for any of the causes itemized above; or for any other cause or causes constituting a material default of SELLER, SELLER shall discontinue the Work or such part thereof as PURCHASER shall designate. SELLER shall store all the Work in such way that it does not impede or obstruct activities on Site or get damaged or deteriorate. SELLER shall proceed with Work promptly when notified by Purchaser to resume operations. SELLER shall not be entitled to receive payments for additional costs and expenses as consequence of suspension.

In case of termination PURCHASER shall have the power to complete the Work herein described or such part thereof as it may deem necessary at the expense of the SELLER. Such expense shall be deducted by the PURCHASER from any payments due to the SELLER. If there are no payments due, the SELLER shall reimburse the PURCHASER such amounts. SELLER shall store all the Work in such way that it does not impede or obstruct activities on Site or get damaged or deteriorate and PURCHASER shall have the right to take possession of or use the whole or any portion of the Work completed or then in progress and SELLER shall transfer the title of such Work to PURCHASER.

SELLER shall be entitled to such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and shall not be entitled to any claim for damages or for loss of anticipated profits.

SELLER shall not suspend Work without written direction by PURCHASER order of a court, or governmental agency and will not be entitled to additional compensation by virtue of such order. Neither will it be liable to PURCHASER in the event the Work is suspended by such order.

  - Suspension of Work and Termination of Contract for Convenience by PURCHASER

- The performance of the Work under this Contract may be terminated by PURCHASER at any time, for its convenience. Any such termination shall be by submittal to SELLER of a written Notice of Termination, which shall be effective upon receipt. In such case, SELLER shall be entitled to such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and to the reimbursement of all expenses demonstrably incurred in the termination of this Contract and subcontracting arrangements, including all costs irrevocably committed at the termination/suspension date.

- After receipt of a Notice of Termination, and except as otherwise directed by PURCHASER, SELLER shall:

- Stop Work under the Contract on the date specified in the Notice of Termination.

- Place no further orders or subcontracts for materials, services or facilities.

- Terminate all orders and subcontracts.

- Settle all outstanding liabilities and all claims arising out of such termination of orders and subcontracts, with the approval or ratification of PURCHASER to the extent it may require, which approval or ratification shall be final for all purposes of this clause.

- Transfer title to PURCHASER and deliver in the manner, at the times, and to the extent, if any, directed by PURCHASER:

1) 	The fabricated parts, work in process, completed work, supplies, and other material produced as a part of, or acquired in connection with the performance of the Work terminated by the Notice of Termination; and

2) The completed, or partially completed plans, drawings, information, software and other property (except for SELLER proprietary software) which, if the Contract had been completed, would have been required to be furnished to PURCHASER.

- Take such action as may be necessary, or as PURCHASER may direct, for the protection and preservation of the property related to the Contract which is in the possession of SELLER and in which PURCHASER has or may acquire an interest.

At any time after thirty (30) days after the termination date specified in the Notice of Termination, SELLER may submit to PURCHASER a list, certified as to quantity and quality; of any or all items of termination inventory not previously disposed of, exclusive of items the disposition of which has been directed or authorized by PURCHASER, and may request PURCHASER to remove such items or enter into a storage agreement covering them. Not later than fifteen (15) days thereafter, PURCHASER will accept title to such items and remove them or enter into a storage agreement covering the same; provided, that the list submitted shall be subject to verification by PURCHASER upon removal of the items or, if the items are stored, within forty-five (45) days from the date of submission of the list, and any necessary adjustments to correct the list as submitted, shall be made prior to final settlement.

- After receipt of a Notice of Termination / Suspension, SELLER shall submit to PURCHASER his termination / suspension claim. Such claim shall be submitted promptly but in no event later than five (5) months from the effective date of termination / suspension, unless one or more extensions in writing are granted by PURCHASER upon request of SELLER made in writing with such five (5) months period or authorized extension thereof. Upon failure of SELLER to submit his termination claim within the time allowed, PURCHASER may determine, on the basis of information available to it, the amount, if any, due to SELLER by reason of the termination and shall thereupon pay to SELLER the amount so determined, which shall be the sole amount to which SELLER shall be entitled as a result of such termination.

- Subject to the provisions of paragraph 3 above, SELLER and PURCHASER may agree upon the whole or any part of the amount or amounts to be paid to SELLER by reason of the termination of Work pursuant to this clause, which amount or amounts may include a reasonable allowance for profit on work done; provided that such agreed amount or amounts, exclusive of settlement costs, shall not exceed the Total Contract Price as reduced by the amount of payments otherwise made and as further reduced by the Contract price of work not terminated. The Contract shall be amended accordingly, and SELLER shall be paid the agreed amount.

- PURCHASER shall have the authority to suspend the Work wholly or in part for such period or periods as it may deem necessary. For the suspension under this clause SELLER shall be entitled to receive payment for the part of the Works performed up to the date of suspension including all additional costs and expenses demonstrably accruing to SELLER and its subcontractors as consequence of the suspension, including all costs irrevocably committed at the suspension date and shall be entitled to an equitable adjustment of price and schedule. Should such suspension exceed a maximum period of 12 months, SELLER and PURCHASER shall mutually agree how to proceed. If the agreement is not reached SELLER shall be entitled to terminate the Contract within next six months and be entitled to the reimbursement as stated in Art. 22.2., first paragraph and 22.2 fourth paragraph (termination fee).  If it should become necessary to stop Work for an indefinite period, SELLER shall store all materials in such manner that they will not obstruct or impede activities at the Site unnecessarily nor become damaged in any way, and it shall take every precaution to prevent damage or deterioration of the Work performed. SELLER shall proceed with the Work promptly when notified by PURCHASER to resume operations.

- Nothing contained in this section shall limit or alter the rights which PURCHASER may have for termination of this Contract under the Art. hereof entitled Suspension of the Work and Termination of Contract by PURCHASER for Default or any other right which PURCHASER may have for default or breach of Contract by SELLER. The rights to terminate stipulated in this Contract shall be Parties sole rights to terminate and shall be to the exclusion of any right to rescind the Contract in accordance with the Applicable law.

  - In case of material breach of the Contract by PURCHASER including but not limited to PURCHASER’s failure to make payment or PURCHASER’s insolvency and if PURCHASER fails to make good such material breach within reasonable time after having been informed by SELLER in writing of such material breach, SELLER may suspend and terminate the Contract. In case of termination, SELLER shall have the remedies available under the applicable law.

In the event of termination as per Art. 22.3 above, SELLER shall be entitled to receive all payments set forth in Art. 22.2.1 and 22.2.4.

# CHANGES

In case that certain services and supplies are not included in the original Contract, but have become necessary for the completion of the Project and without difficulties cannot be performed separately from the Contract, according to the Slovenian Public Procurement Act (Art. 46) the Contractor is invited for negotiation in accordance with provisions hereunder.

The SELLER shall, at the PURCHASER’s request, make changes in design or equipment, material or services, not included in the original Contract, if changes in design, equipment, material or services become necessary for the completion of the Project and cannot be performed separately from the Contract without significant difficulties. In such a case the PURCHASER shall invite the SELLER to negotiations by means of a formal letter, while the negotiations shall be subject to the rules provided in this Article.

Any changes to this Contract shall not have any effect until the SELLER and the PURCHASER have agreed on the price to be paid to the SELLER, the delivery or the performance schedule, Quality Assurance conditions and other affected terms and conditions, so as to reflect any changes in (i) SELLER’s efforts which may be required, 2) the scope of work, 3) the time of the performance and the impact on the schedule, 4) the warranties, and 5) the costs to complete.

Upon receipt of the formal letter with the invitation for negotiations, which must include a description of the object of the change and the reasons for such a change, the SELLER shall prepare and submit to the PURCHASER a proposal for a Change Order in written form, which shall:

a) describe the scope of the proposed change,

b) quote in term of man-hours, rates, prices or otherwise as appropriate, the estimated increase or decrease in the total price that would result from the implementation out of the requested change,

c) specify those terms and conditions which are affected by the change, including time for performance and warranties, and

d) if appropriate, indicate the date on which the SELLER would proceed with the change.

If changes are to be required by any Governmental Agency or Authority, including the United States Nuclear Regulatory Commission, prior to institution of the changes, SELLER and PURCHASER shall agree on the price to be paid to the SELLER for the changes. Such a requirement will constitute an obligation for the PURCHASER to initiate the new public procurement procedure as required and an equitable adjustment shall be made in the Project schedule.

The PURCHASER and the SELLER agree that negotiations for change of this Contract shall be considered an independent procedure in which the SELLER may submit reservations with a technically viable justification or other conditions, insofar as they apply only to the object of the change.

In the event negotiations regarding changes requested by the PURCHASER do not lead to a Change Order but do have an impact on the schedule, the project schedule will be extended appropriately.

The SELLER may propose changes to the PURCHASER, but may not implement them without the prior written consent of the PURCHASER, which the PURCHASER may not deny without well founded grounds if such changes would not adversely affect the SELLER’s warranties, the technical soundness of the Work, the safety or the operability of the Plant or the Project Time Schedule.

Any changes to this Contract shall be made in writing; the Parties agree that changes in any other form shall be considered void.

23.1 Change in laws

Any amendment, enforcement or change of interpretation of any Slovenian Government laws, rules, regulations and decrees or other decision and their requirements for compliance as the same shall relate to the Scope of Services and Delivery, whatsoever issued, amended or enforced by any competent authority (including codes and standards and safety regulations) after the date of signature of the Contract will result in an equitable adjustment of price and schedule.

# ANTI-CORRUPTION CLAUSE

The Contracting Parties shall undertake not to give, promise or receive any present or payment in cash or in any other valuable object to or from each other either directly or indirectly or through any official, officer or any other individual employed in the government or any authority (division, department, agency) or through any political party or any candidate of any political party with the intention of bribing so that any official, officer or any other employee, party or candidate would be tempted to abuse his/her position or to exert influence on any law or any decision made by government or any other competent government department with the purpose to obtain or retain a deal or to direct a deal to a commission agent or to any of his assistants, representatives, distributors, subsidiary companies or any other associated companies. In case the act stated in this paragraph has been committed or attempted to be committed, the Contract that had been concluded or had come into force already shall become null and void. In case the Contract is not valid yet, it shall be deemed not to be concluded.

# SOCIAL CLAUSE

During their involvement in this public procurement order, economic subjects shall fulfil all applicable obligations in the field of environmental, social and labour laws, as they are set out in the European Union legislation, national legislation, collective agreements or the rules of international environmental, social and labour regulations and if they do not fulfil the above stated obligations, the Contract will be terminated.

Applicable international social and environmental conventions are listed in Attachment X of EU Directive 2014/24/EU and Attachment XIV of EU Directive 2014/25/EU.

# OTHER PROVISIONS

Documentation to be submitted for SELLER Team

The documents to be submitted to PURCHASER at the latest 30 days before arrival of SELLER's personnel, including his subcontractors at NEK site are as follows:

Documents needed for NEK's cardkey issuance:

For registration of SELLER’s and his subcontractor(s)’s personnel and security vetting of them SELLER shall fill in, sign and submit to PURCHASER the following documents to be previously provided by PURCHASER:

- Request for Entry Card (6.5-C)

- Written Agreement on Ensuring Collective Occupational Health and Safety, Fire Protection and Environmental Management

- Statement on complying with Act on Ionizing Radiation Protection and Nuclear Safety (6.3-C)

- Security Vetting Certificate *

* The security vetting shall be performed by Ministry of the Interior of the Republic of Slovenia in compliance with the provisions of Art. 155. of ZVISJV-1 and appendices of ADP-1.8.005, revision 5. The employer sends an application for carrying out a security vetting of his employees to the Ministry of the Interior of the Republic of Slovenia

Documents needed for work in NEK's radiation controlled area

The documents to be submitted to PURCHASER for the workers who shall perform the activities in NEK's radiation controlled area are as follows:

    - Agreement on Radiological Protection (to be previously provided for signature by NEK)

    - Personal qualification records

    - HP records

    - Medical examination certificate

SELLER shall also, at SELLER's cost, obtain the approval from Slovenian Nuclear Safety Administration (SNSA) at the Ministry for Environment and Energy that SELLER has obtained license in his country to work in the radiation controlled area under conditions and in accordance with procedures equivalent to conditions and procedures as required under the Slovenian Act on Ionising Radiation Protection and Nuclear Safety.

For Temporary Supply for Work in Controlled Area all SELLER's supplied equipment or tools will, upon demobilization, either meet Site unrestricted release criteria to be removed by SELLER and returned to SELLER’s facilities or be shipped by SELLER as a radioactive shipment to SELLER’s or to his subcontractor's facility. In no case shall PURCHASER shall keep any equipment or tools as radioactive waste. PURCHASER shall not accept tools/equipment with detected alpha contamination radiologically checked at the Site entrance control.

Equipment will be controlled after decontamination and before shipping.

Equipment should be below the following acceptance limits for utilization on other plants:

| Contamination Bq / cm² | / | Low toxic | Other |
| --- | --- | --- | --- |
| Removable | tbc | 0,4 | 0 |
| Fixed | tbc |  | tbc |

SELLER shall be obliged to use its best efforts to minimize the quantity of wastes generated by SELLER's Scope of Services (consumables, etc.).

Labor Permits and Visas

SELLER shall obtain, at SELLER's cost, Slovenian labor permits and visas required by Slovenian authorities to permit SELLER's personnel to perform the services under this Contract.

Documents needed for the Employment Service of Slovenia (applicable only for field services for Contractors from EU)

In accordance with the Transnational Provision of Services Act, a foreign employer from EU is required to register with the Employment Service of Slovenia, before starting to provide services, and provide information about:

1. the company name and seat or the address of the employer;

2. the name and date of birth of the responsible person for the employer;

3. the names, dates of birth and citizenships of the posted workers and the addresses of their residences in the RS;

4. the name and date of birth of the posted worker who will be a liaison between the foreign employer and the competent supervisory bodies, when appropriate;

5. the type of service;

6. the duration of performing the service;

7. the address or the location of providing services;

8. the company name, the name and seat or the address of the client.

A foreign employer from EU is required to ensure that when he posts his workers to the RS, the following documents are kept on the location where the activity is carried out and can be provided for inspection at the request of the supervisory body:

a) a copy of the act of posting or a copy of the contract between the client and the service provider and their translation into Slovenian,

b) a certificate of submitted registration of the provision of services,

c) copy from appropriate register showing company's economic activities with translation into Slovenian,

d) certificate of registering trade in accordance with law regulating trades or certificate of company formation in state of employment with their translation into Slovenian,

e) copies of employment contracts and their translations into Slovenian,

f) copies of payroll lists and their translation into Slovenian,

g) register of presence and its translation into Slovenian,

h) documents in the field of Industrial Safety and their translation into Slovenian,

i) proof of wages paid out or copies of equal documents for all posted workers and their translation into Slovenian, and

j) A1 Forms

# ASSIGNMENT

No Party shall assign this Contract in whole or in part without the prior written consent of the other Party, which consent shall not be unreasonably withheld.

# ENTIRE AGREEMENT

The Contract shall constitute the entire and definitive agreement between Parties thereto with respect to the terms and conditions which shall govern. The Contract will supersede all prior written or oral communications between the Parties concerning the subject matter of the Contract which communication upon signature of the Contract by both Parties shall become null and void.

No waiver, alteration or modification of the Contract shall be binding to the Parties unless made in writing and signed by duly authorized representative of the Parties.

# LANGUAGE

SELLER and PURCHASER agree that the official version of the Contract, the Appendices and the Technical and Quality Requirements shall be in English.

All notices, communications or approvals contemplated hereunder shall be in English.

All Technical Documentation, specifications, drawings, reports specified in the Technical and Quality Requirements and all other documents referred to by this Contract and any of its constituting part are required to be in English.

All SELLER’s identified personnel shall be capable to communicate in one of the three languages (Slovenian, Croatian or English). Please, be aware that the knowledge of one of these three languages is a prerequisite to attend and pass the General Employee Training as a precondition for working at NEK.

# EFFECTIVE DATE OF CONTRACT

The effective date of the Contract shall be the date of the Contract signature by the Parties as provided on the first page of the Contract.

# NOTICES

Any notice pursuant to this Contract shall be deemed to have been duly made when sent to the following address:

PURCHASER:

Nuklearna Elektrarna Krško

Vrbina 12

8270 Krško

Slovenia

Attention:

For technical issues:

Mr. Miran Omerzel, for Inspection of Reactor Vessel and Reactor Vessel Head Flange Sealing Surfaces

Phone: +386 7 4802 542

e-mail: miran.omerzel@nek.si

or

Mr. Matija Guliš, for FOSAR activities

Phone: +386 7 4802 742

e-mail: matija.gulis@nek.si

For commercial issues:

Ms. Janja Švajger

Phone: +386 7 4802 327

e-mail: janja.svajger@nek.si

SELLER:

……………………………………

…………………………………..

…………………………………..

Attention:

For technical issues:

Mr./Ms. ……….

Phone: ……….

e-mail: ……….

For commercial issues:

Mr./Ms. ……….

Phone: ……….

e-mail: ……….

# ATTACHMENTS

The following Attachments are constituent integral parts of this Document Part I General Terms and Conditions, as listed below, and are attached hereto.

ATTACHMENT A:	Bank Repayment Guarantee

ATTACHMENT B: 	Bank Guarantee for Good Performance during Warranty Period

ATTACHMENT C:	Subcontractor’s Data and Bidder’s Consent for Direct Payment (in case there are any subcontractors and they request direct payment)

In witness thereof the Parties have signed this Contract in two (2) identical originals of which each Party hereto retains one (1).

For SELLER	For PURCHASER:

Nuklearna Elektrarna Krško d.o.o.

Gorazd Pfeifer

President of the Management Board

Saša Medaković

Member of the Management Board

ATTACHMENT A

EXHIBIT OF BANK REPAYMENT GUARANTEE

BANK:

........................................................................................................................................................................................................................................................................

Place and Date: ..........................................

Beneficiary:

NUKLEARNA ELEKTRARNA KRŠKO d.o.o.

Vrbina 12, 8270 Krsko, Slovenia

Guarantee No. .....................................

Based on the Contract ...................................................................dated ............  concluded between the Beneficiary ........................... ...........................................

and the Principal ........................................................................................................................................................................................................................................................................

for (subject of the Contract) .....................................................................................................................................to the value of ..................................................................................... the Beneficiary shall pay under the Contract 40 % of the Total Contract Price i.e (amount of) .................................................................... as advance payment against presentation of the Bank Repayment Guarantee by which the Bank guarantees to repay the advance payment effected in full or in part if the Principal fails to perform his contractual obligations as to the quality, quantity or schedule in full or in part as stipulated in the Contract.

Based on the Principal’s request, we, the undersigned being the Guarantor under the present guarantee, hereby irrevocably and unconditionally guarantee to repay upon your first written request and irrespective of any Principal’s contract the advance payment to the maximum amount of .......................................................

covering the amount of advance payment received and appertaining interest if the Principal fails to perform its contractual obligations as to the quantity, quality and schedules as stipulated in the Contract. If any partial or subsequent performance of the contractual obligations is allowed, the value of the advance payment to be repaid by the Principal shall be reduced accordingly.

The Guarantee shall be valid until 30 October 2022 at the latest.

After the expiry of the Guarantee validity, the Guarantee becomes null and void regardless its return to the Bank.

The obligations and the rights under this Guarantee can be used by the Beneficiary only or his legal successor.

The Guarantee is governed by ICC Uniform Rules for Demand Guarantees No. 758.

The Guarantee has been issued in three copies: 2 for the Principal (who will submit one original to the Beneficiary) and one copy shall be kept by the Bank.

(Place and Date)								(Guarantor)
ATTACHMENT B

BANK GUARANTEE FOR GOOD PERFORMANCE

DURING WARRANTY PERIOD

Bank:………………………………………………………………………………..

.................................................................................................................

having its registered office at ..................................... (hereinafter referred to as »Guarantor«) upon request of ................................(hereinafter referred to as »Principal«) as of this date ..................................... and based on the decision number ............................. hereby issues the following:

GUARANTEE FOR GOOD PERFORMANCE DURING THE WARRANTY PERIOD No.......................

Contract between Nuclear Power Plant Krško, Vrbina 12 (hereinafter referred to as »Beneficiary«) and the Principal to which the Guarantee relates:

................................

In accordance with the Contract hereby we are issuing to the Beneficiary the Guarantee to the amount of EUR ……………. as a guarantee for good performance of the contractual obligations during the warranty period as stated in Art. 12.3 of the Contract No………….

Aggregate maximum amount of the Guarantor's liability:

EUR .........................

(in words: .........................................................)

Based on the Principal's request, we, the undersigned being the Guarantor under the present guarantee, undertake, subject to no other conditions than those specified in this document, waiving expressly all rights of objection and defense, to pay to the above Beneficiary upon his first written request the amount of:

EUR ........................

(in words: ..........................................................)

for performance of Warranty obligations as per the Contract.

The Guarantor will effect payment at sight without delay and not later than fifteen (15) days from the receipt of Beneficiary's first written request as set out above.

The Guarantee shall be valid from the date of issuance of this Guarantee till 30 days after the end of the Warranty period as stated in the Contract, Art. 12.3.

After the expiry of the Guarantee validity, the Guarantee becomes null and void regardless its return to the Guarantor.

The Guarantee can be used by the Beneficiary only or his legal successor.

The Guarantee is governed by the ICC Uniform Rules for Demand Guarantees No. 758.

The Guarantee has been issued in 3 copies: 2 for the Principal (who will

submit one original to the Beneficiary) and one copy shall be kept by the Guarantor.

Signature and Date : ...............................	Guarantor: ..........................

ATTACHMENT C

SUBCONTRACTOR'S DATA AND BIDDER'S CONSENT FOR DIRECT PAYMENT

Bidder………………………………………………………………………………………………

We declare that we will engage below stated subcontractor for the part of the Scope of Services and Delivery under the Contract for

……………………………………………………………………………………………………

Name and head office: ……………………………………………………………………………………………..

TAX number: ………………………………………………………………………………………………………

Registration number: ………………………………………………………………………………………………

IBAN: …………………………………………………….…………………………………………………

Statutory representative: ……………………………………………………….……………………………..…

Scope of Services and Delivery to be performed by subcontractor: .………………………………………………………………………………………………………

Value of the services and delivery to be performed by subcontractor:

…………………………………………without VAT………….…………………….. with VAT

Place of performance of work: ……………………………………………………………………….…………………..………

Deadline for performance of work: ……………………………………………………………………………………………………

We declare to be engaged in above stated Scope of Services and Delivery performance as subcontractor to the SELLER.

Please indicate your option:

- We request to be paid directly by Purchaser at our account number, for our part of performed scope of Services and Delivery based on the invoice approved by the SELLER.

- We do not request to be paid directly by Purchaser and therefore we declare that we are informed that no later than 60 days after signing the hand over protocol we and the SELLER need to submit the Statement Att.11 of this Bidding Documentation to Purchaser that we have been reimbursed for the performed services, delivery and/or civil works

With signature of this statement we declare the fulfillment of the following conditions:

- subcontractor fulfills all the conditions requested with this Bidding Documentation for his part of the work, delivery or civil works.

We authorize the Purchaser to acquire the necessary data for this public procurement process, which will confirm the fulfillment of the above conditions.

Place and date: 			Stamp: 		      Bidder’s Signature:

________________		                                                  __________________

Subcontractor’s Signature: