DRAFT CONTRACT

For

REFURBISHMENT OF MAIN GENERATOR ROTOR

concluded on __________________ by and between:

NUKLEARNA ELEKTRARNA KRŠKO d.o.o.

Vrbina 12, 8270 Krško, Slovenia,

represented and duly authorized by

Mr. Gorazd Pfeifer, President of the Management Board and 
Mr. Saša Medaković, Member of the Management Board.

(hereinafter referred to as "PURCHASER" or "NEK" or "NPP Krško")

on one part

and

……………………………………………………………………

represented and duly authorized by

Mr. …………………………………………….

(hereinafter referred to as "CONTRACTOR" or “Contractor”)

on the other part

Whereas, CONTRACTOR represents that it is fully qualified to provide PURCHASER with: REFURBISHMENT OF MAIN GENERATOR ROTOR and shall do so in accordance with the terms and conditions herein specified, and

Whereas, the representatives of CONTRACTOR and PURCHASER possess proper and sufficient authority to agree, and

Now therefore, CONTRACTOR and PURCHASER have agreed as follows:

Subject of the Contract:

REFURBISHMENT OF MAIN GENERATOR ROTOR

(hereinafter referred to as “REFURBISHMENT OF MAIN GENERATOR ROTOR”)

The following documents shall constitute the Contract:

- PART I:  - General Terms and Conditions (this Document)

- PART II – NEK Technical Specification No.: TS33-VNMG14 (IN 8231522), Rev. 0 (hereinafter referred to as ”TS33-VNMG14”)

- PART III:   Quotation   No.

PART I - GENERAL TERMS AND CONDITIONS

TABLE OF CONTENTS

0	DEFINITIONS AND ABBREVIATIONS	4

1	CONTRACTOR'S SCOPE OF SERVICES AND DELIVERY	6

2	PURCHASER'S RESPONSIBILITIES	9

3	QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS	9

4	DELIVERABLES TO BE PROVIDED TO PURCHASER	10

5	SCHEDULE REQUIREMENTS	10

6	DELIVERY TERMS AND CONDITIONS	11

7	PRICE	12

8	PAYMENT TERMS AND SCHEDULE	13

9	INSPECTIONS, TESTS & HANDOVER PROTOCOL	16

10	LIQUIDATED DAMAGES	17

11	SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION	18

12	WARRANTY	19

13	T A X E S	21

14	LICENSES, PERMITS, AND AUTHORIZATIONS	21

15	INSURANCE AND INDEMNITY	22

16	LIABILITY	23

17	PROPRIETARY INFORMATION	24

18	CLAIMS	26

19	ARBITRATION	26

20	SUBSTANTIVE LAW	27

21	FORCE MAJEURE	27

22	SUSPENSION OF WORK AND TERMINATION	28

23	CHANGES	32

24	ANTI-CORRUPTION CLAUSE	33

25	SOCIAL CLAUSE	34

26	EXPORT CONTROL	34

27	OTHER PROVISIONS	34

28	ASSIGNMENT	36

29	ENTIRE AGREEMENT	36

30	LANGUAGE	36

31	EFFECTIVE DATE OF CONTRACT	37

32	NOTICES	37

33	ATTACHMENTS	39

DEFINITIONS AND ABBREVIATIONS

As used throughout the Contract, the following terms shall have the meaning set forth hereinafter:

PURCHASER shall mean NUKLEARNA ELEKTRARNA KRŠKO (NPP Krško), Vrbina 12, 8270 Krško, Slovenia, represented by	
Mr. Gorazd Pfeifer, President of the Management Board

and 
Mr. Saša Medaković, Member of the Management Board

CONTRACTOR shall mean                                      , represented by

PARTY or PARTIES shall mean PURCHASER or/and CONTRACTOR as herein under referred to individually or collectively.

CONTRACT shall mean the agreement between PURCHASER and CONTRACTOR consisting of General Terms and Conditions of the Contract (PART I), Technical Specification TS33-VNMG14 (PART II) and Quotation No:      (PART III).

The Contract documents are complementary, and what is called for by anyone of them shall be binding as if called for by all. Any conflicts in the Contract documents shall be reasonably resolved by PURCHASER after mutual discussion with CONTRACTOR. The validity dates of documents commence with the Effective Date of Contract.

SCOPE OF SERVICES AND DELIVERY/PROJECT as defined in Technical Specification TS33-VNMG14 and other contractual documents.

TECHNICAL REPRESENTATIVES shall mean the PURCHASER’s and the CONTRACTOR’s designated representatives through whom all technical, commercial, Quality Assurance and matters shall be channelled.

COMMERCIAL REPRESENTATIVES shall mean the PURCHASER’s and the CONTRACTOR’s designated representatives through whom commercial matters will be evaluated.

TS33-VNMG14 shall mean NEK Technical Specification No.: TS33-VNMG14 (IN 8231522), Rev. 0 for REFURBISHMENT OF MAIN GENERATOR ROTOR.

ROTOR shall mean main generator rotor as defined in NEK Technical Specification No.: TS33-VNMG14

QUOTATION shall mean CONTRACTOR’s Quotation No.:      .dated

PLANT, SITE, NE Krško, NEK, NPP Krško shall mean Nuclear Power Plant Krško.

APPROVED shall mean the status of any document to be furnished by the CONTRACTOR to PURCHASER under the Contract which is approved by PURCHASER with or without comments but which is not rejected by PURCHASER. The date for the resolution of PURCHASER’s comments shall be mutually agreed upon prior to the approval. In no circumstances the approval can relieve CONTRACTOR from the responsibility for failures within CONTRACTOR’s Scope of Services and Delivery.

HARDWARE shall mean all equipment, spare parts, consumables and materials together with required software needed for the completion of the Project and as defined in the contractual documents.

TOTAL CONTRACT PRICE shall mean all-inclusive total price to be paid to the CONTRACTOR as per Article 7.1 of the Contract.

DAP shall mean Delivered at Place NPP Krško Site as per Incoterms 2020

QA shall mean Quality Assurance

VAT shall mean Value Added Tax

SNSA shall mean Slovenian Nuclear Safety Administration

CONTRACTOR'S SCOPE OF SERVICES AND DELIVERY

CONTRACTOR shall perform the service fully in accordance with TS33-VNMG14 and other contractual documentation. The Scope of Services and Delivery entails but is not limited to the following:

- Base Scope of Services (BS)

BS1: Rotor rewind with original copper and new insulation material (Section 2.2 of the TS33-VNMG14)

BS2: Freight services (Transportation (incl. insurance) of ROTOR from NEK to SELLERS’s workshop and back to NEK site

Detailed description of SELLER’s Scope of Services and Delivery is given in TS33-VNMG14, Section 2.2.

- Optional Scope of Services and Delivery (OS)

| Item | Optional Scope of Services and Delivery (Section 2.3 of the TS33-VNMG14) |
| --- | --- |
| OS1 | Optional Scope 1 (OS1) |
| 1 | Long ring modification with tooth top design |
| 2 | New set of rotor retaining rings (if required for Long ring modification) |
| OS2 | Optional Scope 2 (OS2) |
| 1 | New Copper rotor winding |
| 2 | New set of rotor compressor blades |
| 3 | New blower hub |
| 4 | New turbine-end coupling |
| 5 | New Radial Leads with Seals |

Detailed description of CONTRACTOR’s Scope of Services and Delivery is given in TS33-VNMG14, Section 2.3, and contractual documentation.

Optional Scope of Services and Delivery (TS33-VNMG14, Section 2.3) shall be provided at the price given in Art. 7.2 of this Contract, against PURCHASER written authorization provided to CONTRACTOR to perform such proposed Optional Scope.

All other terms and conditions shall be as stated in this Contract.

Turnkey principle

CONTRACTOR shall perform all engineering, necessary to develop modification packages, components dismantling, installation and modification work including the supply of all necessary hardware all in accordance with the agreed upon TS33-VNMG14 and provisions of this Contract. CONTRACTOR shall be responsible, in compliance with the requirements of TS33-VNMG14 and all referenced documents including PURCHASER’s relevant procedures, listed in TS33-VNMG14, for the detailed design, product quality assurance, materials procurement, fabrication, testing, certification, code stamping prior to shipping, examination, inspection, receiving inspection, and pre-service inspection, cleaning.

Any hardware, software or engineering services not specifically included in TS33-VNMG14 shall be deemed to be included in CONTRACTOR’S undertaking if their inclusion is required to make the Scope of Services and Delivery within the interfacing systems and components physically or functionally complete.

All modification packages will comply with the codes and standards as per TS33-VNMG14 and approved for use by PURCHASER, affecting the scope of work to be performed.

During engineering and design the CONTRACTOR will check the as-built status for all important locations.

The CONTRACTOR will develop and provide all necessary construction activities (procedures, organization, material handling, rigging and transportation, erection, quality assurance/quality control, welding, painting/coating, insulation) when required by the TS33-VNMG14.

The CONTRACTOR shall be responsible for delivering turnkey supplied Hardware fully assembled i.e. ready for direct installation without any additional work in accordance with TS33-VNMG14 and other contractual documents.

The CONTRACTOR shall be responsible for developing and providing to the PURCHASER all documentation, drawings, equipment lists, schedules, stress analyses, seismic analyses and other documents necessary for the dismantling of hardware to be replaced and the installation, assistance to licensing, and operation of supplied Hardware as required by the TS33-VNMG14.

Transfer of title and risk of loss shall pass from CONTRACTOR to PURCHASER upon the Handover Protocol signature (Attachment C) by both the Parties.

CONTRACTOR’s Responsibility

The CONTRACTOR's Scope of Services and Delivery shall be completed in a way which will achieve and meet all performance criteria according to TS33-VNMG14 and other requirements of contractual documentation.

Nothing shall relieve CONTRACTOR of the responsibility to perform analyses, tests, inspections and other activities that through the process become necessary to ensure that the design and materials, as well as the product quality, shall meet the requirements in accordance with the contractual documents.

CONTRACTOR shall be responsible for compliance with all detailed requirements of TS33-VNMG14 its referenced documents and other contractual documents.

Subcontractors

For a part of the Scope of Services and Delivery CONTRACTOR may engage the subcontractors which have been listed in the Quotation and accepted by PURCHASER. If CONTRACTOR upon signature of this Contract wants to change or select new subcontractor(s), this shall be subject to PURCHASER approval, which shall not be unreasonably withheld. Based on the law of ZVISJV (Act on Protection against Ionizing Radiation and Nuclear Safety) and based on “Pravilnik o dejavnikih sevalne in jedrske varnosti (JV 5)” Article 67, PURCHASER is responsible for establishing surveillance on CONTRACTOR and its subcontractors to ensure high quality and nuclear safety for the public.

CONTRACTOR shall ensure that all subcontractors meet high standards of competence, experience and capacity in relation to the tasks to be entrusted to them and that they fully comply with the TS33-VNMG14 requirements and the contractual documents.

Since CONTRACTOR retains full responsibility for all aspects of subcontractors performance including quality and schedule, CONTRACTOR shall ensure that adequate periodic audit and surveillance of the subcontractors is maintained. CONTRACTOR shall identify to all subcontractors all applicable Quality Assurance and Quality Control requirements imposed by PURCHASER’s specifications on CONTRACTOR and shall ensure compliance thereto. All subcontractors shall be on CONTRACTOR’s Approved Suppliers List. NEK’s right of access to CONTRACTOR’s subcontractors’ facilities for the purpose of inspection or audit shall be imposed by CONTRACTOR’s documents.

CONTRACTOR shall not subcontract any portion of the Work without the written approval of PURCHASER Responsible Engineer, which shall not be unreasonably withheld. The absence of any reply from the PURCHASER within three (3) weeks is considered as approval under the condition that CONTRACTOR sends prior notification to PURCHASER within two weeks. Subcontractors performing augmented quality service will need to have either quality assurance program approved by PURCHASER or work in conjunction with CONTRACTOR Quality Assurance Program.

Full overall responsibility always remains on CONTRACTOR’s side concerning participation of CONTRACTOR’s subcontractors.

PURCHASER'S RESPONSIBILITIES

PURCHASER’s responsibilities are given in TS33-VNMG14 Section 11.0.

QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS

CONTRACTOR shall meet all quality assurance requirements, design, performance, material, fabrication and technical requirements as well as procedures, codes and standards as stated in TS33-VNMG14 and other contractual documents.

CONTRACTOR will ensure that contractual quality-related requirements are fulfilled using his own quality management system that complies with requirements defined in Section 13 of TS33-VNMG14.

Quality management system is described in document:

……………………………………….

(document ID, title, revision number).

All portions of this document that have been revised during the contractual period under this Contract must be accepted by NEK beforehand.

Work must be performed in accordance with CONTRACTOR’s quality management system and Quality Plan / Control Plan, which has been previously evaluated and accepted by NEK, technical and quality control procedures, valid legislation, and standards relevant for the scope of Services and Delivery. Work will be supervised by responsible work manager and surveyed by CONTRACTOR’s qualified QA/QC personnel.

The CONTRACTOR is also responsible for satisfying quality requirements, commercial and technical requirements, and schedule for subcontractors, if applicable.

Handover documentation must include all quality records, as defined in the Contract, and must be provided to the PURCHASER in the form of a final report data package after completion of all works.

Handover documentation / final report data package will be reviewed and approved by responsible representatives of the PURCHASER and the CONTRACTOR.

Contractual work is performed in accordance with legal requirements, required standards and technical regulations in such a manner as to comply with requirements of environmental management system as per ISO 14001 and occupational health and safety at work system as per ISO 45001.

If the CONTRACTOR fails to fulfil the above-mentioned QA requirements, this will be deemed as violation of contractual obligations by the CONTRACTOR.

DELIVERABLES TO BE PROVIDED TO PURCHASER

CONTRACTOR shall submit to PURCHASER all deliverables as stated in TS33-VNMG14.

SCHEDULE REQUIREMENTS

Schedule Completion Milestones are given in TS33-VNMG14, Section 9.0.

Critical milestones for the Project are:

| No. | Milestone description | Delivery schedule |
| --- | --- | --- |
| 1. | Loading of the ROTOR at NEK site and successful transportation of the ROTOR from NEK site to CONTRACTOR’s facility | T0 + 2 month |
| 2. | Inspection of the rotor and preparation of the documentation with NEK Approval of Project Quality Plan (PQP) and work procedures | T0 + 5 months |
| 3. | Refurbishment of the rotor with successful completion of Final test and measurements as stated in TS33-VNMG14 | T0 + 11 months |
| 4. | Completion of the service and delivery, including unloading, of ROTOR at NEK site | T0 + 12 months |
| 5. | Submittal of Final Document package, accepted by NEK and submittal of Bank Warranty Bond / Guarantee | T0 + 13 months |

T0* = Effective Date of Contract

DELIVERY TERMS AND CONDITIONS

Hardware as well as all other deliverables of CONTRACTOR’s Scope of Services and Delivery as stated in Art. 1 above shall be delivered DAP NPP Krško Site as per Incoterms 2020. CONTRACTOR shall be responsible and shall organize and perform at its cost transportation (incl. preparation of all needed documents) and insurance of all goods, equipment, instruments, material, etc., Delivery specifically includes packing, loading, transportation from NEK site to the Supplier facility and packing, transportation, unloading from the Supplier facility to NEK site.

Transfer of Risk of Loss or Damage

Transfer of risk of loss/or damage as well as of nuclear risk for ROTOR shall pass from PURCHASER to CONTRACTOR upon completion of NEK ROTOR loading from NEK site provided by CONTRACTOR and shall remain with CONTRACTOR all time (during transportation from NEK site to CONTRACTOR’s workshop and back, during refurbishment and storage at CONTRACTOR’s workshop, etc.) until delivery DAP at NEK site of refurbished ROTOR.

Anyhow, ROTOR sent to CONTRACTOR under this Contract shall at all times remain PURCHASER’s property.

CONTRACTOR and its subcontractors shall be liable upon taking over of the ROTOR up until return delivery at NEK site (hereinafter “Custody Period”) as per above including Waste.

SELLER shall be liable for Nuclear Damages it has caused within its Scope of Services during the Custody Period.

Delivery of shipping documents

As soon as possible, but not later than on ten (10) days before the day of delivery of ROTOR, in order to ensure timely receipt and customs clearance, CONTRACTOR or its forwarding agent shall send to PURCHASER the following information and documents:

- estimated time of departure / arrival of ROTOR from / at NEK site;

- shipping invoice with the value of ROTOR sent for refurbishment and the value of the ROTOR refurbishment as per the Contract packing list;

- copy of AWB or RWB or B/L, etc. (relative to means of transportation);

- copy of Shipper’s Declaration for Dangerous Goods (if applicable);

The use of EUR-1 Form for optimizing of customs formalities shall be mandatory whenever feasible.

Temporary Import to NPP Krško site

CONTRACTOR shall organize and perform at its cost all transportation and insurance of all temporarily imported equipment, instruments, material, etc. necessary to perform CONTRACTOR’s Scope of Services and Delivery under this Contract to NPP Krško site, return at CONTRACTOR’s cost without delay from NEK site and insurance of them also during the stay at NEK site.

PRICE

7.1 	The total all-inclusive fixed and firm Total Contract Price for the whole contractual Scope of Services and Delivery as per Art. 1 above under the terms and conditions of this Contract is:

EUR/USD  …………………….(excl. V.A.T.)

(in words: …………………………..Euros/U.S. Dollars)

All labor, materials, equipment, parts, components, and services like engineering and documentation as well as living, traveling and similar costs of CONTRACTOR's personnel, etc. necessary for CONTRACTOR to fulfill its obligations as stated in Art. 1. of this Contract are included in the above Total Contract Price on a turnkey principle.

7.2. 	The price structure is given below:

| Item | Base Scope of Services and Delivery | Price EUR/USD |
| --- | --- | --- |
| BS1 | Rotor rewind with original copper and new insulation material (Section 2.2 of the TS33-VNMG14) |  |
| BS2 | Freight services (Transportation (incl. insurance) of ROTOR from NEK to CONTRACTOR’s workshop and back to NEK site |  |
|  | TOTAL (BS1 + BS2): |  |

7. 3 Price Structure for Optional Scope of Services and Delivery (Section 2.3 of the TS33-VNMG14):

Fixed and Firm prices for the activities as per Article 1.B above are as follows:

| Item | Optional Scope of Services and Delivery (Section 2.3 of the TS33-VNMG14) | Price / EUR |
| --- | --- | --- |
| OS1 | Optional Scope 1 (OS1) |  |
| 1 | Long ring modification with tooth top design |  |
| 2 | New set of rotor retaining rings (if required for Long ring modification) |  |
| OS2 | Optional Scope 2 (OS2) |  |
| 1 | New Copper rotor winding |  |
| 2 | New set of rotor compressor blades |  |
| 3 | New blower hub |  |
| 4 | New turbine-end coupling |  |
| 5 | New Radial Leads with Seals |  |
| OS1 + OS2 | TOTAL MAXIMUM PRICE for Optional Scope of Work = OS-1 + OS-2 |  |

PAYMENT TERMS AND SCHEDULE

8.1.	Payment terms

All payments under this Contract will be made by means of a bank transfer, net due thirty (30) days upon receipt of the goods at NEK site. The invoice shall be approved or rejected within fifteen (15) days from the receipt. If the invoice is not rejected within fifteen (15) days from the receipt, it is considered to be approved.

Payment instalments

Payment will be made against commercial invoices and upon receipt of deliverables as described in the table provided below:

| Item | Description of Payment Milestones |  | Payment Amount (% of Total Contract Price | Estimated Month of Invoice |
| --- | --- | --- | --- | --- |
| 1 | Upon NEK Approval of Project Management Manual (PMM), Project Quality Plan (PQP) and work procedures |  | 5% | T0 + 1 |
| 2 | Upon successful transportation of the ROTOR from NEK site to CONTRACTOR’s facility |  | 15% | T0 + 2 |
| 3 | Upon completion of refurbishment of the ROTOR, that is upon successful completion of Final test and measurements as stated in TS33-VNMG14 |  | 50% | T0 + 11 |
| 4 | Upon successful completion of the service and delivery, including unloading, of ROTOR at NEK site |  | 25% | T0 + 12 |
| 5 | Upon submittal of complete Final Document package, accepted and approved by NEK and submittal of Bank Warranty Bond / Guarantee |  | 5% | T0 + 13 |
|  |  | SUM | 100% |  |

Payment installments for Optional Scope of Work as per Art. 7.3.

Payment for the performed scope defined in Article 1.B above (Optional Scope of Work) will be made upon successful completion of the optional scope and together with the third (3rd) payment installment for the Base Scope (see Art. 8.1, item 3).

Payment of SELLER’s Subcontractors (if any)

If the CONTRACTOR engages a subcontractor who wants to be paid directly and they submit the Attachment D - Subcontractor’s Data and Bidder’s Consent for Direct Payment, NEK is obliged to pay the subcontractor directly.

Beside the invoice submitted by the CONTRACTOR to the PURCHASER with total amount of the payment due including the value of subcontractor work specified separately, the CONTRACTOR shall also approve and submit the invoice and specifications of its subcontractors for each payment milestone.

The CONTRACTOR authorizes the PURCHASER to make direct payments to the subcontractors for their services and supplies, based on the approved invoices addressed to CONTRACTOR.

If a subcontractor is replaced after the conclusion of the Contract or if the CONTRACTOR concludes a contract with a new subcontractor which is subject to direct payment, the CONTRACTOR that concluded the Contract with the PURCHASER must submit to the latter, within 5 days of change:

- The statement that all non-disputed liabilities have been settled to the original subcontractor;

- authorization for the payment of provided and delivered work or products directly to the new subcontractor, and

- the consent of the new subcontractor to the acceptance of direct payment

The payment will be made in accordance with the payment terms and conditions above and based on the signed Subcontractor’s Data and CONTRACTOR’s Consent for Direct Payment in the form and content according to Attachment D.

.

8.2	Guarantees

The Bank Good Performance Guarantee to the amount of 10% of the Total Contract Price as per Art. 7.1 in the form and content according to Attachment A, shall be submitted to PURCHASER not later than three (3) weeks after the Contract signature with a validity of 30 days upon signature of the Handover Protocol.

After receipt of NEK authorization for the Optional Scope as per Art. 1.B, if any, the amount of the Good Performance Guarantee shall be increased accordingly. Relevant Amendment to the Good Performance Guarantee shall be submitted to PURCHASER within twenty (20) days upon receipt of PURCHASER authorization for the Optional Scope.

If CONTRACTOR fails to perform its contractual obligations as to the quantity, quality and schedule, due to reasons attributable to CONTRACTOR, PURCHASER shall be entitled to call for the Good Performance Guarantee up to its total amount. PURCHASER shall notify CONTRACTOR of disputed contractual obligations and its intent to call for the Guarantee.

The Warranty Bond/ Guarantee for Operational period to the amount of 5% of the Total Contract Price as per Art.7.1 shall be submitted to PURCHASER not later than three (3) weeks from the day of the rotor's installation in the main generator in the form and content according to Attachment B, with a validity of 30 days after the end of warranty period as stated in Art. 12.3.2 (Operational Warranty) below.

If CONTRACTOR does not fulfill its obligations under Art. 12 within reasonable mutually agreed period of time in no case exceeding the warranty period as stated in Art.12.3, PURCHASER is then entitled to call for the Warranty Bond/ Guarantee issued by CONTRACTOR’s bank up to its total amount. PURCHASER shall notify CONTRACTOR of disputed contractual obligations and its intent to call for the Guarantee.

All here abovementioned Guarantees shall be issued at CONTRACTOR’s cost by a first-class bank and shall be returned by PURCHASER to CONTRACTOR on their date of expiry.

8.3	Delayed Payment

If PURCHASER fails to make any payment due (for which payment preconditions as stated in the table as per Art. 8.1 above have been fulfilled) to CONTRACTOR, PURCHASER shall pay to CONTRACTOR interest on the amount of each delayed payment. The interest shall be calculated in accordance with the Statutory Default Interest Rate Act (“Zakon o predpisani obrestni meri zamudnih obresti – ZPOMZO”) at the due payment date from the date the payment is due until the payment in full is effected. Such interest shall be paid by PURCHASER to CONTRACTOR on a quarterly basis by bank transfer.

INSPECTIONS, TESTS & HANDOVER PROTOCOL

All tests and inspections shall be performed in accordance with TS33-VNMG14.

After successful completion of the Project, the Parties, CONTRACTOR and PURCHASER, shall sign the Handover Protocol as per Attachment C if no significant faults are counteracting. Minor remaining issues such as open Project deficiencies reports of category C and D to be taken care of by CONTRACTOR or PURCHASER shall be registered in the Handover Protocol and the signing of the Handover Protocol shall not be withheld for such minor remaining issues.

The prerequisites to sign the Handover Protocol are successful completion of all activities as defined in TS33-VNMG14 with completed resolution of all open items (non-conformances and deficiency reports) and NEK receipt of Test Reports.

The Parties shall sign the Handover Protocol within ten (10) days after the preconditions in the previous paragraph are fulfilled. The protocol shall include at least:

(i)	the date on which all the requirements of Article 9 have actually been met and consequently the date and exact hour on which the warranty period commences;

(ii)	a list of all open Project deficiencies reports of category C and D. No open deficiencies category A and B (as defined in PMM) are allowed.

If the Handover Protocol is not signed within ten (10) days after the prerequisites to sign have been fulfilled or if CONTRACTOR fails to perform said tests for reasons attributable to CONTRACTOR, Handover Protocol shall be deemed as signed and the warranty period commences.

Signing of the Handover Protocol does not interfere with the rights of PURCHASER related to warranty for hidden defects for which CONTRACTOR is responsible.

LIQUIDATED DAMAGES

10.1 	Liquidated damages for delay

In case of delay in the delivery of CONTRACTOR’s Scope of Services and Delivery in completion of the following critical milestones as defined in Article 5 of the Contract, due to reasons solely attributable to CONTRACTOR, CONTRACTOR shall pay to PURCHASER liquidated damages as follows:

  - 1,00% of the Total Contract Price per entire week (7 days) of delay in the completion of the milestone No. 4 as stated in Article 5, starting after the first day of delay, but maximum up to 10% of the Total Contract Price (excl. VAT).

10.2   Liquidated Damages for Violation of Occupational Safety and Health (OSH), Fire Safety (FS) and Foreign Material Exclusion (FME) Rules and Regulations

The PURCHASER may demand payment of a contractual penalty if the CONTRACTOR violates contractual obligations by:

- violating the legislation and requirements of the Krško NPP in the area of occupational safety and health (OSH), fire safety (FS) and Krško NPP procedures,

- violating the provisions of the safety plan and the instructions of the safety and health at work coordinator for the work execution phase in accordance with the Decree on ensuring safety and health at work on temporary and mobile construction sites, (Official Gazette of the Republic of Slovenia, No. 83/2005),

- work suspension due to serious violations of OSH measures (endangering the life and health of workers)

based on violations of OSH and FS requirements recorded by the person in charge of PURCHASER's Safety at Work, project manager, work supervisor, head of department, head of unit, sector director…), repeated violations in the book of measures from OSH at the construction site and entered in the minutes of the coordination meeting or the violation recorded in the request of the corrective program (ZKP) on the basis of which the request of the Occupational Safety and Health at Work Department the request for the calculation of the contractual penalty is given.

The amount of the penalty for each individual deviation from the above is EUR 10,000 per breach and is not included in other contractual penalties. There are also no billing restrictions for them based on the contract value. In the case of repeated individual violations, the multiples of the above penalties will be charged (eg 2 x violation = 2 x penalty, 3 x violation = 3 x penalty, etc.).

The Purchaser reserves the right to permanently remove the worker who does not comply with the rules of OSH and FS from the Site.

The Purchaser has the right to withdraw from the contract due to the violations of the provisions of OSH and FS on the part of the contractor.

Violation of the provisions of OSH and FS may also be a reason for the bid impermissibility and the exclusion of the contractor from future procurement processes.

Any extension of the contractual deadlines, price increase or claims for damages due to the suspension of works for the above reasons are not permitted.

SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION

In order to ensure safety and health at work, CONTRACTOR shall follow the provisions of the Law on Safety and Health at Work (Official Gazette of RS No.43/11), ADP procedure 1.1.033 Safety and Health at Work at NPP Krško and in compliance with provisions of a separate written Agreement concluded in accordance with Article 39 of the Law on Safety and Health at Work of the Republic of Slovenia.

CONTRACTOR shall make sure that the performance of Work be in accordance with internal procedures and instructions issued by responsible PURCHASER’s employees.

In order to fulfill the provisions of the Act on Protection against Ionizing Radiation and Nuclear Safety, the contractual parties shall adhere to the Agreement on Protection against Ionizing Radiation (applicable for suppliers performing services in the controlled area). Based on the provisions of this Agreement, CONTRACTOR shall provide all necessary data and signed statements of workers by which they allow transferring the information on their personal dose rates for further use.

CONTRACTOR shall test his subcontractor workers on their knowledge of safety rules and document such in-house testing by signing Statement on Complying with Act on Ionizing Radiation Protection and Nuclear Safety.

The CONTRACTOR employing simultaneously more than 15 workers on Site (per one Purchase Order/Contract or more Purchase Orders) or performing high risk works shall nominate and ensure the presence of a safety at work expert depending on the number of workers and the degree of the worker(s) safety risk exposure.

The criteria for temporary Site presence of the safety at work expert are as follows:

- 15 – 30 workers               1 day/week

- 31 – 50 workers               2 days/week

- 51 – 80 workers               3 days/week

- 81 – 150 workers            permanent presence

- ˃ 150 workers                  ˃ 2 workers/permanent presence

NOTE: The above numbers do not include permanently hired staff

Should the PURCHASER learn that the CONTRACTOR has not fulfilled relevant above criterion,  within 3 working days PURCHASER will invite him in writing (by e-mail, mail) to do it. The Site presence of the required safety at work expert on the day following the receipt of the above invitation will be considered as a fulfillment of the above criterion.  If the CONTRACTOR does not comply with the above criterion, CONTRACTOR shall pay liquidated damages of 1000€ for each day of non compliance.

One week before the beginning of Site works as a minimum, the Contractor shall submit to PURCHASER a list containing the details on  safety at work expert  presence on Site. In case of doubt in the level of risk associated with the works to be performed and resulting demand for safety expert Site presence, the Contractor may contact directly Mr. Rudi Janežič (e-mail: rudi.janezic@nek.si )

WARRANTY

12.1	CONTRACTOR warrants that all the hardware furnished under this Contract shall be new and free from liens, encumbrances and defects in title and shall be free from defects in design, workmanship and material and that the Hardware delivered under this Contract shall achieve the performance and functional requirements as stipulated in TS33-VNMG14 and other contractual documents. Approval of material, test results, suppliers and schedules by PURCHASER shall not in any way limit or diminish the CONTRACTOR’s warranties hereunder.

12.2 	CONTRACTOR warrants that all services he provides shall be in full conformity with the Contract; shall comply with all applicable codes, standards, laws, rules, and regulations; shall be performed in a highly professional and workmanlike manner which would be exercised by  those who perform similar services at the time the services are  performed and shall be free from defects in design, material and workmanship; shall conform to applicable specifications, and shall be free from all liens  and encumbrances and shall  achieve the design, performance and functional requirements as stipulated in TS33-VNMG14 and other contractual documents. Warranties shall survive acceptance or payment for any and all services required pursuant hereto but shall end with the elapse of the pertinent warranty period as per Article 12.3.

12.3.1	Storage Warranty: A period of up to 20 years from the date of delivery to the NEK site, during which the rotor, when stored, handled, and maintained in accordance with the specific guidelines and instructions provided by the SELLER, is guaranteed against defects due to manufacturing issues.

12.3.2 Operational Warranty: A period of 10 (ten) years commencing from the day of the rotor's installation in the main generator. This warranty is conditioned on the rotor being handled, stored, maintained, operated, installed, or serviced in line with the requirements of the applicable operating instructions provided by the SELLER, design documentation, and as per the terms and conditions stipulated in this Contract or universally accepted industry practices and standards. It further asserts that the rotor has neither been operated beyond its rating nor mishandled in any form, ensuring its operation and maintenance in a normal and proper manner under proficient supervision and without exposure to accidents, alterations, misuse, or abuse.

The Contract shall remain in effect until the expiration of the Operational Warranty period.

12.4	CONTRACTOR shall remedy at his own cost all faults and hardware and service deficiencies pursuant to Article 12.1 and/or 12.2 above, other than normal wear and tear or faults or deficiencies attributable to PURCHASER detected and reported in writing claim to CONTRACTOR by PURCHASER provided that such PURCHASER’s claim has been received by CONTRACTOR within the warranty period. The reporting shall be made within thirty (30) days after the detection of the fault or deficiency. The remedy shall be made by:

(i) replacement or repair of the faulty or deficient unit (spare part or equipment) at CONTRACTOR’s option approved by PURCHASER, such approval being not unreasonably withheld, and within shortest reasonable period of time to be determined between the Parties or

(ii) repeat of the defective services.

CONTRACTOR’s obligations to remedy faults or deficiencies under the warranty shall be deemed to have been fulfilled when CONTRACTOR has either made the remedy at the Site or delivered and installed the replacement unit to PURCHASER and PURCHASER has inspected and accepted it. A refusal shall be for justified reasons only. CONTRACTOR shall pay the transportation and insurance cost from Krško Site to the designated facility and back to DAP Krško Site.

A fresh warranty period shall commence for the repaired or replaced material/equipment. The duration of the fresh warranty shall be …. years after the remedy. CONTRACTOR shall, however, have no warranty obligations anymore after … years following the starting date of the warranty period as stated in Art. 12.3 above.

12.5	If CONTRACTOR does not fulfil his obligations under Article 12.4 above within a mutually agreed upon period of time, PURCHASER shall be entitled to correct the defective pieces of Hardware or services at the expense of CONTRACTOR provided that such expense shall not exceed the price of the above defective pieces/services as reasonably evaluated by PURCHASER and CONTRACTOR on the basis of the current international market prices.

12.6	If it becomes necessary for CONTRACTOR to repair or provide replacement  Hardware under these warranties, PURCHASER, without cost to CONTRACTOR, shall, to the extent necessary for CONTRACTOR to perform its warranty obligations:

(i) provide reasonable access to the defective part(s);

(ii) make available to CONTRACTOR, PURCHASER's facilities, equipment and tools available on Site, and (iii) perform any necessary decontamination.

12.8		The express warranties and remedies set forth in this Article 12 shall constitute the sole and exclusive warranties, guarantees and remedies made to the PURCHASER and are exclusive and in lieu of all other warranties, guarantees and remedies of any kind. Any further rights and claims arising from warranty are excluded except as provided under this Article.

12.9    CONTRACTOR shall not, in any event, be responsible for any work done by third parties or for any loss, damage, cost or expense arising out of or resulting from such work, provided that in the event CONTRACTOR has engaged subcontractors for the performance of its obligations under the Contract CONTRACTOR shall have the same responsibilities to PURCHASER for such work as it has with respect to its own work.

T A X E S

  - CONTRACTOR shall be responsible for the payment of all taxes, duties, tariffs, fees and other like charges of CONTRACTOR arising from or in connection with the subject matter of the Contract.

  - CONTRACTOR shall register with Slovenian Taxing Authorities and obtain Slovenian VAT Number. In that case CONTRACTOR's invoices to PURCHASER shall include Slovenian VAT. CONTRACTOR is responsible for calculation and payment of Slovenian VAT according to Slovenian VAT. In no case shall the CONTRACTOR impose his Slovenian subcontractors VAT in his invoices to PURCHASER.

  - If CONTRACTOR does not register with Slovenian Taxing Authorities and has no Slovenian VAT number, PURCHASER will pay VAT and apply »Reverse Charge according to Article 196 Council Directive 2006/112/EC as amended by Council Directive 2008/8EG.

  - PURCHASER shall be responsible only for the payment of Slovenian import tax (payable at Slovenian boarder) and relevant Slovenian V.A.T.

LICENSES, PERMITS, AND AUTHORIZATIONS

14.1	If required, CONTRACTOR shall assist PURCHASER in all its own dealings with the Government Agencies, Licensing Bodies/Authorities and independent inspection agencies in Slovenia. This shall be limited to assistance in obtaining and maintaining licenses, permits and authorizations that may be required for CONTRACTOR’s performance under the Contract. To the extent requested, CONTRACTOR shall make any necessary presentations to, participate in meetings with, and furnish required information to the competent Slovenian authorities.

CONTRACTOR shall be responsible for all dealings with Government Agencies outside Slovenia. This shall include but not necessarily be limited to obtaining, maintaining and paying for licenses, permits and authorizations that may be required for CONTRACTOR’s performance under this Contract concerning manufacturing, export and transportation of Hardware within CONTRACTOR’s Scope of Services and Delivery.

INSURANCE AND INDEMNITY

PURCHASER’s Insurance at PURCHASER’s Cost

PURCHASER represents that it is the responsible operator of the Plant. Therefore, in no event and under no circumstances shall CONTRACTOR, its subcontractor, suppliers, directors, agents and the personnel employed by any of them, (hereinafter collectively referred to as the “Indemnified Parties”), irrespective of their activities under this Contract be considered as being the nuclear operator of the Krško Nuclear Power Plant. For its own protection and the protection of the Indemnified Parties, the PURCHASER has in effect and shall maintain in force Material Damage Insurance Policy including machinery break down covering also nuclear and fire perils, and Third Party Liability Insurance Policy against liability and risks arising out of or resulting from a Nuclear Incident (as defined in the Convention on Third Party Liability in the Field of Nuclear Energy of 29th July 1960, as amended by the Additional Protocol of 28th January 1964 and by the Protocol of 16th November 1982 - the Paris Convention) provided in accordance with Slovenian Nuclear Liability Legislation and available within the Slovenian Insurance Market.

CONTRACTOR’s Insurance at CONTRACTOR’s Cost

Equipment Insurance. CONTRACTOR shall procure and maintain in full force and effect, until their removal, insurance of CONTRACTOR’s materials, equipment, tools and other objects on Site.

Liability Insurance. CONTRACTOR shall procure and maintain in full force and effect until leaving the Site insurance against damage to or loss of the property of PURCHASER and damage or loss and injury to third parties (including without limitation PURCHASER’s subcontractor and suppliers and its or their employees), occasioned by any negligent act or omission of CONTRACTOR, its subcontractor and suppliers and its and their employees.

Scope of Services and Delivery Insurance. CONTRACTOR shall procure and maintain in full force and effect until leaving the Site Insurance of  the Scope of Services and Delivery for its full replacement value insofar as it relates to equipment and material, at any time against damage or loss howsoever caused. PURCHASER shall be a named insured under such insurance. Any proceeds under such insurance shall be applied towards the repair or replacement of any part of the Scope or Services and Delivery damaged or lost.

Personnel insurance. CONTRACTOR in respect of all personnel employed by CONTRACTOR and its subcontractors for work on Site shall procure and maintain such insurance against occupational injury as is lawfully required from employers in the relevant jurisdiction(s).

Insurance arranged in pursuance of the above Articles shall be with a recognized international insurer. CONTRACTOR upon request shall submit to PURCHASER certificates of insurance policies.

LIABILITY

CONTRACTOR's Liability and Indemnity. CONTRACTOR shall be liable in respect of, and hereby agrees to indemnify and hold PURCHASER and its subcontractor and all of its or their officers, agents, servants and employees ("Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of PURCHASER and of damage to the property of, and injury (including death) to, any third party (such term including employees of PURCHASER's and CONTRACTOR's subcontractor and suppliers of any tier) to the extent that such claim, loss, damage, liability or expense arises out of or results from acts or omissions attributable to CONTRACTOR, its subcontractor and suppliers of any tier and their respective directors, officers, agents, servants or employees during their performance of the Work or from defects in design, workmanship and material of the Scope of Services and Delivery.

PURCHASER’s Liability and Indemnity. PURCHASER shall be liable in respect of, and hereby agrees to indemnify and hold CONTRACTOR, its subcontractor and suppliers and all of its or their directors, officers, agents, servants and employees (hereinafter referred to as the "Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of and/or injury (including death) to the Indemnitee or any third party which arises out of or results from acts or omissions attributable to PURCHASER or its subcontractors, or any of its or their respective directors, officers, agents, servants or employees.

16.3	The Indemnified Parties as defined in Article 16.1 shall in no event be liable with respect to any loss of, damage to property and/or injury (including death), caused by or resulting from a Nuclear Incident and PURCHASER shall indemnify, hold harmless and waive any and all claims and rights of recourse against CONTRACTOR.

  - Definition. For purposes of this Contract, "Nuclear Incident" shall have the meaning assigned to it by the Paris Convention on Third Party Liability in the field of Nuclear Energy of 1960 as amended by the Protocol of 1964 and 1982, including any nuclear risks such as contamination as provided with Slovenian Nuclear Liability legislation and available within Slovenian Insurance Market.

A party to the Contract who employs a subcontractor to perform its obligations under the Contract shall be liable to the other party, as for its own actions, for the non-performance or improper performance of the party’s obligations by the subcontractor.

Damages, to which parties to the Contract are entitled in accordance therewith, shall be paid against the indemnified party’s invoice thirty (30) days net. If CONTRACTOR fails to pay damages in accordance with the Contract against said PURCHASER’s invoice, the PURCHASER is entitled to demand the payment out of the guarantee valid at that time CONTRACTOR’s Bank Good Performance Guarantee or Warranty Bond/ Guarantee.

The total and cumulative liability of the CONTRACTOR, including any claim, warranty, cost and expenses of any kind arising out of or resulting from any cause whatsoever, whether based on contract, tort (including negligence), strict liability or otherwise shall in no event exceed 100% of the Total Contract Price. In no event and under no circumstances shall CONTRACTOR and PURCHASER be liable for indirect or consequential damages, unavailability of plant, plant outage, plant shutdowns or services interruptions, loss of use of equipment or replacement power, costs of capital, loss of profits or revenues or loss of use thereof, arising at any time, whether founded on contract, tort (including negligence), strict liability or otherwise as well as any indirect or consequential losses or damages of any nature.

The limitations under this Article shall not apply for damages which are caused willfully or by gross negligence on the part of CONTRACTOR, its subcontractors and all of their directors, officers, agents, servants and employees.

CONTRACTOR shall only be liable for damages occurring up to the end of the pertinent Warranty Period if such damages are reported to the CONTRACTOR immediately after occurrence or discovery of the damage.

PROPRIETARY INFORMATION

PURCHASER’s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by PURCHASER in connection with the Scope of Services and Delivery under this Contract shall remain PURCHASER' s property. CONTRACTOR agrees not to use or release to any third party such Information except for purposes of performance of CONTRACTOR’s obligations under the Contract unless prior written consent of the contrary is given by the PURCHASER. With respect to such information being disclosed to a subcontractor of CONTRACTOR, CONTRACTOR shall cause the subcontractor to execute such undertakings as are necessary to give effect to this provision. CONTRACTOR shall give PURCHASER a receipt for property furnished by PURCHASER and shall be responsible for safekeeping and return to PURCHASER upon request, upon termination of the Contract, or upon termination of the services to which such property applies.

CONTRACTOR ‘s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by CONTRACTOR or its subcontractor in connection with the Scope of Services and Delivery under this Contract shall remain CONTRACTOR 's or its subcontractor's proprietary information.

PURCHASER agrees to use such information only for purposes of verification of the design of the Scope of Services and Delivery, for commissioning, operation, testing, analyses, maintenance, and repairs and the installations at Site and the design and execution of any modification therein or extension thereof and agrees to disclose such information to third parties only for obtaining licenses, permits and other official approvals or as required by mandatory law.

In case of disclosure to third parties, PURCHASER shall cause the party to which information is to be provided to execute such undertakings as are necessary to give effect to this provision, save in the case of disclosure to public authorities where PURCHASER shall limit as far as practicable the scope of information so furnished.

CONTRACTOR’s proprietary information may not be disclosed to any competitor of CONTRACTOR in the field of design and/or construction without CONTRACTOR’s prior approval.

The ownership for CONTRACTOR's software shall remain with CONTRACTOR. CONTRACTOR grants the PURCHASER a non-exclusive, non-transferable, personal right to use the software and firmware supplied under the Contract for operation, maintenance and repairing the deliveries of the CONTRACTOR under this Contract.

CONTRACTOR shall have the right to call for arbitration in the event PURCHASER violates Section 17.2, and also to seek and receive provisional ruling awaiting the valid arbitral decision.

17.3	The provision of this Article 17. shall not apply to Information, notwithstanding any confidential designation thereof, which is known to the receiving Party without any restriction as to disclosure or use at the time it is furnished, which is or becomes generally available to the public without breach of any agreement, or which is received from a third party without limitation or restriction on said third party or to the receiving Party at the time of disclosure.

CLAIMS

Any claim of a Party to the Contract shall be in writing, justified in detail and shall be immediately submitted by the Party through a letter or fax, to the authorized representative of the other Party and in no event later than thirty (30) days after discovery of basis for such claim. In case the basis of the claim is of such a nature that it requires longer claim submittal period, then this period will be adequately prolonged. The claiming Party will inform the other Party thereof in advance. No claim shall be valid under the Contract if submitted to the other party 30 days after the expiry of the respective warranty period. The Party against whom the claim has been made shall notify the claiming Party of its acceptance or dismissal of the claim within thirty (30) days after the receipt of the claim. If no such notification is received by the claiming Party within the said time, the claim is deemed to have been accepted by the other Party.

All claims shall be resolved satisfactorily within mutually agreed time period.

ARBITRATION

19.1   Any differences or disputes arising from or in connection with this Contract shall be settled by an amicable effort on the part of both the Parties to the Contract. An attempt to arrive at a settlement shall be deemed to have failed as soon as one of the Parties to the Contract so notifies the other Party in writing.

19.2 If an attempt by the parties to arrive at a settlement has failed, any differences or disputes arising out of or in connection with the Contract shall be finally settled in accordance with the Arbitration Rules of the International Chamber of Commerce (Paris) by three arbitrators appointed in accordance with the said Rules.  Any such arbitration shall take place in Zurich (Switzerland) and shall be conducted in the English language. The procedural law of this place shall apply where the Rules are silent.

19.3   Any arbitral award shall be rendered in writing and be final and binding upon the Parties. To enforce compliance with such arbitration   decision, it may be entered in the appropriate court in either CONTRACTOR’s country or Slovenia, assuming the country otherwise has jurisdiction over the Parties. The arbitral tribunals shall decide on the matter of costs of the arbitration.

19.4   All disputes shall be settled in accordance with the provisions of this Contract.  Arbitration under this Article is the sole remedy for disputes arising out of the Contract, its performance or the enforcement thereof.

19.5   Performance under this Contract shall continue if reasonably possible during any disagreement or court proceeding, and no funds payable to either Party under the Contract shall be withheld on account of such disagreement or proceeding.

SUBSTANTIVE LAW

All differences, disputes or claims shall be settled in accordance with the provisions of the Contract, otherwise in accordance with the substantive law in force in Switzerland, without reference to any Swiss conflict of laws and connexity rules incompatible with such choice of law.

FORCE MAJEURE

21.1	Neither Party to the Contract shall be considered to be in default in the performance of its obligations to the extent that the performance of any such obligation is hindered, prevented or delayed by a Force Majeure circumstance, occurred after entering into the obligations, and which could not be foreseen by the Party in entering into obligations.

21.2	A force majeure circumstance shall mean any circumstance existing which is beyond a Party’s reasonable control and which is not a result of its fault or negligence, including but not limited to: acts of God, such as storm, flood,  or earthquake; acts or omissions of civil or military authority; war (declared or undeclared), acts or omissions of governmental authority, such as quarantine, embargo, priorities of trade, delay or failure to issue Construction Permit; civil disturbances, such as revolution, rebellion, riots, or insurrection; sabotage, transport accident, fuel or energy shortage, or any other circumstances beyond reasonable control of the Party, which may interfere with the commencement or progress of the Scope of Services and Delivery. The deficiency of labour force and/or defects in material and/or strike of local character with CONTRACTOR’s suppliers and subcontractors will not be deemed as Force Majeure.

21.3 	Upon the discovery of the occurrence of any such Force Majeure circumstance, the Party affected by it shall within thirty (30) days of becoming known notify the other Party thereof, and of its estimated effect, by a registered letter, shall use diligent efforts to eliminate such circumstance and mitigate its effects, and shall keep the other Party fully informed of the progress of its efforts. In the notice of the Force Majeure circumstance, the Party shall indicate the cause of the Force Majeure circumstance, its beginning date and anticipated duration with the confirmation by a competent authority, such as Chamber of Commerce, of the validity of the notice. The affected Party shall also notify in the same way the other Party of the termination of the Force Majeure circumstance. However, this communication is dispensed with if the impact of the conditions of Force Majeure on compliance with the contractual obligations becomes obvious to the other Party in any other way. If the circumstances of Force Majeure also affect the postal routes, the thirty (30) days period for notification shall be deemed to apply only after termination of the obstacles in postal transmission.

21.4	The time for the performance of the obligation of the affected Party shall be extended by a time equal to the duration of the Force Majeure circumstance. Any exceptions to the above shall be mutually agreed upon by the Parties.

21.5	If either Party is prevented from performance of the Contract for a continuous period in excess of three weeks because of Force Majeure either Party may suspend the Scope of Delivery. If furthermore a Force Majeure impediment exceeds one (1) month individually or three (3) months in aggregate due to Force Majeure the Contract may be terminated if both the Parties agree in writing with such decision provided that neither Party is entitled to any profit on the account of the other Party. The termination shall take effect at the date mutually agreed by the Parties. In case the Scope of Services and Delivery is suspended or terminated, the CONTRACTOR shall be paid for the Scope of Services and Delivery performed up to the date of suspension or termination.

21.6   Under Force Majeure circumstances, each Party bears its own costs.

SUSPENSION OF WORK AND TERMINATION

  - Suspension of Work and Termination of Contract by PURCHASER for Default

PURCHASER shall have the right to suspend the Work or any portion of the Work or to terminate the Contract for material default which shall include the following:

- Significant discontinuances and disturbances of CONTRACTOR in the progress of the Work which seriously delays the Project Time Schedules

- CONTRACTOR’s insolvency or bankruptcy, or other financial inability to carry on the Work.

- Failure on the part of CONTRACTOR to observe any material requirements of the Contract (not limited to schedule, quality and technology of work), having a direct consequence on the performance of the Contract.

- Collusion for the purpose of illegally procuring a contract or perpetrating fraud on PURCHASER in the construction of the Work under this Contract.

PURCHASER shall give CONTRACTOR written notice of any default which may be a basis for suspension or termination hereunder, and shall provide CONTRACTOR the opportunity to cure or institute acceptable action to cure such default in a period not to exceed thirty (30) days from receipt of such notice. Such suspension or termination notice, if issued, will be by a written order to CONTRACTOR whereupon CONTRACTOR shall immediately comply therewith.

When the Work is suspended for any of the causes itemized above; or for any other cause or causes constituting a material default of CONTRACTOR, CONTRACTOR shall discontinue the Work or such part thereof as PURCHASER shall designate. CONTRACTOR shall store all the Work in such way that it does not impede or obstruct activities on Site or get damaged or deteriorate. CONTRACTOR shall proceed with Work promptly when notified by Purchaser to resume operations. CONTRACTOR shall not be entitled to receive payments for additional costs and expenses as consequence of suspension.

In case of termination PURCHASER shall have the power to complete the Work herein described or such part thereof as it may deem necessary at the expense of the CONTRACTOR. Such expense shall be deducted by the PURCHASER from any payments due to the CONTRACTOR. If there are no payments due, the CONTRACTOR shall reimburse the PURCHASER such amounts. CONTRACTOR shall store all the Work in such way that it does not impede or obstruct activities on Site or get damaged or deteriorate and PURCHASER shall have the right to take possession of or use the whole or any portion of the Work completed or then in progress and CONTRACTOR shall transfer the title of such Work to PURCHASER. CONTRACTOR shall be entitled to such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and shall not be entitled to any claim for damages or for loss of anticipated profits.

CONTRACTOR shall not suspend Work without written direction by PURCHASER order of a court, or governmental agency and will not be entitled to additional compensation by virtue of such order. Neither will it be liable to PURCHASER in the event the Work is suspended by such order.

  - Suspension of Work and Termination of Contract for Convenience by PURCHASER

The performance of the Work under this Contract may be suspended or terminated by PURCHASER at any time, for its convenience. Any such suspension or termination shall be by submittal to CONTRACTOR of a written Notice of Termination, which shall be effective upon receipt.

PURCHASER shall have the authority to suspend the Work wholly or in part for such period or periods as it may deem necessary. For the suspension under this clause CONTRACTOR shall be entitled to receive payment for the part of the Works performed up to the date of suspension including all additional costs and expenses demonstrably accruing to CONTRACTOR and its subcontractors as consequence of the suspension and shall be entitled to an equitable adjustment of schedule. Should such suspension exceed a maximum period of 12 months, CONTRACTOR and PURCHASER shall mutually agree how to proceed. If the agreement is not reached CONTRACTOR shall be entitled to terminate the Contract within next six months and be entitled to the reimbursement as stated in article 22.2., 3rd paragraph.  During suspension CONTRACTOR shall store all materials in such manner that they will not obstruct or impede activities at the Site unnecessarily nor become damaged in any way, and it shall take every precaution to prevent damage or deterioration of the Work performed. CONTRACTOR shall proceed with the Work promptly when notified by PURCHASER to resume operations.

In case of termination, CONTRACTOR shall be entitled to 1) such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and to 2) reimbursement of all direct and documented expenses demonstrably incurred, including demobilization costs, in the termination of this Contract and CONTRACTOR’s supplies and subcontracting arrangements.

After receipt of a Notice of Termination, and except as otherwise directed by PURCHASER, CONTRACTOR shall:

Stop Work under the Contract on the date specified in the Notice of Termination.

- Place no further orders or subcontracts for materials, services or facilities.

- Terminate all orders and subcontracts.

- Settle all outstanding liabilities and all claims arising out of such termination of orders and subcontracts, with the approval or ratification of PURCHASER to the extent it may require, which approval or ratification shall be final for all purposes of this clause.

- Transfer title to PURCHASER and deliver in the manner, at the times, and to the extent, if any, directed by PURCHASER:

1) 	The fabricated parts, work in process, completed work, supplies, and other material produced as a part of, or acquired in connection with the performance of the Work terminated by the Notice of Termination; and

2) The completed, or partially completed plans, drawings, information, software and other property (except for CONTRACTOR proprietary software) which, if the Contract had been completed, would have been required to be furnished to PURCHASER.

- Use its reasonable efforts to sell, in the manner, at the times, to the extent, any property of the types referred to in e above; provided, however, that CONTRACTOR:

1) 	Shall not be required to extend credit to any PURCHASER and

2) 	May acquire any such property under the conditions prescribed and at a price or prices approved by PURCHASER;	
And provided further, that the proceeds of any such transfer or disposition shall be applied in reduction of any payments to be made by PURCHASER to CONTRACTOR under this Contract or shall otherwise be credited to the price or cost of the Work covered by this Contract.

- Take such action as may be necessary, or as PURCHASER may direct, for the protection and preservation of the property related to the Contract which is in the possession of CONTRACTOR and in which PURCHASER has or may acquire an interest.

At any time after thirty (30) days after the termination date specified in the Notice of Termination, CONTRACTOR may submit to PURCHASER a list, certified as to quantity and quality; of any or all items of termination inventory not previously disposed of, exclusive of items the disposition of which has been directed or authorized by PURCHASER, and may request PURCHASER to remove such items or enter into a storage agreement covering them. Not later than fifteen (15) days thereafter, PURCHASER will accept title to such items and remove them or enter into a storage agreement covering the same; provided, that the list submitted shall be subject to verification by PURCHASER upon removal of the items or, if the items are stored, within forty-five (45) days from the date of submission of the list, and any necessary adjustments to correct the list as submitted, shall be made prior to final settlement.

After receipt of a Notice of Termination, CONTRACTOR shall submit to PURCHASER his termination claim. Such claim shall be submitted promptly but in no event later than five (5) months from the effective date of termination, unless one or more extensions in writing are granted by PURCHASER upon request of CONTRACTOR made in writing with such five (5) months period or authorized extension thereof. Upon failure of CONTRACTOR to submit his termination claim within the time allowed, PURCHASER may determine, on the basis of information available to it, the amount, if any, due to CONTRACTOR by reason of the termination and shall thereupon pay to CONTRACTOR the amount so determined, which shall be the sole amount to which CONTRACTOR shall be entitled as a result of such termination.

Nothing contained in this section shall limit or alter the rights which PURCHASER may have for termination of this Contract under the article hereof entitled Suspension of the Work and Termination of Contract by PURCHASER for Default or any other right which PURCHASER may have for default or breach of Contract by CONTRACTOR.

  - In case of material breach of the Contract by PURCHASER including but not limited to PURCHASER’s failure to make payment or PURCHASER’s insolvency and if PURCHASER fails to make good such material breach within reasonable time after having been informed by CONTRACTOR in writing of such material breach, CONTRACTOR may suspend and terminate the Contract. In case of termination, CONTRACTOR shall be entitled to receive all payments set forth in article 22.2., 3rd paragraph.

CHANGES

In case that certain additional services and supplies (Extra Work as per Article 1. C of this Contract), which are not included in the original Scope of this Contract, but have become necessary for the completion of the Project and without difficulties cannot be performed separately from the Contract, according to the Slovenian Public Procurement Act (Article 95) the Contractor is invited for negotiation in accordance with provisions hereunder.

The CONTRACTOR shall, at the PURCHASER’s request, make changes in design or equipment, material or services, not included in the original Contract, if changes in design, equipment, material or services become necessary for the completion of the Project and cannot be performed separately from the Contract without significant difficulties. In such a case the PURCHASER shall invite the CONTRACTOR to negotiations by means of a formal letter, while the negotiations shall be subject to the rules provided in this Article.

Any changes to this Contract shall not have any effect until the CONTRACTOR and the PURCHASER have agreed on the price to be paid to the CONTRACTOR, the delivery or the performance schedule, Quality Assurance conditions and other affected terms and conditions, so as to reflect any changes in:

1) CONTRACTOR’s efforts which may be required,

2) the scope of work,

3) the time of the performance and the impact on the schedule,

4) the warranties,

5) the costs to complete.

Upon receipt of the formal letter with the invitation for negotiations, which must include a description of the object of the change and the reasons for such a change, the CONTRACTOR shall prepare and submit to the PURCHASER a proposal for a Change Order in written form, which shall:

a) describe the scope of the proposed change,

b) quote in term of man-hours, rates, prices or otherwise as appropriate, the estimated increase or decrease in the total price that would result from the implementation out of the requested change,

c) specify those terms and conditions which are affected by the change, including time for performance and warranties, and

d) if appropriate, indicate the date on which the CONTRACTOR would proceed with the change.

If changes are to be required by any Governmental Agency or Authority, including the United States Nuclear Regulatory Commission, prior to institution of the changes, CONTRACTOR and PURCHASER shall agree on the price to be paid to the CONTRACTOR for the changes. Such a requirement will constitute an obligation for the PURCHASER to initiate the new public procurement procedure as required and an equitable adjustment shall be made in the Project schedule.

The PURCHASER and the CONTRACTOR agree that negotiations for change of this Contract shall be considered an independent procedure in which the CONTRACTOR may submit reservations with a technically viable justification or other conditions, insofar as they apply only to the object of the change.

In the event negotiations regarding changes requested by the PURCHASER do not lead to a Change Order but do have an impact on the schedule, the project schedule will be extended appropriately.

The CONTRACTOR may propose changes to the PURCHASER, but may not implement them without the prior written consent of the PURCHASER, which the PURCHASER may not deny without well founded grounds if such changes would not adversely affect the CONTRACTOR’s warranties, the technical soundness of the Work, the safety or the operability of the Plant or the Project Time Schedule.

Any changes to this Contract shall be made in writing; the Parties agree that changes in any other form shall be considered void.

23.1 Change in laws

Any amendment, enforcement or change of interpretation of any Slovenian Government laws, rules, regulations and decrees or other decision and their requirements for compliance as the same shall relate to the Scope of Services and Delivery, whatsoever issued, amended or enforced by any competent authority (including codes and standards and safety regulations) after the date of signature of the Contract will result in an equitable adjustment of price and schedule.

ANTI-CORRUPTION CLAUSE

The Contracting Parties shall undertake not to give, promise or receive any present or payment in cash or in any other valuable object to or from each other either directly or indirectly or through any official, officer or any other individual employed in the government or any authority (division, department, agency) or through any political party or any candidate of any political party with the intention of bribing so that any official, officer or any other employee, party or candidate would be tempted to abuse his/her position or to exert influence on any law or any decision made by government or any other competent government department with the purpose to obtain or retain a deal or to direct a deal to a commission agent or to any of his assistants, representatives, distributors, subsidiary companies or any other associated companies. In case the act stated in the this paragraph has been committed or attempted to be committed, the Contract that had been concluded or had come into force already shall become null and void. In case the Contract is not valid yet, it shall be deemed not to be concluded.

SOCIAL CLAUSE

During their involvement in this public procurement order, economic subjects shall fulfil all applicable obligations in the field of environmental, social and labour laws, as they are set out in the European Union legislation, national legislation, collective agreements or the rules of international environmental, social and labour regulations and if they do not fulfil the above stated obligations, the Contract will be terminated.

Applicable international social and environmental conventions are listed in Attachment X of EU Directive 2014/24/EU and Attachment XIV of EU Directive 2014/25/EU.

EXPORT CONTROL

The Parties shall comply with all applicable export control laws governing the

transactions described in this Contract. PURCHASER agrees not to disclose,

directly or indirectly, transfer, export or re-export out of E.U. any CONTRACTOR’s provided export controlled information, or any direct products or technology resulting therefrom without CONTRACTOR’s prior approval which shall not be unreasonably withheld.

PURCHASER shall cooperate in good faith with the reasonable requests of

CONTRACTOR made for purposes of its compliance with such laws and regulations.

Notwithstanding any other provisions in this Contract, the obligations set forth

in this clause shall be binding on the Parties so long as the relevant applicable

export laws are in effect.

OTHER PROVISIONS

Documentation to be submitted for CONTRACTOR Team

The documents to be submitted to PURCHASER at the latest 30 days before arrival of CONTRACTOR's personnel, including his subcontractors at NEK site are as follows:

Documents needed for NEK's cardkey issuance:

For registration of CONTRACTOR’s and his subcontractor(s)’s personnel and security vetting of them CONTRACTOR shall fill in, sign and submit to PURCHASER the following documents to be previously provided by PURCHASER:

- Request for Entry Card (6.5-C)

- Written Agreement on Ensuring Collective Occupational Health and Safety, Fire Protection and Environmental Management

- Statement on complying with Act on Ionizing Radiation Protection and Nuclear Safety (6.3-C)

- Security Vetting Certificate *

* The security vetting shall be performed by Ministry of the Interior of the Republic of Slovenia in compliance with the provisions of Article 155. of ZVISJV-1 and appendices of ADP-1.8.005, revision 5. The employer sends an application for carrying out a security vetting of his employees to the Ministry of the Interior of the Republic of Slovenia

Labor Permits and Visas

CONTRACTOR shall obtain, at CONTRACTOR's cost, Slovenian labor permits and visas required by Slovenian authorities to permit CONTRACTOR's personnel to perform the services under this Contract.

CONTRACTOR shall also, at CONTRACTOR's cost, obtain the approval from Slovenian Nuclear Safety Administration (SNSA) at the Ministry for Environment and Energy that CONTRACTOR has obtained license in his country to work in the radiation controlled area under conditions and in accordance with procedures equivalent to conditions and procedures as required under the Slovenian Act on Ionising Radiation Protection and Nuclear Safety.

Documents needed for the Employment Service of Slovenia (applicable only for field services for Contractors from EU)

In accordance with the Transnational Provision of Services Act (Official Gazette of RS, no. 40/23), the foreign employer from EU is required to register with the Employment Service of Slovenia, before starting to provide services, and provide information about:

1. the company name and seat or the address of the employer;

2. the name and date of birth of the responsible person for the employer;

3. the names, dates of birth and citizenships of the posted workers and the addresses of their residences in the RS;

4. the name and date of birth of the posted worker who will be a liaison between the foreign employer and the competent supervisory bodies, when appropriate;

5. the type of service;

6. the duration of performing the service;

7. the address or the location of providing services;

8. the company name, the name and seat or the address of the client.

A foreign employer from EU is required to ensure that when he posts his workers to the RS, the following documents are kept on the location where the activity is carried out and can be provided for inspection at the request of the supervisory body:

a) a copy of the act of posting or a copy of the contract between the client and the service provider and their translation into Slovenian,

b) a certificate of submitted registration of the provision of services,

c) copy from appropriate register showing company's economic activities with translation into Slovenian,

d) certificate of registering trade in accordance with law regulating trades or certificate of company formation in state of employment with their translation into Slovenian,

e) copies of employment contracts and their translations into Slovenian,

f) copies of payroll lists and their translation into Slovenian,

g) register of presence and its translation into Slovenian,

h) documents in the field of Industrial Safety and their translation into Slovenian,

i) proof of wages paid out or copies of equal documents for all posted workers and their translation into Slovenian, and

j) A1 Forms

ASSIGNMENT

No Party shall assign this Contract in whole or in part without the prior written consent of the other Party, which consent shall not be unreasonably withheld.

ENTIRE AGREEMENT

The Contract shall constitute the entire and definitive agreement between Parties thereto with respect to the terms and conditions which shall govern. The Contract will supersede all prior written or oral communications between the Parties concerning the subject matter of the Contract which communication upon signature of the Contract by both Parties shall become null and void.

No waiver, alteration or modification of the Contract shall be binding to the Parties unless made in writing and signed by duly authorized representative of the Parties.

LANGUAGE

CONTRACTOR and PURCHASER agree that the official version of the Contract, the Appendices and the Technical and Quality Requirements shall be in English.

All notices, communications or approvals contemplated hereunder shall be in English.

All Technical Documentation, specifications, drawings, reports specified in the Technical and Quality Requirements and all other documents referred to by this Contract and any of its constituting part are required to be in English.

All CONTRACTOR’s identified personnel shall be capable to communicate in one of the three languages (Slovenian, Croatian or English). Please, be aware that the knowledge of one of these three languages is a prerequisite to attend and pass the General Employee Training as a precondition for working at NEK.

EFFECTIVE DATE OF CONTRACT

The effective date of the Contract shall be the date of the Contract signature by the Parties as provided on the first page of the Contract.

Despite any conflicting provision contained in this Contract or the applicable

Contract documents, the provisions of the following Articles shall survive

expiration or termination of this Contract:

Article 15 – Insurance and Indemnity

Article 16 – Liability

Article 17 – Proprietary Information

Article 18 – Claims

Article 19 – Arbitration

Article 20 – Substantive Law

Article 22 – Suspension of Work and Termination

Article 26 - Export Control Provision

NOTICES

Any notice pursuant to this Contract shall be deemed to have been duly made when sent to the following address:

PURCHASER:

Nuklearna Elektrarna Krško

Vrbina 12

8270 Krško

Slovenia

Attention:

For technical issues:

Mr. Klemen Grozina

Phone: 00386/7/4802-820

e-mail: klemen.grozina@nek.si

For commercial issues:

Ms. Nataša Lisec

Phone: 00386/7/4802-619

e-mail: natasa.lisec@nek.si

CONTRACTOR:

Attention:

For technical issues:

For commercial issues:

ATTACHMENTS

The following Attachments are constituent integral parts of this Document Part I General Terms and Conditions, as listed below, and are attached hereto.

ATTACHMENT A:	Bank Good Performance Guarantee

ATTACHMENT B:	Bank Warranty Bond /Guarantee

ATTACHMENT C:	Handover Protocol upon Successful Completion of the Project

ATTACHMENT D: 	Subcontractor’s Data and Bidder’s Consent for Direct Payment (in case there are any subcontractors and they request direct payment)

ATTACHMENT E:     Statement of Received Payment for Subcontractor's Part of Services or/and Delivery (if applicable)

In witness thereof the Parties have signed this Contract in two (2) identical originals of which each Party hereto retains one (1).

For CONTRACTOR	For PURCHASER:

Nuklearna Elektrarna Krško d.o.o.

Gorazd Pfeifer

President of the Management Board

Saša Medaković

Member of the Management Board

- ATTACHMENT A

BANK GOOD PERFORMANCE GUARANTEE

Bank:……………........................................................................................................ ……………………………………………………..

having its registered office at ..................................... (hereinafter referred to as »Guarantor«) upon request of ................................(hereinafter referred to as »Principal«) as of this date ..................................... and based on the decision number ............................. hereby issues the following:

GOOD PERFORMANCE GUARANTEE NO. ......................

Contract between Nuclear Power Plant Krško, Vrbina 12 (hereinafter referred to as »Beneficiary«) and the Principal to which the Guarantee relates:

.........................................

Total Contract Price: EUR………………

(in words:                                                           )

covering schedule, quantity, quality and other terms of the Contract No….

In accordance with the Contract hereby we are issuing to the Beneficiary the Guarantee to the amount of EUR……………. as a guarantee for good performance of the contractual obligations.

Aggregate maximum amount of the Guarantor's liability:

EUR ………………………

(in words:                                                             )

Based on the Principal's request, we, the undersigned being the Guarantor under the present guarantee hereby guarantee that the Principal shall perform its contractual obligations as to the quantity, quality and schedule.

If the Principal fails to perform its above contractual obligations, we undertake, subject to no other conditions than those specified in this document, waiving expressly all rights of objection and defense, to pay to the above Beneficiary upon his first written request the amount of:

EUR ………………………..

(in words:	)

Our obligation to pay is valid also in cases of partial fulfillment of contractual obligations when the guaranteed quality, quantity and schedule have not been met completely.

The payment shall be made within fifteen (15) days from receipt by the Bank of the first written request accompanied by a copy of the letter sent to the Principal giving him notice that he is in breach of its obligations under the Contract.

The Guarantee shall be valid from the date of issuance of this Guarantee till …………….

After the expiry of the Guarantee validity, the Guarantee becomes null and void regardless its return to the Guarantor.

The Guarantee can be used by the Beneficiary only or his legal successor.

The Guarantee is governed by the ICC Uniform Rules for Demand Guarantees No. 758.

The Guarantee has been issued in 3 copies: 2 for the Principal (who will submit one original to the Beneficiary) and one copy shall be kept by the Guarantor.

Signature and Date : ...............................				Guarantor:..........................

- ATTACHMENT B

Bank Warranty Bond/ Guarantee for Operational Period

TYPE OF GUARANTEE: Warranty Bond/ Guarantee

GUARANTEE NO.: ………………….. (draft)

THE GUARANTOR: ……………..

THE APPLICANT: ……………

THE BENEFICIARY: …………………

THE UNDERLYING RELATIONSHIP: The Applicant’s obligation during warranty period in respect of the Agreement No. …….. dated ………….concluded between Beneficiary and the Applicant for …….………..at a total price of EUR ………...

According to the Conditions of the above Agreement a Warranty Guarantee in the amount of ……% of the total contractual price, i.e. EUR ……….., is required.

GUARANTEE AMOUNT AND CURRENCY: EUR ……….

(in words: Euro .………………./100)

ANY DOCUMENT REQUIRED IN SUPPORT OF THE DEMAND FOR PAYMENT, APART FROM THE SUPPORTING STATEMENT THAT IS EXPLICITLY REQUIRED IN THE TEXT BELOW: none

FORM OF PRESENTATION: Paper presentation only by registered mail or any courier service. The demand must be presented through the intermediary of your bank confirming that your signature(s) on your demand for payment appear to conform to specimen(s) held in your bank’s records.

PLACE FOR PRESENTATION: ………

EXPIRY: ……………….

As Guarantor, we hereby irrevocably undertake to pay the Beneficiary any amount up to the Guarantee Amount upon presentation of the Beneficiary’s complying demand, in the form of presentation indicated above, supported by such other documents as may be listed above and in any event by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, indicating in what respect the Applicant is in breach of its obligations under the Underlying Relationship.

Beneficiary’s statement must state, that the Applicant after the receipt of request to make good a deficiency in the warranty period under the Underlying Relationship, hasn’t fulfilled his contractual warranty obligations under the Underlying relationship.

Any demand under this Guarantee must be received by us on or before Expiry at the Place for presentation indicated above.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758.

Name and address of the Beneficiary

Date

Or

IRREVOCABLE LETTER OF CREDIT ISSUED BY CONTRACTOR’S BANK

(SPECIMEN FORM FOR CONTRACT PERFORMANCE GUARANTEE)

With the same obligations as stated in the above bank guarantee.

- ATTACHMENT C

HANDOVER PROTOCOL

UPON SUCCESSFUL COMPLETION

We hereby certify that the Project “REFURBISHMENT OF MAIN GENERATOR ROTOR” at NPP Krško has been successfully completed fully in line with the scope, schedule, delivery time and other terms and conditions stipulated in the Contract No……..-

and is operationally and functionally satisfying the requirements as stated in Technical Specification TS33-VNMG14

The list of all open Project deficiencies reports (no deficiency shall affect general operability of the system) is attached hereto ( if applicable).

The list of remaining non-installed items of hardware with relevant technical/QA documentation and part numbers and other details necessary for warehouse acceptance which shall be moved to PURCHASER’s warehouse with the transfer of Title and Risk of Loss is attached to this Protocol (if applicable).

The date on which all the requirements as stated in Art. 9 of the Contact No. ……. have actually been met and consequently the date and exact hour on which the warranty period commences is:……………………..

Date:								Date:

For CONTRACTOR				  	For PURCHASER

ATTACHMENT D

SUBCONTRACTOR'S DATA AND BIDDER'S CONSENT FOR DIRECT PAYMENT

(in case there are any subcontractors and they request direct payment)

Bidder………………………………………………………………………………………………

We declare that we will engage below stated subcontractor for the part of the Scope of Services and Delivery under the Contract for

……………………………………………………………………………………………………

Name and head office: ……………………………………………………………………………………………..

TAX number: ………………………………………………………………………………………………………

Registration number: ………………………………………………………………………………………………

IBAN: …………………………………………………….…………………………………………………

Statutory representative: ……………………………………………………….……………………………..…

Scope of Services and Delivery to be performed by subcontractor: .………………………………………………………………………………………………………

Value of the services and delivery to be performed by subcontractor:

…………………………………………without VAT………….…………………….. with VAT

Place of performance of work: ……………………………………………………………………….…………………..………

Deadline for performance of work: ……………………………………………………………………………………………………

We declare to be engaged in above stated Scope of Services and Delivery performance as subcontractor to the CONTRACTOR.

Please indicate your option:

- We request to be paid directly by Purchaser at our account number, for our part of performed scope of Services and Delivery based on the invoice approved by the CONTRACTOR.

- We do not request to be paid directly by Purchaser and therefore we declare that we are informed that no later than 60 days after signing the hand over protocol we and the CONTRACTOR need to submit the Statement Att.11 of this Bidding Documentation to Purchaser that we have been reimbursed for the performed services, delivery and/or civil works

With signature of this statement we declare the fulfillment of the following conditions:

- subcontractor fulfills all the conditions requested with this Bidding Documentation for his part of the work, delivery or civil works.

We authorize the Purchaser to acquire the necessary data for this public procurement process, which will confirm the fulfillment of the above conditions.

Place and date: 			Stamp: 		      Bidder’s Signature:

________________		                                                  __________________

Subcontractor’s Signature:

ATTACHMENT E

STATEMENT OF RECEIVED PAYMENT FOR SUBCONTRACTOR'S PART OF SERVICES, DELIVERY OR/AND CIVIL WORKS (if applicable)

CONTRACTOR:__________________________________________

and

SUBCONTRACTOR:                   ______________________________

hereby declare that the Subcontractor stated above has received all payments

due for his part of the services, delivery and/or civil works under the Contract

No._______________

for the _________________________________.

(subject of the public tender)

Place and Date: 		  Stamp:    	 		 Bidder’s Signature:

Subcontractor’s Signature:

In accordance with article 94.6 of ZJN-3, the Purchaser shall receive this statement in 60 days after the main Contractor issues the final invoice.