FORM 1

Client:

DRAVSKE ELEKTRARNE MARIBOR d.o.o.

Obrežna ulica 170, 2000 Maribor

Tenderer:

TENDER NO.___________

Pursuant to a Public procurement notice published on the Public Procurement Portal on ___________, under the No. ________________, we hereby tender for the contract and attach our tender documentation in accordance with the Instructions for the preparation of the tender.

- Subject of the public procurement: Replacement of the gantry crane and trash-rack cleaning machine at the Zlatoličje HPP.

- The tender is valid up to and including 120 days after the deadline for submission of tenders.

- Tender submission:

(circle as appropriate)

- An independent tender, as a single Tenderer

- A joint tender, as the leading partner in a group of tenderers

- A tender with subcontractors, as a single Tenderer with subcontractors

- A tender using the capacities of other entities

- Tenderer’s details:

| TENDERER’S FULL NAME AND BUSINESS NAME: |  |
| --- | --- |
| TENDERER’S REGISTERED OFFICE (ADDRESS): |  |
| CONTACT PERSON: |  |
| CONTACT PERSON'S E-MAIL ADDRESS: |  |
| CONTACT PERSON'S PHONE NUMBER: |  |
| VAT IDENTIFICATION NUMBER: |  |
| REGISTRATION NUMBER: |  |
| BANK ACCOUNT NUMBER AND BANK: |  |
| PERSON AUTHORISED FOR SIGNING THE CONTRACT (specifying their position): |  |
| TENDERER’S LEGAL REPRESENTATIVES: |  |

We declare, under criminal and civil liability, that:

- In the event of being selected to execute the public procurement contract, we commit to carrying out the contractual obligations in a professional and high-quality manner. Our performance will adhere to the rules of the profession, comply with applicable regulations (laws, rules, standards, technical approvals), and follow technical instructions, recommendations, and norms.

- We fully agree and accept, without any limitation whatsoever, all the terms, conditions, and other requirements laid out by the Client in these public procurement documents.

- We accept the contents of the model contract (Form 5) and confirm the truthfulness of all declarations in the other documents attached to the tender.

- We have reviewed the entire public procurement documents when preparing the tender.

- We are fully aware of the scope and complexity of the public procurement contract.

- We will not assert any claims against the Client in the event that we are not selected to execute the public contract.

- We have only made true or truthful statements.

- If selected as the most advantageous Tenderer and invited to finalise the contract, we commit to submitting a Performance Security to the Client within 15 days of contract signing, adhering to Item 4.2 of the Instructions to Tenderers. The wording of the security will align with the sample provided in the Public procurement documents (Form 11).

- If selected as the most advantageous Tenderer and upon concluding the contract, we will furnish the Client with a Defects Liability Security within 15 days of the final contractual takeover of works, as per Item 4.3 of the Instructions to Tenderers. The wording of the security will align with the sample provided in the Public procurement documents (Form 12).

- If selected as the most advantageous Tenderer and invited to finalise the contract, we commit to providing a copy of the insurance policy or a certified declaration from the insurer, as per Item 4.4 of the Instructions to Tenderers. This documentation will demonstrate that the Contractor's equipment and services are appropriately insured in accordance with the provisions of the Item.

- We acknowledge that the Client is not obligated to accept any of the tenders received and retains the right to terminate the public procurement at any time in accordance with legal provisions.

- We assume responsibility for ensuring the functionality of the email address provided by us in the e-JN system. It is understood that the Client holds no responsibility for any failure to receive emails sent to the specified email address. The Tenderer shall be considered to have received any email sent to that address via the Client's email address, e-JN, or the procurement portal at the time of dispatch.

Date, place:

The Tenderer shall confirm the above by submitting an ESPD form.

FORM 2

POWER OF ATTORNEY FOR SIGNING THE TENDER PROPOSED BY A GROUP OF TENDERERS

| Signed (name and surname of the responsible person - authorising person) |  |
| --- | --- |
| Title (position) |  |
| Company name and address |  |

| Signed (name and surname of the responsible person - authorising person) |  |
| --- | --- |
| Title (position) |  |
| Company name and address |  |

| Signed (name and surname of the responsible person - authorising person) |  |
| --- | --- |
| Title (position) |  |
| Company name and address |  |

We confirm that we are the legal representatives of the Contractors/Tenderers submitting a joint tender in the public procurement procedure "Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP" and hereby authorise

as the leading partner:

Name and address of the leading partner in the joint tender

and for signing the joint tender:

| Signed (name and surname of the responsible person) |  |
| --- | --- |
| Title (position) |  |
| Signature |  |
| Initials |  |

to sign the tender on our behalf, including any amendments, modifications, or withdrawals of the tender. They are furthermore authorised to receive all information pertaining to this public procurement process. In the event that we are awarded the tender under the open procedure "Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP," published on the Public Procurement Portal, they are also authorised to sign the contract on our behalf. This authorisation is subject to the condition that if the business cooperation agreement (contract) specifies that the contract must be signed by all partners in the group, such agreement shall prevail.

We affirm that if we are selected as the successful Tenderers in the public procurement process, we will, before signing the contract, provide the Client with a contract or an agreement on business cooperation for the execution of the public procurement project titled "Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP," as outlined in Item 1.7. of the Public procurement documents.

Mandatory annexes for each tenderer in the group:

- Co-tenderer information - Form 2.1

- ESPD form

Date, place:	The business entity authorising the leading partner shall certify the above by signing the ESPD form.

INSTRUCTIONS:

- FORM 2 must be completed by tenderers who have submitted a joint tender. All co-tenderers involved in the joint tender are required to fill out this form.

- If a Tenderer is submitting a joint tender for the public procurement, they must include FORM 2.1 for each co-tenderer along with FORM 2.1.

- If a Tenderer is participating in the public procurement with subcontractors, they should also include FORM 3, FORM 3.1, and FORM 3.2.

- For a Tenderer participating in the public procurement by utilising the capacities of other entities, FORM 2.1 must be completed for each entity whose capacities are referred to.

DETAILS OF THE CO-TENDERER/ENTITY WHOSE CAPACITIES ARE BEING REFERENCED BY THE TENDERER

FORM 2.1

| BUSINESS ENTITY’S FULL NAME AND BUSINESS NAME: |  |
| --- | --- |
| BUSINESS ENTITY’S ADDRESS: |  |
| CONTACT PERSON: |  |
| CONTACT PERSON'S E-MAIL ADDRESS: |  |
| CONTACT PERSON'S PHONE NUMBER: |  |
| VAT IDENTIFICATION NUMBER: |  |
| REGISTRATION NUMBER: |  |
| BANK ACCOUNT NUMBER AND BANK: |  |
| BUSINESS ENTITY’S LEGAL REPRESENTATIVES: |  |
| TYPE OF WORK TO BE CARRIED OUT BY THE BUSINESS ENTITY: |  |
| AMOUNT OF WORK CARRIED OUT BY THE BUSINESS ENTITY: |  |
| VALUE OF THE WORKS CARRIED OUT BY THE BUSINESS ENTITY (in EUR excluding VAT): |  |

Date, place:	The business entity, acting as the co-tenderer or the entity whose capacities are being referenced by the Tenderer, is required to validate the information above by signing the ESPD form.

INSTRUCTIONS:

FORM 2.1 must be filled out by each partner participating in the joint tender and by each entity whose capacities are being referenced by the Tenderer.

FORM 3

DECLARATION ON SUBCONTRACTOR ENGAGEMENT

Client:

DRAVSKE ELEKTRARNE MARIBOR d.o.o.

Obrežna ulica 170

2000 Maribor

Tenderer:

________________________________________________________________________

In the performance of the public procurement “Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP”, published on the Public Procurement Portal under the publication number ..........................., dated ..........................., we will cooperate with the following subcontractors:

|  |  | Subcontractor’s direct payment request YES/NO |
| --- | --- | --- |
| Name of subcontractor No 1 |  |  |
| Name of subcontractor No 2 |  |  |
| Name of subcontractor No 3 |  |  |
| Name of subcontractor No 4 |  |  |
| Name of subcontractor No 5 |  |  |
| Name of subcontractor No ... |  |  |

We declare that we will:

- Assume full responsibility for the quality of the services provided by all subcontractors involved in the execution of the public procurement contract outlined in this form.

- Grant authorisation to the Client for direct payment to subcontractors based on a confirmed invoice, in the event of a direct payment request.

Date, place:	The Tenderer shall confirm the above by submitting an ESPD form.

FORM 3.1

SUBCONTRACTOR DATA

| NAME OF THE SUBCONTRACTOR: |  |
| --- | --- |
| ADDRESS OF THE SUBCONTRACTOR: |  |
| CONTACT PERSON: |  |
| CONTACT PERSON'S E-MAIL ADDRESS: |  |
| CONTACT PERSON'S PHONE NUMBER: |  |
| VAT IDENTIFICATION NUMBER: |  |
| REGISTRATION NUMBER: |  |
| BANK ACCOUNT NUMBER AND BANK: |  |
| SUBCONTRACTOR’S LEGAL REPRESENTATIVE: |  |
| PERSON AUTHORISED FOR SIGNING THE CONTRACT WITH THE TENDERER: |  |
| THE SUBJECT AND SCOPE OF WORKS TO BE CARRIED OUT BY THE SUBCONTRACTOR FOR THIS PUBLIC PROCUREMENT: |  |
| QUANTITY OF THE SUBCONTRACTOR'S WORKS: |  |
| VALUE OF THE WORKS CARRIED OUT BY THE SUBCONTRACTOR (in EUR excluding VAT): |  |

Date, place:	The Tenderer shall confirm the above by submitting an ESPD form.

_________________________

Note: This form must be filled out individually for each subcontractor.

Mandatory attachments:

- ESPD form for each subcontractor

- Subcontractor's direct payment request if the subcontractor requests direct payment

FORM 3.2

SUBCONTRACTOR'S DIRECT PAYMENT REQUEST AND SUBCONTRACTOR'S CONSENT FOR SETTLEMENT OF THEIR CLAIMS AGAINST THE MAIN CONTRACTOR

Client:

DRAVSKE ELEKTRARNE MARIBOR d.o.o.

Obrežna ulica 170

2000 Maribor

Subcontractor: _______________________________________________________________

________________________________________________________________

(Name and address of the Subcontractor)

As a Subcontractor in the public procurement "Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP", published on the Public Procurement Portal under the publication number ............................., dated ............................., we hereby request, in accordance with the Public Procurement Act (ZJN-3), direct payment. Additionally, we consent to the payer/Client - Dravske elektrarne Maribor d.o.o. - settling our (the Subcontractor's) claims against the main Contractor instead of the main Contractor.

Date, place:	The Subcontractor shall confirm the above by signing the ESPD form.

Note: If there are several subcontractors requesting direct payment, each Subcontractor must fill out their own form.

FORM 4

A DECLARATION OF COMPLIANCE WITH THE REQUIREMENTS OF THE INTEGRITY AND ANTI-CORRUPTION LEGISLATION

Business entity:

_______________________________________________________________

________________________________________________________________

(name and address of the business entity)

As a Tenderer or co-tenderer in a joint tender we are not included in the list of business entities with which contracting entities are prohibited from cooperating pursuant to Article 35 of the Integrity and Prevention of Corruption Act - ZIntPK (Official Gazette of the RS, No 69/11).

By signing this declaration, we commit that if selected as the most advantageous Tenderer or during the execution of the public procurement, we will, as per Article 14(6) of the ZIntPK, furnish the Client with information within eight (8) days of receiving the Client's request. This information will include details about:

- Our founders, partners, including silent partners, shareholders, limited partners or other owners, and information about their respective ownership interest.

- Business entities deemed related to us under the provisions of the Companies Act.

In case of engaging subcontractors, where the subcontractor is to be paid directly by the Client for an amount exceeding €10,000.00 excluding VAT, we will also provide all the above information for the subcontractors.

By signing this declaration, we confirm the contents of the sample declaration of natural and legal persons’ participation in the Tenderer/Subcontractor’s ownership structure set out in Form 4.1, which we will sign and submit to the Client, if we are selected as the most advantageous Tenderer.

Date, place:	The Tenderer shall confirm the above by submitting or signing the ESPD form.

_________________________

FORM 4.1

MODEL DECLARATION OF NATURAL AND LEGAL PERSONS’ PARTICIPATION IN THE TENDERER/SUBCONTRACTOR’S OWNERSHIP STRUCTURE

The undersigned legal representative of the Tenderer/Subcontractor (Tenderer's name, registration number, address):   ______________________________________________________________________________________________________________________________________________

In accordance with Article 14(6) of the Integrity and Prevention of Corruption Act (Official Gazette of the Republic of Slovenia, No. 45/2010, as amended, hereinafter referred to as the "ZintPK") of the Republic of Slovenia, I hereby submit the following,

# DECLARATION OF NATURAL AND LEGAL PERSONS’ PARTICIPATION IN THE TENDERER/SUBCONTRACTOR’S OWNERSHIP STRUCTURE

# Direct and indirect participation in the tenderer/subcontractor’s ownership structure:

- Participation of natural persons

| # Name and surname | # Address | # Ownership share |
| --- | --- | --- |

- Participation of legal persons

| # Business name | # Registered office | # Registration no. | # Ownership share | # Shareholders/business interest holders |
| --- | --- | --- | --- | --- |

- Participation of silent partners in the Tenderer and owners of the Tenderer/Subcontractor

| # Business name/name and surname | # Registered office/residential address | # Registration no. | # Ownership share |
| --- | --- | --- | --- |

- Participation of business entities associated with the tenderer or the owners of the tenderer/subcontractor - associated companies of the Tenderer and the Tenderer's owners

| # Business name | # Registered office | # Registration no. | # Ownership share |
| --- | --- | --- | --- |

# The Tenderer/subcontractor hereby agrees that the Client may, upon request, submit this declaration or the information contained in this declaration to the Commission for the Prevention of Corruption in accordance with Article 14(6) of the ZintPK. The Client is obliged to protect the Declaration in accordance with the Personal Data Protection Act.

The Tenderer/Subcontractor assures the ongoing relevance, correctness, and accuracy of the information provided in this declaration. If the Tenderer submits a false declaration or furnishes inaccurate information regarding the facts stated, the contract/framework agreement will be considered null and void.

# The Tenderer/Subcontractor expressly warrants that all natural persons directly or indirectly involved in the ownership structure of the tenderer have been specified in this declaration.

Name and surname: ………………………………

Position: ............................................

# Signature: …………………………………….

# On .................

FORM 5

Dravske elektrarne Maribor d.o.o., Obrežna ulica 170, 2000 Maribor, represented by Damjan Seme, M. Sc., Managing Director, VAT ID: SI96254459, registration number: 5044286000, hereinafter referred to as the “Client”

and

______________ (company name), _____________ (company address), represented by _______________, VAT ID: ______________, registration number: ______________, hereinafter referred to as the “Contractor”

hereby conclude the following

CONTRACT FOR THE PERFORMANCE OF THE PUBLIC PROCUREMENT

Replacement of the gantry crane and trash-rack cleaning machine at the Zlatoličje HPP

Client’s Contract No: ..................... Contractor's Contract No: …………………….

- Introductory provisions

The Parties acknowledge that the Client has conducted a public procurement procedure in accordance with Article 40 of the Public Procurement Act (Official Gazette of the Republic of Slovenia, No. 91/2015), hereinafter referred to as ZJN-3, for the Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP.

The Contractor was selected as the most advantageous Tenderer following an open procedure published on the Public Procurement Portal on ...................... under the publication No ...........................

The public procurement documents (hereinafter referred to as the "documents") and the tender submitted by the Contractor No ........................., dated ......................., constitute an integral part of this contract. The Contractor shall fulfil all obligations and adhere to all other requirements not explicitly mentioned in this contract but indicated or implied by the documents and the tender.

In case of any conflict between this contract, the documents, and the tender, the provisions of this contract shall take precedence, followed by the provisions of the documents, and then by the provisions of the tender, unless expressly stated otherwise in this contract.

- Subject and scope of the contract

The subject of the contract is the Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP, in accordance with the public procurement documents and the Contractor's tender which are integral parts of this contract.

The contractual scope of work encompasses the following:

- Preparation of design and technical documents.

- Dismantling of the existing gantry crane with a trash-rack cleaning machine, with a capacity of 2x100 kN.

- Manufacturing and supply of a new gantry crane with a trash-rack cleaning machine, with a capacity of 2x150 kN.

- Manufacturing and supply of new lifting tongs.

- Manufacturing and supply of a ramp elevation, also functioning as a safety fence.

- Execution of civil works.

- Unforeseen works.

The precise scope of the works, encompassing all technical data, requirements and conditions, is set out in the public procurement documents, the Contractor's tender and Bill of Quantities, all of which constitute integral components of the contract.

The Contractor is obliged to fulfil all obligations stipulated by this contract in alignment with the provisions of this contract and the specific requirements set out in the public procurement documents.

3.   Contract price

The total contract price for the scope of work referred to in Article 2 of this contract is estimated at:

Estimated contract price excluding VAT:	€______________

(in words: .....................................Euros and ..... /100)

Details of the contract price with unit prices will be set out in the Contractor's Bill of Quantities or tender annexed to this contract.

The contract price encompasses all expenses for the thorough and compliant execution of the contract works at the designated site (DDP) (Incoterms 2010).

The contract price for the scope of the contract specified in Item 2 of this contract shall remain fixed for the entire duration of the service performance and shall cover all costs associated with the execution of the contractual services.

The Client retains the authority to reduce the contractual scope of work during the execution of the works. In the event of such a reduction, the Contractor waives any entitlement to claim costs associated with the reduced scope of work, as explicitly agreed upon by the Contractor.

The Client retains the right to modify or supplement the technical documentation upon which this contract is based.

Throughout the implementation of the contract, unforeseen circumstances may necessitate additional services or supplies that were not fully anticipated or included in the Bill of Quantities.

Unforeseen works (services and supplies) refer to those tasks that, despite being unforeseeable and not initially included in the contract scope, are essential for fulfilling the contract. These works do not fundamentally change the nature of the public procurement and are typically requested retroactively after the contract's conclusion.

Unforeseen works, explicitly approved in writing in advance by the Client and deemed necessary for fulfilling the contractual obligations, will be invoiced based on the actual volume of such works. The Contractor is required to furnish the Client with a cost estimate for the execution of any unforeseen works.

As per Item 2 of the contract, the contract price already encompasses unforeseen works, estimated at 2% of the contract price excluding VAT. If the necessity for unforeseen works is not substantiated or is less than 2%, the final contract price excluding VAT will be decreased accordingly.

If the unforeseen works surpass the aforementioned allocation, the contracting parties will conclude an Annex to this contract during its validity, as outlined in paragraph 1, Article 95 of the ZJN-3.

- Settlement and payment for works carried out

The Contractor is responsible for invoicing the completed works through provisional monthly statements and a final statement, reflecting the actual quantities of works executed. This invoicing process shall adhere to the tender specifications and the Contractor's construction log book, which must be maintained and kept current.

The Contractor is only permitted to invoice for work that has been completed and pre-approved by the Client's supervisor. The Client's supervisor will verify and validate the quantities recorded in the book of measurements by the final day of the month for the respective month. If the final day falls on a non-working day, verification will occur on the first subsequent working day.

Once all the works under contract are completed, and a final settlement his prepared, the Contractor will issue a final statement.

This statement should include: the net value of the completed works, detailing quantity, price and value (both cumulative and monthly); VAT as per Article 76a of the ZDDV-1 or 22% VAT; the total amount to be paid.

Statements must be issued in accordance with Article 82 of the Value Added Tax Act. The Contractor is required to include the contract number on the statement: __________________.

The Contractor shall issue statements in two (2) copies and deliver them to the Client no later than by the 5th of the month for the previous month. The accounting period runs from the first to the last day of the month.

The Contractor shall forward the statements to the Client in electronic form in due time, in accordance with the agreed deadline:

- in .pdf format, by email to invoices@dem.si, or

- in .xml and .pdf format, via the bizBox portal,

- in .xml format, via a verified electronic channel directly to the e-bank.

The Client is fully responsible for the operational status of the email address mentioned in the preceding paragraph. Consequently, the statement is considered received on the same day as the receipt of the email containing the .pdf version of the statement.

If the statement, along with all the required and necessary annexes, is not received within the specified time limit, the Client reserves the right to deduct 0.5% of the total value of the delayed payment for each calendar day of delay. The Client will issue a debit note to the Contractor for the penalty amount due to the late delivery of the statement, which may be deducted from the amount payable to the Contractor.

The Client shall have the right to object in writing to the submitted statement within 10 days after receiving the statement. If the Client or the Supervisor identifies errors or misstatements in the provisional statement, it will be rejected, and the Contractor is obligated to issue a new statement. The payment period starts from the receipt of the newly issued statement.

Payment of the final statement is contingent upon the successful completion of the contractual takeover of the works and the receipt of the Defects Liability Security.

The Client is obligated to settle the provisional and final statements by making payment into the Contractor's (or Subcontractor's) bank account within 45 days from the date of receiving the Contractor's duly issued statement along with the pertinent supporting documentation. Alternatively, the Client may fulfil their obligations to the Contractor or Subcontractor through compensation, assignment agreement, or any other mutually agreed-upon method.

The Client reserves the right to deduct a cash discount of 0.04% for each day of early payment before the due date of the agreed payment period, provided that prior notice is given to the Contractor.

If the Client neglects to pay the duly issued statement for the work performed under this contract within the specified time limit outlined in this Article, the Contractor has the right to levy statutory late payment interest from the payment's due date.

Payments to subcontractors shall be made in accordance with Item 7 of this contract.

4.   Contractual deadline

The Contractor will commence work after the contract's conclusion and will finalise it no later than 17 months following the contract's signature.

Upon completion of installation and testing, a trial period of 90 calendar days will commence in accordance with Item 13 of this contract. The final contractual deadline, incorporating the trial operation and contractual takeover of the works, is set at 20 months following the contract's signature.

The precise date for commencing the works will be mutually agreed upon between the Contractor and the Client. The date of commencement of the works will be recorded in the construction logbook.

The parties will collaborate to establish a more detailed time schedule for fulfilling the contractual obligations, which will subsequently be incorporated as an integral component of this contract.

The Contractor is permitted to conduct work on the Client's premises during working hours, from 7 a.m. to 3 p.m.

The Client also retains the right, should changed circumstances arise after the contract's conclusion, to extend or shorten the contract's validity period, as mutually agreed upon between the Client and the Contractor. Such adjustments shall not be deemed material amendments to the contract in accordance with the provisions of Article 95 of the ZJN-3.

In accordance with Article 95(1)(1) of the ZJN-3, the Client retains the right to amend the time schedule and, consequently, adjust the contractual deadline for justified reasons or due to changed or unforeseen circumstances. While the Client endeavours to plan comprehensively at the time of contract conclusion, it acknowledges the inability to anticipate all factors influencing the project's progression. Factors that are objectively unpredictable to the Client at the time of entering into this contract may include, but are not limited to:

- The occurrence of high waters, as outlined in the internal Rules on high water measures and barrier-breaching hazards.

- Urgent maintenance work required to ensure the smooth operation of the power plant.

- Audits or planned inspections and maintenance of the power plant's power units.

- Other objectively justifiable reasons beyond the control of both the Client and the Contractor.

In the event of any changed or unforeseen circumstances, the deadlines of the time schedule, including the final completion deadline, may be postponed, shortened, or extended by the same duration as the unforeseen circumstances, with the agreement of the Client. However, such adjustments shall not affect any changes in the Contractor's obligations under the contract or in the value of the contract.

If there is a modification in the time schedule due to the circumstances outlined in this Article, the completion deadline may be adjusted by concluding an Annex to the contract for the duration equivalent to the period during which the circumstance persisted.

The Contractor will be considered to have fulfilled the contract once all the works are completed, the agreed-upon documentation in the contract is provided, and the contract works have been taken over.

- Liquidated damages

If the Contractor, due to their own fault or for reasons attributable to them, fails to complete the works within the agreed completion dates specified in the contract or neglects to commence the works at the agreed-upon times, they shall be liable to pay liquidated damages to the Client.

For each day of delay, the Contractor shall be liable to pay liquidated damages to the Client for failing to fulfil the contract on time.

The Client reserves the right to claim liquidated damages from the Contractor, amounting to 0.5% of the contract price, excluding VAT, for each day of delay in meeting the contractual term. The cumulative liquidated damages shall not surpass 10% of the contract price, excluding VAT.

The liquidated damages for non-compliance with contractually agreed deadlines will be claimed by the Client at the latest in the final settlement of the works, and the final invoice amount may be reduced by the liquidated damages amount. Liquidated damages are calculated on the basis of the total number of days of delay.

The Client will document liquidated damages arising from the Contractor's delay by issuing an invoice to the Contractor, who must settle the invoice within 15 days of its issuance date.

If this contract is terminated due to delay, the liquidated damages shall be offset against any amount that the Client owes to the Contractor for their work performed up to the date of termination. If the Client owes nothing more to the Contractor, the liquidated damages shall be the Contractor's debt to the Client.

If the Client suffers economic loss exceeding the value of the liquidated damages as a result of the Contractor's delay in carrying out the works, the Client shall be entitled to full compensation. The Contractor will not be obligated to pay liquidated damages if the contract deadline was exceeded due to reasons attributable to the Contractor.

The Client reserves the right to enforce liquidated damages upon payment, even in instances where it has not explicitly cautioned the Contractor or provided written notice of the delay.

- Meeting obligations towards subcontractors

1. The Contractor shall carry out the works under this contract without subcontractors

or

(If the Tenderer intends to subcontract the works from the public procurement contract:)

2. The Contractor has the authority to subcontract the execution of the works outlined in this Contract to the subcontractors specified in the list of subcontractors in Annex 1, along with the particulars of each Subcontractor also documented in Annex 1. If any alterations occur regarding the subcontractors during the execution of the procurement, the Contractor must promptly notify the Client and provide the updated information, no later than five days following the change, along with any requisite annexes. This amendment does not exempt the Contractor from fulfilling their contractual obligations and is executed in compliance with Article 95(1)(1) of the ZJN-3, which does not require the formal conclusion of an annex.

Despite the provisions outlined in the previous paragraph of this Article, the Contractor must ascertain the suitability, qualifications, and references of subcontractors and shall bear responsibility for any actions, omissions, or negligence of any subcontractor, its representatives, or agents, as if they were actions, omissions, or negligence of the Contractor themselves, their representatives, or agents.

The Contractor should act as a representative for their subcontractors in their interactions with the Client and must oversee and supervise their work to ensure the proper execution of this Contract.

The Contractor will bear full responsibility to the Client for the fulfilment of the contractual obligations, regardless of the number of subcontractors involved.

If the Subcontractor requests direct payment in accordance with and in the manner provided for in Article 94(2) and (3) of the ZJN-3, such direct payment to the Subcontractor shall be deemed compulsory and the obligation shall be binding on the Client and the main Contractor.

If a Subcontractor submits a request for direct payment, the Subcontractor's consent - as outlined in Annex 2 - shall be considered an integral component of this Contract. This consent enables the Client to settle the subcontractor's claims with the Contractor directly rather than through the Contractor.  In this instance, by signing this Contract, the Contractor grants authorisation to the Client to directly remunerate subcontractors who have solicited direct payment, utilising certified invoices/statements as the basis for such transactions. The Contractor is required to append to their invoice/statement the invoices/statements of their subcontractors, which have been pre-approved by them. A precondition for payment is the submission of a subcontractor's invoice/statement that has been pre-approved.

Only if all the conditions set out in the preceding paragraph are fulfilled shall the Client be obliged to make a direct payment to the Subcontractor.

Payments to subcontractors shall be made within the same timeframes and in the same manner as payments made to the Contractor.

During the performance of the public procurement contract, the Contractor shall inform the Client of any changes to the information referred to in Article 94(2) of the ZJN-3 and shall send information on any new subcontractors that they intend to subsequently involve in the performance, no later than five days after the change. In the event of the inclusion of new subcontractors, the Contractor is obligated to furnish, along with the notification, the requisite information and documents stipulated for subcontractors in the relevant documents.

The Client will reject any Subcontractor if there are grounds for exclusion as set out in the relevant documents.

The Client retains the right to decline a proposal for the replacement of a Subcontractor or the inclusion of a new Subcontractor if such actions could impede the seamless execution or completion of the works, and if the new Subcontractor fails to meet the conditions established by the Client in the relevant documents. If the Client rejects the new Subcontractor, they shall inform the Contractor within 10 days of receiving the proposal.

If making direct payments to the Subcontractor is not obligatory, the Client will request that the main contractor provides them, no later than 60 days after settling the final invoice or statement, with a written declaration. Additionally, the Subcontractor should also provide a written declaration confirming that they have received payment for the work, services, or goods directly related to the subject of the public procurement.

Failure to submit a declaration within the specified time frame constitutes grounds for initiating minor offence proceedings against the Contractor before the National Review Commission. The Contractor may face sanctions beyond just fines, including exclusion from procurement procedures for a specified period.

- The responsibilities of the Contracting Parties

The Contractor’s main obligations are:

- To execute all contracted works with craftsmanship, adhering to the required quality standards, within the agreed-upon time-frame stipulated in this Contract, and in compliance with the specifications outlined in the technical section of the tender documents: the Technical Specifications with Annexes.

- To carry out contractual works cost-effectively for the benefit of the Client.

- To organise the site in accordance with the safety plan.

- To do everything within the scope of the obligations assumed to meet the completion dates agreed under this Contract.

- To rectify, at their own expense, any defects and address any deficiencies arising from the Contractor's fault, whether due to substandard workmanship or the use of faulty materials.

- To maintain open communication with the Client regarding any ongoing issues or circumstances that may impact the fulfilment of the undertaken obligations.

- To keep a logbook and other site documentation readily available on-site.

- To conduct the works in adherence to safety measures stipulated for the construction site, including regulations on occupational safety, fire protection, measures for property and site security, as well as access within the construction site area and adjacent buildings, and to adhere to the instructions of experts appointed by the Client.

- The Contractor is accountable for executing the work and safeguarding the environment in alignment with the pertinent legislation of the Republic of Slovenia and the specifications outlined by the Client. If environmental damage arises due to the Contractor's activities, the Contractor must adhere to professional standards and rectify the damage at their own expense.

- To fulfil all obligations towards subcontractors engaged for this project, as outlined in this contract.

- To adhere to all requirements specified in Annex III, Technical Specifications when carrying out the works.

- To comply with the requirements and instructions of the Client in accordance with the contract documents.

- To ensure that their staff receive professional training to proficiently manage, coordinate, and fulfil the undertaken obligations.

- To appoint a representative and give them the powers necessary to represent them under this contract.

- To regularly attend meetings convened by the Client, the Client's representative, and the supervisory authorities.

- To obtain the Client's approval for any new Subcontractor and/or Sub-supplier, aside from those specified in the tender and endorsed by the contract.

- To provide periodic updates on the progress of the work.

- To replace or remove specific personnel from the project upon a valid reason and at the written request of the Client.

- To guarantee that only adequately qualified personnel perform tasks under this contract.

- To conduct the work within the Client's working hours, from 7 a.m. to 3 p.m., with the possibility of extension by mutual agreement until 10 p.m.

- To appoint a site manager and a responsible individual, who may be one person, to oversee the implementation of collective health and safety measures among all contractors on the premises.

- To clean and organise the work area upon the completion of the work and dispose of any waste in compliance with the law.

- To ensure the presence of an installation manager on-site.

- To safeguard the Client's other assets such as equipment, installations, and surfaces from damage, dust, etc., throughout the execution of the works. Failure to do so will result in the Contractor being responsible for repairing any damage caused. If the Contractor neglects to rectify the damage, the Client will undertake the repairs at the Contractor's expense.

- To pay for all costs and damages caused by them to the Client or to third parties during the performance of the work.

- To assume full responsibility for any damage to the Client’s existing equipment or property, as well as damage to new equipment or spare parts during the execution of the works, unless such damage is caused by the Client's actions.

The Contractor remains liable for any destruction until the final taking-over of all works and/or equipment by the Client.

- To comply with the Client's instructions, regulations, and safety precautions.

If the Contractor or their Subcontractor neglects to clean up the work area and remove waste material after the completion of the contracted works, notwithstanding the Client’s request, the Client reserves the right to undertake these tasks independently or engage another qualified Contractor for this purpose.

The obligations of the Contractor outlined in this Article and the scope of work specified in Article 2 of this contract are not mutually exclusive.

If the Contractor stores materials, equipment, machinery, vehicles, etc., on the work site, the Contractor bears sole responsibility for any destruction, damage, or theft of such items.

The Client's obligations include:

- Cooperating with the Contractor to ensure timely and satisfactory completion of the undertaken work.

- Providing a power source, water, and installation space in accordance with safety plans for the renovations.

- Handing over available technical documentation to the Contractor.

- Supplying the Contractor with a copy of the TS HSE Technical Standards.

- Overseeing the implementation of the approved quality control program.

- Supervising the execution of the works on-site.

- Making timely payments to the Contractor for completed works as per contractual provisions.

- Keeping the Contractor informed of any ongoing issues or situations that may impact the fulfilment of the undertaken obligations.

- Documentation

The Contractor is obligated to provide the Client with technical documentation in accordance with the specifications outlined in Annex III Technical Specifications.

- Representatives of the Contracting Parties

The contractual representatives for works under this contract appointed by the Client shall be:

Contract Administrator: Peter Andrejek, e-mail: peter.andrejek@dem.si, Phone: 02 3005 290

Supervisor: Simon Urbas, e-mail: simon.urbas@dem.si, Phone: 02 3005 296

The Client's representatives are authorised to act on behalf of the Client in all matters concerning the services covered by this contract. They are required to collaborate with the Contractor throughout the contract period and furnish the Contractor with all necessary information that the Client is obligated to provide in accordance with their responsibilities under this Contract.

The contractual representative for works under this contract appointed by the Contractor shall be: ________________________.

E-mail:

Mobile:

The Contractor's representative is empowered to act on behalf of the Contractor in all matters concerning the works under this contract and shall directly collaborate with the Client's representative throughout the contract duration.

Any substitution of the designated representatives must be mutually communicated in writing by the Contracting Parties within eight days of the replacement.

- Duty to inform and coordination meetings

The Parties are obligated to inform and coordinate their mutual obligations and other contract-related matters through their designated representatives.

Both Contracting Parties acknowledge that all notices, requests, and demands must be provided to the other Party in writing, properly addressed, and sent by post or email to the contact details specified in this contract as the relevant contact information. Any notice sent to an alternative address will not hold legal validity.

The Contracting Parties mutually agree to promptly and reliably notify each other of any circumstances that could potentially impact the fulfilment of their obligations, including but not limited to:

- The Contractor's suspension of payments or insolvency.

- Issuance of a prohibition notice to the Contractor, alteration in the Contractor's registered activity if it affects the execution of contractual obligations.

- Any disciplinary, criminal, or penal actions resulting in the exclusion of any Contractor's employees from employment or profession, especially those designated as contact persons under this contract.

Information exchange must adhere to the contractual stipulations; otherwise, it will not hold legal validity.

Failure by the Contractor to inform the Client constitutes a significant breach of contractual obligations, allowing the Client to terminate the contract without notice. Either the Client or the Contractor's representative may request the other party's presence at coordination meetings to discuss preparations for future work. The Client is responsible for documenting these meetings and distributing copies of the minutes to all participants. The minutes must delineate the responsibilities for the planned activities as per the contract.

- Quality control procedures: material inspection, equipment manufacturing oversight, factory testing, purchased equipment quality assurance, and field installation quality control

The Client or an authorised representative has the right to conduct quality control and testing of the equipment to verify adherence to the Contract specifications. The scope of quality control and testing is outlined in the technical section of the tender documents.

The Contractor must notify the Client of the testing dates in the factory and on-site at least five days before each test. In the event of no response from the Client, the Contractor may proceed with quality control and measurements independently. The Contractor is solely responsible for covering the expenses incurred for conducting checks and tests.

- Functional testing and field adjustments of assembled equipment

The extent of functional testing and field adjustments for assembled equipment is detailed in the technical part of the public procurement documents.

- Trial operation

The Contractor is responsible for conducting tests on the gantry crane and the trash-rack cleaning machine as per the technical specifications outlined in the tender documents. The trial operation period for the gantry crane with the trash-rack cleaning machine will be 90 calendar days following the successful completion of equipment functional testing.

If the supplied equipment is non-operational for more than 24 hours, the trial period will be extended by the corresponding number of days. In case of continuous non-operation exceeding 5 days due to breakdown, the 30-day trial period will reset from the equipment's restoration date.

Upon completion of the trial operation with the gantry crane with a trash-rack cleaning machine, with a capacity of 2x150 kN, both items will be handed over to the client, and a Taking-Over Certificate will be issued.

- Contractual taking-over and transfer of risk of damage

Upon completion of the contracted works, the Contractor must notify the Client in writing of the work's conclusion. Contractual taking-over occurs after successful testing, supported by a written Taking-Over Certificate issued by the Client. The Taking-Over Certificate necessitates signatures from the contractual representatives of both Contracting Parties.

On the date specified in the Taking-Over Certificate, the risks of damage to the gantry crane and the trash-rack cleaning machine transfer from the Contractor to the Client. Following successful taking-over, the Contractor must furnish the Client with a Defects Liability Security.

- Warranty

All work must be executed correctly, to a high standard, and in compliance with applicable regulations, professional standards, technical instructions, recommendations, and norms.

The Contractor is accountable for all costs and damages incurred due to poor quality, incorrect, or unprofessional work, as documented by the Client's supervisor.

The Contractor is liable for any defects arising within the warranty period, commencing from the date of contractual taking-over of the works.

The warranty period for supplied equipment, installation works, and other services provided under the contract is two (2) years from the contractual taking-over date, as specified in Item 14 of the contract.

The warranty period for corrosion protection, as per degree of rusting Ri2 (ISO 4628) and degree of flaking 2 ISO 4628 (Part 5), is ten (10) years from the contractual taking-over date, as detailed in Item 14 of this Contract and serial number 1.3 in the Bill of Quantities.

The Client must notify the Contractor in writing of any visible defects or inadequate work within 7 days of discovering the defect or as soon as practicable thereafter. The Contractor must be given the opportunity to verify the validity of the complaint.

During the warranty period, the Contractor is obligated to rectify any defects and address deficiencies resulting from faulty workmanship or defective materials at their own expense. The warranty period restarts for rectified defects.

The Contractor is not liable for defects resulting from improper use or insufficient maintenance by the Client.

If the Contractor fails to remedy the deficiencies within the time frame specified by the Client in a written notice, the Client reserves the right to engage another Contractor to rectify the deficiencies, with costs borne by the Contractor.

- Insurance of the Contractor's equipment and services

Upon contract conclusion, the Contractor must furnish the Client with a copy of an insurance policy or a certified declaration from the insurer. This insurance must remain valid throughout the contractual relationship, demonstrating coverage for liability against material and non-material damage during transport or work execution to any person or Client property. Coverage must extend from the contract's commencement until the completion of all works or the handover of completed works to the Client. The total insured sum must be at least €100,000.00.

The insurer is obligated to compensate the Client for any incurred damage, either directly to the Client or in accordance with the Client's specified method of payment for the damage.

- Performance security

As a guarantee of satisfactory work performance, the Contractor must furnish the Client with a bank or insurance company security within 15 days of contract conclusion. The performance security should amount to 10% of the total contract price, inclusive of VAT. The Client is the beneficiary of the security.

If the performance security is not provided within the specified time frame outlined in this article, the Client retains the right to withhold any payment owed under the undisputed invoice amount.

The security must remain valid for a minimum of 30 days after the contractual taking-over date.

The Contractor will be considered to have fulfilled its duty to provide a performance security by presenting the Client with an irrevocable bank or insurance company security. This security ensures that the issuer commits to disbursing the covered amount to the Client within five (5) days upon the initial request, without raising any objections.

If, during the duration of this contract, the security becomes invalid, is damaged, or is otherwise rendered unusable by the Client, the Contractor must, upon the Client's initial request, replace the invalid, damaged, or unusable security within 15 days of receiving the Client's request. The replacement security must adhere to the terms outlined in this Article. If the Contractor fails to furnish the security to the Client within the specified time frame mentioned above, the Client is not obliged to make payments for the contractually agreed amounts to the Contractor until a new, valid security is provided. The Client shall not be deemed in default for non-payment if such non-payment is a result of the Contractor's failure to furnish the required security.

Should there be modifications to the completion dates, type, quality, or quantity of the goods to be supplied or services to be performed during the contract execution, the value of the performance security must be adjusted accordingly. Furthermore, the period of validity may be extended to align with these changes. If the Contractor is not accountable for extending the contractual time limit, the Client shall reimburse the Contractor for the expenses accrued by the Contractor in extending the security.

The Client has the authority to redeem the security either in its entirety or partially, should the Contractor fail to meet any of their contractual obligations, such as those pertaining to quality, scope, completion dates, and other events specified in the contract.

The performance security shall be returned to the Contractor by the Client no later than 40 days after the contractual taking-over of the works.

- Defects liability security

Within 15 days of the contractual taking-over of the works, the Contractor must provide the Client with a defects liability security issued by a bank or insurance company. Specifically:

- For a duration of two years, the security shall amount to five percent (5%) of the contract price, inclusive of VAT.

- After the initial two-year period and until the end of the ten-year term, the defects liability security amount will reduce to five percent (5%) of the contract price inclusive of VAT, specifically designated for corrosion protection as outlined in Item 1.3 of the Bill of Quantities, as specified in Item 14 of this Contract.

The security shall remain valid for 30 days after the conclusion of the two-year warranty period for the equipment and the completed works, as well as for 30 days after the expiration of the 10-year warranty period for the corrosion protection (as detailed in the Bill of Quantities, serial number 1.3, as referenced in Item 14 of this contract).

The Contractor will be considered to have fulfilled its duty to provide a defects liability security by presenting the Client with an irrevocable financial guarantee from a bank in Slovenia. This guarantee ensures that the issuer commits to disbursing the amount covered by the defects liability security to the Client upon the Client's first request and without any objection within five (5) days of receiving the request.

If, during the warranty period, the security becomes invalid, invoked, damaged, or is otherwise rendered unusable by the Client, the Contractor must, upon the Client's initial request, replace the invalid, damaged, or unusable security within 15 days of receiving the Client's request. The replacement security must adhere to the terms outlined in this Article.

The defects liability security will be returned to the Contractor by the Client no later than 40 days after the expiry of the warranty period.

If the Contractor fails to provide a defects liability security with the specified contents within the agreed time limit, the Client is not obligated to accept the defects liability security at a later date. Instead of a defects liability security, the Client reserves the right, at its discretion, to either invoke the performance security or withhold payment of the final statement at 5% until the expiration of the maximum warranty period stipulated in this contract. Additionally, the Client may pay for the rectification of defects from these means if the Contractor fails to address them within the agreed or specified time limit, unless otherwise mutually agreed upon in writing by both Parties. The Client shall pay the retained funds to the Contractor within 30 days after the expiration of the maximum warranty period stipulated in this contract, deducting any amounts necessary to address defects identified during the warranty period. In this scenario, the Client shall not incur default interest or any other charges on the retained funds until the expiration of the maximum warranty period.

- Occupational health and safety, and fire protection

The Contractor confirms the following:

- Familiarity with regulations governing occupational health and safety, as well as fire protection, and a commitment to strictly adhere to these regulations.

- Possession of the following documentation for every worker carrying out work on the Client's premises:

- A valid employment contract,

- Proof of social security, health, pension and disability insurance,

- Insurance coverage against work-related injuries,

- Proof of training in occupational health and safety, and fire safety,

- Confirmation of the worker's medical fitness for the assigned tasks,

- Work permit for non-EU nationals.

- Assurance that all work equipment is and will be duly inspected in accordance with the requirements of the applicable legislation.

- Commitment that their workers and all subcontractors will use all prescribed personal protective equipment.

The Client’s competent employee shall inform the Contractor and any subcontractors of the Client's safety regulations and specific safety precautions applicable at the site/facility through a written declaration for external contractors. The Contractor and all subcontractors must comply with all safety regulations and measures.

Before the start of the work, the Contractor's safety officer must sign a Written agreement on the organisation of joint health and safety measures at the common worksite. All Subcontractors must also sign the written agreement.

If the Client’s competent employee finds that the Contractor and/or Subcontractors are not complying with safety regulations and measures or that their work practices present a risk, they shall notify the Contractor of this in writing. If the Contractor or Subcontractors do not comply with the warnings and instructions of the Client and continue with unsafe work, the Client's competent employee will prohibit further work and require removal from the site until conditions for safe work are restored.

- Environmental protection:

The Contractor declares that:

- They are aware that DEM has an environmental management system in place according to the international standard ISO 14001:2015 and is aware of the environmental requirements of the standard.

- All their employees will comply with all environmental protection requirements in accordance with applicable legislation and standards in this field.

- They shall assume responsibility for any damages arising from non-compliance with environmental protection requirements and in cases of environmental pollution during the execution of the works.

- Data confidentiality

The Parties undertake to keep confidential, throughout the term of the Contract and without limitation after its termination, all information derived from the contract documents and other data, all information arising from the contractual relationship or any information obtained in any form whatsoever, to the extent that it is identified as a business secret. Additionally, the obligation extends to information not labelled as a business secret but for which the Parties should or could have recognised that unauthorised disclosure might cause damage.

The obligation to safeguard confidentiality shall apply to the contracting parties, their employees, and any other individual who may come into possession of such information during the execution of work under this Contract.

The Contractor shall indemnify the Client for any breach of these provisions, for the unauthorised use of data or information for their own purposes, and for any unauthorised disclosure of data and information to third parties without the explicit written consent of the Client. The disclosure or transmission of information in accordance with the Public Information Access Act shall not constitute a violation under this article.

- Contract cancellation

The Client retains the right to terminate the contract at any time through written notice if the Contractor fails to execute the work in a professional manner and in accordance with the terms of the contract. Upon contract cancellation, the Client shall compensate the Contractor solely for the works actually performed in a professional manner, approved by the Client, and not adversely impacting the quality of subsequent works by another Contractor. In the event the Client terminates the contract due to the Contractor's unprofessional conduct or non-compliance with contractual terms, resulting in the necessity to engage a new Contractor, all associated costs and damages shall be the responsibility of the Contractor.

The Client reserves the right to withhold payment for work already completed and approved if the Contractor neglects to reimburse the Client for incurred expenses and damages resulting from contract termination, subsequent delays in completing the agreed-upon work, and increased costs stemming from the engagement of a new Contractor. Delays resulting from engaging a new Contractor shall be assessed in accordance with the procedures outlined for calculating liquidated damages.

- Anti-corruption clause

Should any unauthorised advantage be offered or provided by any party to this contract, or in connection therewith, on behalf of or for the account of the other contracting party, to the signatory of the contract or to any employee or individual performing work for the Client, with the intention of securing business or obtaining business under more favourable conditions, compromising the exercise of due diligence in fulfilling contractual obligations, or for any other action or omission resulting in harm to the contracting party or granting undue advantage to the signatory of the contract or any employee or individual performing work for the contracting party, the contract shall be deemed null and void.

- Resolutory condition

This contract is subject to a resolutory condition, which will be triggered if any of the following conditions occur:

- The Client becomes aware of a court's final decision indicating that the Contractor or a Subcontractor has violated obligations under labour, environmental, or social legislation.

or

- The Client becomes aware of at least two instances where the Contractor or a Subcontractor has committed violations during the contract's execution regarding:

  - Remuneration for work,

  - Working hours,

  - Rest periods,

  - Engaging in work under civil law contracts despite the presence of elements indicating an employment relationship, or

  - Involvement in illegal employment,

And such violations have resulted in fines imposed by final decisions.

If the Client becomes aware of the infringement, the Client shall inform the Contractor within 10 days.

The Contractor may, within a period set by the Client, not exceeding 15 days, provide evidence that they have taken sufficient measures to establish their reliability despite the existence of the infringement. In the case of a breach by a Subcontractor, the Contractor may, within the same time-frame, provide evidence that the Subcontractor has taken sufficient measures to demonstrate its reliability despite the breach. If the Contractor fails to provide evidence for the Subcontractor, or if they do and the Client deems these measures inadequate, the Contractor may replace the Subcontractor within a time limit determined by the Client, not exceeding 15 days in accordance with Article 94 of the ZJN-3, or may undertake the subcontracted work themselves, provided that such replacement or takeover does not constitute a substantial modification of the Contract. If the Contractor fails to provide evidence for themselves or a Subcontractor, or if they do and the Client deems these measures inadequate, or if the Contractor fails to undertake the work themselves or propose a new Subcontractor, or if the Client rejects a timely proposed new Subcontractor in accordance with Article 94 of the ZJN-3, the resolutory condition shall be invoked, provided that at least six months remain between the Client becoming aware of the breach and the contract's expiration. However, termination of this Contract will not occur if such termination would result in disproportionate expenses for the Client, substantial difficulties in the smooth execution of the works, or excessive delay. This is subject to the Client notifying the Contractor no later than 20 days after becoming aware of the breach that the Contract is not intended to be terminated.

If the resolutory condition is met, the contract shall be terminated for this Contractor as of the date of concluding a new public procurement contract for the relevant public procurement. The Contractor will be informed of the date of concluding the new contract by the Client.

If the Client does not initiate a new procurement procedure within 60 days of becoming aware of the infringement, the contract shall be terminated on the sixtieth day after becoming aware of the infringement.

- Force Majeure

The Contractor shall be absolved of liability for damages arising from a failure or delay in fulfilling their contractual obligations if, following the contract's conclusion, unforeseen circumstances arise which the Contractor could not have prevented, remedied, or avoided (force majeure).

As exceptional circumstances, the Client would regard earthquakes and high-water events that would impede or hinder the Contractor's work for safety reasons. Adverse weather conditions shall not justify non-performance or delay unless they render the Contractor's work completely impossible.

The party experiencing force majeure events shall promptly inform the other party of the occurrence or cessation of such events and specify the obligations whose fulfilment has been or will be impeded. During force majeure events, the affected party must seek alternative solutions to continue activities unaffected by force majeure.

Upon the cessation of force majeure events, the contracting parties shall identify and document any changes to contractual obligations and based on that, execute an appropriate amendment to this contract. If the contracting parties incur damages due to force majeure events, each party shall bear their own damages resulting from such events.

- Laws and regulations

In fulfilling the contractual obligations outlined in this contract, the Contractor shall adhere to the legislation of the Republic of Slovenia in effect at the time of contract implementation, as well as other regulations and standards specified in the technical section of the public procurement documents.

- Dispute resolution

The contracting parties commit to resolving any disputes arising from or relating to this contract amicably. If amicable resolution proves unattainable, the competent court in Maribor shall have jurisdiction to settle the dispute.

- Amendments and modifications to the contract

Amendments and modifications to this contract shall be governed by Article 95 of the ZJN-3.

Any changes to this contract must be made in writing, in the form of an annex to the contract.

The requirement for written communication also extends to all correspondence between the parties under this contract. In cases of urgent oral communication, immediate written confirmation is necessary, regardless of the communicating party.

- Special provisions

All communications regarding the execution of this contract shall be conducted in Slovenian.

Additionally, all documentation produced by the Contractor in accordance with the tender documents must be in Slovenian.

The contract encompasses the documents listed in this section, and these documents must be mutually interpreted.

For interpretation purposes, the precedence of documents shall be determined in the following order:

- Contract

- Public procurement documents, and annexes to the public procurement documents

- Technical Specifications with annexes

- Bill of Quantities

- Contractor's tender

If any ambiguities or inconsistencies arise in the documents, the Client shall furnish necessary explanations or instructions.

The Parties mutually agree that the Contractor is prohibited from transferring, pledging, or otherwise disposing of its claim against the Client under this contract to any other natural or legal person.

If any provision of the Contract is deemed invalid, the remaining provisions shall remain unaffected. The invalid provision shall be substituted with a valid provision that closely aligns with the intended purpose of the invalid provision.

The Contractor is obligated to indemnify the Client against any damages resulting from actions taken by the Contractor in the course of and in connection with fulfilling the contractual obligations.

- Final provisions

The Contract becomes effective upon the signatures of both legal representatives of the contracting parties and upon receipt of the Performance Security. It remains valid until all contractual obligations are fulfilled by both parties. Regarding warranty clauses, the contract remains in force until the expiration of all warranty periods or any extensions thereof.

Any matters not expressly defined in this contract shall be governed by the provisions of the Obligations Code and other applicable laws that pertain to this contract.

Two (2) identical copies of the contract shall be prepared, with one (1) copy provided to each contracting party.

..........., on ............................	…………, on ……………………

Signature 	Signature

for and on behalf of Contractor:	Dravske elektrarne Maribor d.o.o.

…………………………	…………………………                        (first and surname), 	Damjan Seme, M. Sc.

(title)			Managing Director

Annex 1

Apart from the Contractor, the following subcontractors are also engaged in executing the works:

| Each type of work to be performed by | Name, full address, registration number, tax number, bank account no. | Subject, quantity, price, place and date of work execution | Subcontractor’s direct payment: YES/NO |
| --- | --- | --- | --- |

FORM 6

LIST OF REFERENCES

In connection with the public procurement titled "Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP," we hereby declare and warrant that:

- Between 1.1.2016, and the tender submission deadline, we have effectively undertaken and satisfactorily completed a minimum of two (2) projects/contracts for the fabrication and installation of a gantry or bridge (overhead) crane with the classic lifting mechanism with a capacity of 30 tons or more, including its commissioning within the agreed-upon time-frames:

| Seq. no. | Reference Client (name and address) | Description of the reference (type of work) | Date of completion of works | Reference object | Crane load capacity |
| --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |
| 2. |  |  |  |  |  |
| 3. |  |  |  |  |  |
| 4. |  |  |  |  |  |

The business entity that will perform the procurement in the part of the manufacturing and installation of the gantry crane and a trash-rack cleaning machine and commissioning (to be entered by the Tenderer):

______________________________________________________________________________

- We have successfully completed a minimum of two (2) projects/contracts within the stipulated time-frames for the application of corrosion protection on machinery, involving blast cleaning up to Sa 2.5 or Sa 3, covering areas exceeding 100 m2 classified in accordance with SIST EN ISO 12944-2 as category C4 for exposed areas and Im1 for submerged components:

| Seq. no. | Reference Client (name and address) | Description of the reference (type of work) and reference object | Blast cleaning up to (Sa), area (m2) and exposure category (for air and submerged parts) | Date of completion of works |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |

The business entity that will perform the procurement in the part of corrosion protection of the machinery (to be entered by the Tenderer):

______________________________________________________________________________

Date, place:	The Tenderer confirms the above by submitting an ESPD form.

NOTE:

If several references are being notified, the Tenderer shall complete or copy the form accordingly.

FORM 7a

REFERENCE CERTIFICATE

Signed by the issuer of the certificate

(name)		..................................

(address)		…………………………….

As the Client, we confirm that the Contractor

(name)		..................................

(address)		…………………………….

Carried out (definition of work):

…………………………………………………………………………………………………………………..

For the reference object:

…………………………………………………………………………………………………………………..

Crane load capacity in tonnes: ………………………………..

In the period from ...................................... to …………………….

Brief description of the work carried out:

Client’s contact person: (name and surname)  ………………………………

Telephone/mobile: ………………………………

E-mail: ………………………………

Throughout our collaboration, the Contractor has demonstrated being a high-quality, professional, and fair contractor. The Contractor has carried out all the work in accordance with the contractual provisions.

This recommendation is provided upon the request of the Contractor for the public procurement No.:..............................

Place and date:__________________                 Stamp and signature of the certificate issuer:

NOTE:

For each reference, the Tenderer must provide all essential information for the Client to evaluate whether the reference requirements have been met. The form must be duplicated for each reference.

FORM 7b

REFERENCE CERTIFICATE

Signed by the issuer of the certificate

(name)		..................................

(address)		…………………………….

As the Client, we confirm that the Contractor

(name)		..................................

(address)		…………………………….

Carried out (definition of work):

…………………………………………………………………………………………………………………..

For the reference object:

…………………………………………………………………………………………………………………..

Blast cleaning up to (Sa): …………………………………

Area (m2): …………………………………….

Exposure category (for air and submerged parts): …………………………….

In the period from ......................................to ……………………..

Brief description of the work carried out:

………………………………………………………………………………………………………………….

………………………………………………………………………………………………………………….

Client’s contact person: (name and surname)  ………………………………

Telephone/mobile: ………………………………

E-mail: ………………………………

Throughout our collaboration, the Contractor has demonstrated being a high-quality, professional, and fair contractor. The Contractor has carried out all the work in accordance with the contractual provisions.

This recommendation is provided upon the request of the Contractor for the public procurement No.:..............................

Place and date:__________________                 Stamp and signature of the certificate issuer:

NOTE:

For each reference, the Tenderer must provide all the information from which the Client will be able to determine whether the reference requirements have been met.

FORM 8

A DECLARATION OF TECHNICAL AND PROFESSIONAL COMPETENCE

In connection with the public procurement titled “Replacement of the gantry crane and a trash-rack cleaning machine at the Zlatoličje HPP,” we hereby declare and warrant that:

- We have the appropriate personnel to carry out the subject of the public procurement contract, who will be directly involved in the work, including:

- a) At least one individual - the head of works responsible for supervising the activities outlined in this Invitation to tender. This individual possesses a minimum of two (2) confirmed references in work management related to the fabrication or overhaul of gantry or bridge (overhead) cranes with a lifting capacity of 30 tons or more, obtained between 1.1.2016 and the tender submission deadline. Additionally, the individual holds at least a secondary education (level V) in a technical field, specifically mechanical or electrical engineering, and is registered in the relevant register of the Engineering Chamber of Slovenia (IZS).

STAFF REFERENCE LIST:

| Seq. No. | Name and surname, Staff employer (name and address) (tenderer, lead partner, partner, subcontractor) | Field and level of education and identification number of the head of works (IZS) | Reference object, description of the reference (type of work) | Crane load capacity | Client/investor of the reference project | Date of completion of works |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |

- We possess suitable factory premises, machinery, and work equipment to meet the requirements of the contract, specifically:

- We have or have access to the capacities of other business entities to provide adequately enclosed and covered factory premises equipped with suitable machinery and work equipment for manufacturing or refurbishing the mechanical equipment specified in the contract.

- We have or have access to the capacities of other business entities for the necessary work equipment required to conduct corrosion protection of the equipment outlined in the contract. Additionally, we possess suitable industrial scaffolding for this purpose.

- The services and equipment offered, including the coatings proposed for use in the corrosion protection activities under this Invitation to tender, shall comply with all the technical requirements of the Client as outlined in Annex III.I. Technical specifications of the Public procurement documents.

Date, place:	The Tenderer confirms the above by submitting an ESPD form.

NOTE:

If multiple references are being provided, the Tenderer shall complete or duplicate the form accordingly. The Tenderer must attach a copy of the staff training certificate following this form.

FORM 9

STAFF REFERENCE CERTIFICATE

Signed by the issuer of the certificate

(name)		..................................

(address)		…………………………….

As the Client, we confirm that

Name		………………………………..

Surname	……………………………….

carried out the following works for us (brief description of how the works were carried out):

Details of the reference facility showing compliance with the requirements:

Period of performance of the works:

Client’s contact person: (name and surname)………………………..

Telephone/mobile:…………………………

E-mail: …………………………..

This recommendation is issued at the request of the Contractor for the public procurement No:..............................

Place and date:__________________                 Stamp and signature of the certificate issuer:

NOTE:

The form shall be copied for each staff reference.

| FORM 10 |  |
| --- | --- |

- Performance security sample

Header with Guarantor details (insurance company/bank) or SWIFT key

For:       (Beneficiary, i.e. the Client)

Date:       (date of issue)

TYPE OF SECURITY:       (type of security: surety guarantee/bank guarantee)

NUMBER:       (Performance security number)

GUARANTOR:       (name and address of the insurance company/bank in the place of issue)

PRINCIPAL:       (name and address of the Principal of the security, i.e. the Tenderer selected in the public procurement procedure)

BENEFICIARY:       (the Client)

UNDERLYING OBJECTIVE: The obligation of the Principal of the security under contract No.       as of       (number and date of the public procurement contract), whose subject is       (subject of the public procurement contract).

AMOUNT IN EUR:       (The maximum amount written in number and word)

IN ADDITION TO THE DECLARATION, THE FOLLOWING DOCUMENTS MUST BE ATTACHED TO THE REQUEST FOR PAYMENT AND ARE EXPRESSLY REQUIRED IN THE FOLLOWING TEXT: none

LANGUAGE IN THE REQUIRED DOCUMENTS: Slovenian

FORM OF SUBMISSION: On paper by registered post or any form of express mail or in person or electronically by SWIFT system to the following address       (the Guarantor’s SWIFT address)

PLACE OF SUBMISSION:       (the Guarantor shall enter the address of the branch where the submission of paper documents is to be made, or an email address for electronic submission, such as the Guarantor's SWIFT address)

Regardless of the address of the branch entered by the Guarantor, the submission of paper documents may be made at any branch of the Guarantor in the territory of the Republic of Slovenia.

DATE OF VALIDITY: DD. MM. YYYY (maturity date of the security)

THE PARTY LIABLE FOR THE COSTS:       (name and address of the Principal of the security, i.e. the Tenderer selected in the public procurement procedure)

As the Guarantor, we hereby commit to paying the Beneficiary an amount equivalent to the security provided, upon the submission of a suitable request for payment. This request must adhere to the specified form of submission outlined above, signed by the authorised signatories, and accompanied by any additional documents as required. Furthermore, the request must include a statement from the Beneficiary, either within the body of the request or in a separate signed document, detailing any failure by the Principal of the security to fulfil its obligations under the underlying objective.

Any request for payment under this security must be submitted on or before the effective date specified above at the place of submission specified above.

Disputes concerning this security will be resolved by a competent court in Maribor, in accordance with Slovenian law.

This security is subject to the Uniform Rules for Demand Guarantees (URDG), revised in 2010, issued by MTZ under No 758.

Guarantor									(stamp and signature)

| FORM 11 |  |
| --- | --- |

Defects liability security sample

Header with Guarantor details (insurance company/bank) or SWIFT key

For:       (beneficiary, i.e. the Client)

Date:       (date of issue)

TYPE:       (type of security: surety guarantee/bank guarantee)

NUMBER:       (performance security number)

GUARANTOR:       (name and address of the insurance company/bank in the place of issue)

PRINCIPAL:       (name and address of the principal of the security, i.e. the Tenderer selected in the public procurement procedure)

BENEFICIARY:       (the Client)

UNDERLYING OBJECTIVE: The obligation of the Principal of the Defects liability security arising from Contract No       dated       (public procurement contract), whose subject is       (subject of the public procurement contract).

AMOUNT IN EUR:       (enter the amount in figures and words equal to 5% of the total final contract price) and valid for a period of two years until ___________

AMOUNT IN EUR:       (insert reduced amount with number and word in accordance with the provisions of the Contract, Item 18) and valid until ____________.

IN ADDITION TO THE DECLARATION, THE FOLLOWING DOCUMENTS MUST BE ATTACHED TO THE REQUEST FOR PAYMENT AND ARE EXPRESSLY REQUIRED IN THE FOLLOWING TEXT: none

LANGUAGE IN THE REQUIRED DOCUMENTS: Slovenian

FORM OF SUBMISSION: On paper by registered post or any form of express mail or in person or electronically by SWIFT system to the following address       (the Guarantor’s SWIFT address)

PLACE OF SUBMISSION:       (the Guarantor shall enter the address of the branch where the submission of paper documents is to be made, or an email address for electronic submission, such as the Guarantor's SWIFT address)

Regardless of the address of the branch entered by the Guarantor, the submission of paper documents may be made at any branch of the Guarantor in the territory of the Republic of Slovenia.

DATE OF VALIDITY: DD. MM. YYYY (maturity date of the security)

THE PARTY LIABLE FOR THE COSTS:       (name and address of the Principal of the security, i.e. the Tenderer selected in the public procurement procedure)

We, as the Guarantor, hereby irrevocably undertake to pay to the Beneficiary any amount up to the amount of the security when the Beneficiary submits a suitable request for payment in the form of submission specified above, signed by the authorised signatory(ies), together with other documents as may be listed above, and in any event accompanied by a statement made by the Beneficiary, either included in the body of the request for payment itself or on a separate signed document accompanying or referring to the request for payment, indicating in what respect the principal of the security has failed to fulfil its contractual obligations under underlying objective.

Any request for payment under this security must be submitted on or before the effective date specified above at the place of submission specified above.

Any disputes relating to this security shall be settled by a competent court having jurisdiction in Maribor according to Slovenian law.

This security is subject to the Uniform Rules for Demand Guarantees (URDG), revised in 2010, issued by MTZ under No 758.

Guarantor									(stamp and signature)

FORM 12

Schedule of technical data

By submitting the ESPD form, the Tenderer confirms the schedule of technical data and that they will supply equipment with the technical characteristics indicated in the column "Data offered".

In the schedule of technical data, the Tenderer must enter the required data in all grey shaded cells in the column - Data offered. If the Tenderer does not fill in all the grey shaded cells in the column 'Data offered', the tender will be declared inadmissible and will be excluded from the procurement procedure, as well as if the values or data entered in the column 'Data offered' are not within the scope of the Client's requirements as set out in the column 'Required'.

GUARANTEED TECHNICAL DATA

| No. | Description | Unit | Required | Data offered |
| --- | --- | --- | --- | --- |
| 1 | Gantry crane with a trash-rack cleaning machine |  |  |  |
|  | - Maximum wheel pressure per running wheel | kN | Max. 180 |  |
|  | - Distance between rails | mm | 5000 |  |
|  | - Classification of structure |  | ≥ HC2,S4 (EN 13001) |  |
|  | - Classification of main lifting operations equipment |  | ≥ M6 (FEM ) |  |
|  | - Classification of longitudinal and lateral movement equipment |  | ≥ M6 (FEM ) |  |
| 2 | The gantry of the crane |  |  |  |
|  | - Travel speed | m/min | 0 - 20 |  |
|  | - Span between rails | mm | 5000 |  |
| 3 | Trash-rack cleaning machine |  |  |  |
|  | - Travel speed | m/min | 0 - 10 |  |
|  | - Load capacity | kg | Min. 6000 |  |
|  | - Lifting speed | m/min | Minimum 20 |  |
|  | - Speed of lowering the grab rake | m/min | Minimum 30 |  |
|  | - Grab rake volume | m3 | Min. 1.00 |  |
|  | - Classification of trash-rack cleaning machine equipment |  | ≥ M7 (FEM) |  |
|  | - Rake material |  | Min. Hardox 400 |  |
| 4 | Lifting tongs |  |  |  |
|  | - Lifting capacity | kg | Min. 30000 |  |
| 5 | Corrosion protection |  |  |  |
|  | - Coatings manufacturer |  |  |  |
| 6 | ELECTRICAL EQUIPMENT |  |  |  |
|  | - Electric motors type and manufacturer: |  |  |  |
|  | - Frequency converter type and manufacturer: |  | ABB or equivalent |  |
|  | - PLC controller type and manufacturer: |  | Siemens or equivalent |  |

ADDITIONAL TECHNICAL DATA

| No. | Description | Unit | Data offered |
| --- | --- | --- | --- |
| 1 | The gantry of the crane |  |  |
|  | Gantry structure |  |  |
|  | - Material of steel structure |  |  |
|  | - Material of crane roof |  |  |
|  | - the largest piece for delivery | mm |  |
|  | - Type and manufacturer of dampers |  |  |
|  | - Type and manufacturer of winding drum |  |  |
|  | - Type and manufacturer of power cable |  |  |
|  | - Type and manufacturer of led flood lights |  |  |
|  | Gantry travel drive |  |  |
|  | - Number of drives | piece |  |
|  | - Number of running wheels | piece |  |
|  | - Number of driven running wheels | piece |  |
|  | - Material of running wheels |  |  |
|  | - Type and manufacturer of gearbox |  |  |
|  | - Type and manufacturer of brakes |  |  |
| 2 | Lifting trolley |  |  |
|  | Lifting trolley structure |  |  |
|  | - Material of steel structure |  |  |
|  | - Dimensions of lifting trolley | mm |  |
|  | - Type and manufacturer of dampers |  |  |
|  | Lifting trolley travel drive |  |  |
|  | - Number of drives | piece |  |
|  | - Number of driven running wheels | piece |  |
|  | - Number of running wheels | piece |  |
|  | - Material of running wheels |  |  |
|  | - Type and manufacturer of gearbox |  |  |
|  | - Type and manufacturer of brakes |  |  |
|  | Lifting 2x150 kN |  |  |
|  | - Type and manufacturer of wire rope |  |  |
|  | - Diameter of wire rope | mm |  |
|  | - Wire rope safety coefficient |  |  |
|  | - Type and manufacturer of brakes |  |  |
|  | - Type and manufacturer of brake actuator |  |  |
|  | - Diameter of winding drum | mm |  |
|  | - Material of winding drum |  |  |
|  | - Type and manufacturer of gearbox |  |  |
|  | - Type and manufacturer of overload protection |  |  |
| 3 | Trash-rack cleaning machine |  |  |
|  | Trash-rack cleaning machine structure |  |  |
|  | - Material of steel structure |  |  |
|  | - Dimensions of closing board | mm |  |
|  | Grab rake travel drive |  |  |
|  | - Number of drives | piece |  |
|  | - Grab rake opening and closing system |  |  |
|  | - Number of guiding wheels | piece |  |
|  | - Material of wheels |  |  |
|  | - Type and manufacturer of gearbox |  |  |
|  | - Type of altimeter (distance meter) |  |  |
|  | - Type and manufacturer of wire rope |  |  |
|  | - Diameter of wire rope | mm |  |
|  | - Wire rope safety coefficient |  |  |
|  | - Type and manufacturer of brakes |  |  |
|  | - Type and manufacturer of brake actuator |  |  |
|  | - Diameter of winding drum | mm |  |
|  | - Material of winding drum |  |  |
|  | - Type and manufacturer of overload protection |  |  |
|  | - Dimensions of grab rake | mm |  |
| 4 | Lifting tongs |  |  |
|  | - Material of lifting tongs structure |  |  |
|  | - Dimensions of lifting tongs | mm |  |
| 5 | Ramp elevation |  |  |
|  | - Material of structure (stainless steel) |  |  |
| 5 | Corrosion protection |  |  |
|  | Environmental exposure - C5VH |  |  |
|  | - Type and thickness of primer | µm |  |
|  | - Type and thickness of the intermediate coating | µm |  |
|  | - Type and thickness of topcoat | µm |  |
|  | Environmental exposure - Im1 |  |  |
|  | - Type and thickness of primer | µm |  |
|  | - Type and thickness of the intermediate coating | µm |  |
|  | - Type and thickness of topcoat | µm |  |

Date, place:	The Tenderer shall confirm the above by submitting an ESPD form.

FORM 13

QUANTITIES SUMMARY (RECAPITULATION)

Replacement of the gantry crane with a trash-rack cleaning machine at the Zlatoličje HPP

- Name of the business entity:

…………………………………………………………….

- TENDER PRICE (TOTAL TENDER PRICE AS INDICATED IN THE BILL OF QUANTITIES)

| Total tender price (excluding VAT): | ……………. EUR |
| --- | --- |

The prices quoted must include all expenses accrued by the Contractor for the satisfactory completion of the subject outlined in the public procurement contract, including all constituent elements, taxes, and other duties (excluding VAT).

The tender's validity shall extend up to and including 120 days following the tender submission deadline.

Date, place:	The Tenderer is required to confirm the above by submitting an ESPD form.

_________________________

For a public limited company, only those shareholders who hold, directly or indirectly, more than 5% of the shares or who participate with more than 5% in the founding rights, management or capital of the public limited company shall be listed.

See the definition of associated companies in Article 527 of the Companies Act (Official Gazette of RS no. 65/2009-ZGD-1-UPB1, as amended)