Dravske elektrarne Maribor d.o.o.

Kozjak Pumped-Storage Hydropower Plant

TERMS OF REFERENCE

for the provision of services:

- peer review of the revised Conceptual design from 2024

- preparation of tender documentation LOT TGD

- consultancy services during the call for tenders phase

- preparation/review of the proposal for CDE in BIM

Maribor, June 2024

Table of Contents

1	INTRODUCTION	4

2	PROJECT DESCRIPTION	5

3	SUBJECT OF THE TERMS OF REFERENCE	7

3.1	Peer review of the revised Conceptual design (nIDP)	7

a)	Overview of the solutions outlined in the nIDP	7

b)	Safety of personnel, PSP facilities	8

c)	Sustainability of facilities (lifetime)	8

d)	Efficiency of equipment, assemblies, and the facility as a whole, and lifetime of equipment	8

e)	Provision of electricity market services (system services, …)	8

f)	Availability of equipment on the market	8

g)	Timetable for project implementation in organisation of LOT division	8

h)	Review of price break-down	9

3.2	Preparation of tender documentation LOT TGD	10

3.3	Consultancy services during the call for tenders phase	12

3.4	Preparation/review of the proposal for CDE and BIM	12

4	REQUIREMENTS FOR DRAFTING DOCUMENTATION	13

5	CONTRACTOR'S OBLIGATIONS	13

6	CLIENT'S OBLIGATIONS	14

7	PAYMENT CONDITIONS	14

8	TIME SCHEDULE FOR PREPARING THE DOCUMENTATION	14

9	ANNEXES	15

Abbreviations used:

BIM		Building Information Modelling

CDE		Common Data Environment

CFSM		Converter Fed Synchronous Machine

DEM		Dravske elektrarne Maribor – Client

DFIM		Double Fed Induction Machine

DPN   		national spatial plan

ECI		Early Contractor Involvement

ELES		Elektro Slovenija, Electric power organization company

FIDIC		International Federation of Consulting Engineers

GD 		construction permit

HSE 		Holding Slovenske Elektrarne

HSE Invest	subsidiary company – Engineer

IBE		Designer

IDP		Conceptual design

LOT TGD	tender documentation for the turbine, generator and overhead crane in the cavern

nIDP		revised Conceptual design

ToR		Terms of Reference

INTRODUCTION

Dravske elektrarne Maribor, d.o.o. (hereinafter DEM) is a significant member of Holding slovenskih elektrarn, d.o.o. and an important producer of electricity in the Slovenian energy sector, as it is the largest producer of electricity from renewable sources in Slovenia. With its eight major hydroelectric power plants along the Drava River, five small-scale hydroelectric power plants and four solar power plants, DEM generates almost a quarter of all Slovenian electricity. The company is development-oriented and pursues long-term objectives of ensuring safe, high-quality, stable and reliable electricity production while aiming to increase electricity production from renewable sources, which also implies the need to place and build new energy facilities.

DEM d.o.o. is in the planning stages for the construction of the Kozjak PSP along with its associated arrangements, for which the Decree on the detailed plan of national importance for the pumping hydroelectric power station on the Drava River and its connection to the distribution and transformer station in Maribor (Official Gazette of the RS, No. 12/11) has been adopted (hereinafter referred to as: DPN). The construction of the Kozjak PSP is being planned in accordance with the concession agreement for the use of the Drava River for the production of electricity. This approach ensures that the total gross potential of the watercourse remains unaltered.

The adopted DPN and the corresponding project documentation define the spatial arrangements – the buildings and the accompanying arrangements, which will be further elaborated through more detailed design phases. The construction of the Kozjak HPP in accordance with the DPN is contingent upon obtaining a construction permit (GD) and other necessary documents required by law. The obtaining of the GD will be carried out through an integral procedure.

In the preliminary phases of the project and for the preparation and adoption of the DPN Decree, project documentation up to the level of the Conceptual design (IDP), an environmental report, investment documentation, as well as some surveys, studies, and expert backgrounds have already been prepared. In 2011/12, an revised Conceptual design (nIDP) featuring a cavern variant power house was prepared, and a peer review of the nIDP was carried out by Lahmeyer International. In 2022, a study on the selection of the optimal technological equipment was also prepared, containing a presentation of the current technology of PSP equipment worldwide as well as a technology proposal for the Kozjak PSP.

The Client is collaborating with the Engineer on the project, namely the subsidiary company HSE Invest, which is involved in all phases of the development of the Kozjak PSP project.

PROJECT DESCRIPTION

The Kozjak PSP will be located in the site and area shown in Figure 1 below. The primary function of the PSP is to store energy in the reservoir, utilising pump operation mode, and to convert the potential energy of the water back into electricity during turbine mode operation. With the Kozjak PSP, the investor aims to optimise electricity production from its own generation facilities as well as those of the HSE Group. Additionally, the investor plans to offer system services that will be marketed. The intake of water for pumping to the reservoir will be sourced from the Drava River, and the water will likewise be returned to the Drava River during the production regime.

Figure 1: Location for the construction of the Kozjak PSP in accordance with the adopted DPN Decree

Kozjak PSP facilities and a brief description:

- The upper reservoir is planned to be situated at Kolarjev vrh. The estimated useful volume is approximately 3,000,000 m3. The crest of the reservoir embankment will be elevated on the water side, featuring a reinforced concrete wall. The intake structure is planned to be of a cylindrical column design. A bridge is foreseen as the connection between the crest of the embankment and the intake structure.

- A penstock (shaft) is planned to run vertically between the upper intake-outlet structure and the turbine axis. Before reaching the power house cavern, the penstock will transition from a vertical to a horizontal orientation, splitting into two symmetrical sections.

- The power house cavern is oriented perpendicular to the intake-outlet system in plan and is adjusted in height to accommodate the appropriate turbine submergence, thereby determining the position of the turbine axis.

- The transformer cavern is situated parallel on the downstream side of the power house cavern. The cavern will accommodate the main transformers along with cable distribution.

- The main access tunnel begins with an entrance portal. The tunnel route initially ascends slightly to facilitate drainage of hillside water during construction, before descending towards the vicinity of the transformer cavern. In the section between the two caverns, the route remains horizontal at the level of the installation platform. In addition to access, the tunnel also accommodates provisions for exhaust air, drainage water, sewerage, hydrant network, medium voltage (MV) cables, communication cables, and smoke extraction.

- The cross-section of the service tunnel is horseshoe-shaped with a semicircular calotte. From the entrance portal, the tunnel route initially ascends slightly to facilitate drainage of hillside water during construction, before descending towards the transformer calotte and the power house calotte. During the construction phase, it serves as a research tunnel and provides access to the transformer cavern calotte, the power house cavern, and the surge tank. In the final phase, it serves for routing 400 kV cables, fresh air intake, and evacuation.

- During the construction phase, the auxiliary tunnels serve as access points to the work site of the other facilities. Auxiliary tunnels have the same cross-section as the service tunnel.

- The discharge tunnel extends from the junction of the extensions of the two draft tubes to the lower intake-outlet structure.

- A surge tank is included to offset the water pressure in the supply-discharge tunnel. It is designed as a cylindrical shaft. The upper part of the cylinder, which is subject to level fluctuations, is larger.

- On the lower platform, the outflow channel of the PSP to the Drava, the control facility, the technological facility (including diesel equipment, medium voltage switchgear, transformers, batteries, etc.), and the 400 kV GIS switchyard will be situated. Access to the entrances of the main access tunnel and the service tunnel will be facilitated from the platform.

- Additionally, there will be a 2×400 kV cable line from the transformers to the 400 kV switchyard and from the 400 kV switchyard to the overhead transmission line.

- Access routes to all parts of the facility must be provided for construction, operation, and maintenance purposes.

- Connection to the public utility infrastructure, including roads, water supply, sewerage, electricity, and telecommunications, as well as connection to the 20 kV power grid, must be established.

- Connection to the 10 kV busbar of the Fala HPP for the PSP auxiliary power supply is required.

- Connection to the Client's telecommunications and energy infrastructure is required.

- Exterior arrangements, spatial design, and landscaping are to be considered.

Further details are provided in the nIDP under peer-review.

SUBJECT OF THE TERMS OF REFERENCE

The scope of services under this Terms of Reference (ToR) is as follows:

3.1 peer review of the revised Conceptual design (nIDP)

3.2 preparation of tender documentation LOT TGD

3.3 consultancy services during the call for tenders phase

3.4 preparation/review of the proposal for CDE in BIM

Peer review of the revised Conceptual design (nIDP)

The nIDP was prepared by the Designer IBE d.d. in 2024. The Conceptual design, which served as the basis for the preparation of the DPN, was prepared in 2011.

The Contractor is required to substantiate the proposals and measures for improving the solutions outlined in the nIDP. Additionally, the Contractor must provide calculations for these proposals and measures, ensuring alignment with the requirements of relevant legislation, the Transmission System Operator (TSO), and the electricity services market.

Access roads and the route of the 2x400kV transmission line are mentioned in the nIDP; however, they are not the focus of the peer-review. The boundary of the nIDP extends to a 400kV switchyard with a connection (looping) to the existing transmission line Maribor-Kainachtal.

The detailed requirements for the works are outlined below.

Overview of the solutions outlined in the nIDP

The Contractor will receive the nIDP from the Client in electronic PDF format and, if necessary, in an active format. The nIDP documentation will be in English.

The remaining documentation (DPN, studies, reports) available to the Designer during the preparation of the nIDP will also be provided to the Contractor. The remaining documentation will be made available to the Contractor in Slovenian in electronic form, with the necessary segments translated into English upon agreement. The documentation shall be submitted in PDF format.

The Contractor is tasked with reviewing the quality of the nIDP documentation produced and the extent to which the technical solutions provided in the nIDP have been processed.

The Contractor will examine the solutions put forward in the nDIP and their relevance in the light of legislation, technical regulations, standard, good engineering practice, the state of the market for equipment manufacturers and the state of the market for electricity services. The Contractor will provide suggestions for improvements.

The nIDP project has not identified and selected technical solutions for the generator and is considering both DFIM and CFSM technology.

In the context of the conceptual review, special attention should be paid to the safety of the storage in terms of the technical solution in the Conceptual design, seismic safety, overtopping protection, geology, ice formation, silt accumulation and removal, etc.

The Contractor is to verify all preliminary calculations in the nIDP, transient calculations for all operating regimes based on currently available data, dimensioning of the pipeline and other equipment and thus indicate any additional project requirements.

It is necessary to verify the adequacy of the concept in terms of the adequacy of cooling and heat removal, especially in the case of the selection of a synchronous machine with a full converter.

Safety of personnel, PSP facilities

It is necessary to revise the solutions outlined in the nIDP and provide starting points and guidelines in terms of the safety of personnel who will be inside or on the PSP facilities during construction, operation and maintenance, with special attention to the prevention of hazardous events, as well as to the evacuation and rescue of persons in the event of emergencies.

Technical solutions concerning the safety of PSP facilities are to be reviewed under all operating conditions (regular and irregular) of PSP equipment. Special attention should be paid to ensuring the safety of the upper reservoir in case of natural disasters such as earthquakes, landslides, and fires, as well as natural emergencies like heavy rainfall, strong winds, etc.

Technical solutions concerning the safety of PSP equipment are to be reviewed under all operating conditions (regular and irregular).

Sustainability of facilities (lifetime)

The solutions outlined in the nIDP are to be reviewed and verified in terms of ensuring the longevity of building structures and facilities.

Efficiency of equipment, assemblies, and the facility as a whole, and lifetime of equipment

The Contractor will conduct a review and examine the selected technical solution for efficiency, proposing possible improvements to enhance the cycle's efficiency (pumping/production). Moreover, the choice of technology and equipment is to be examined in terms of ensuring longer equipment lifetime and reduced maintenance costs.

The Contractor will also examine the solutions related to dissipating losses or waste energy (heat) and explore potential beneficial uses of waste energy.

Provision of electricity market services (system services, …)

The Contractor will verify and examine the flexibility of equipment and technical solutions as a whole to provide services in electricity markets.

Availability of equipment on the market

The Contractor will check the availability of equipment for the technical solution provided in the nIDP from equipment manufacturers and assess the experience or references of equipment manufacturers in relation to the Kozjak PSP project data. They will propose solutions and suggest choices that do not compromise flexibility and efficiency, potentially attracting more potential bidders.

Timetable for project implementation in organisation of LOT division

The Contractor will review the intended sequence of works, the reasonableness of the division of LOTs and provide observations and suggestions based on their experience.

Review of price break-down

The Contractor will check the cost sheet of the revised Conceptual design and provide an assessment of the relevance of the key items and any suggestions, comments on this cost sheet.

During the peer-review, the Contractor will collaborate with the Client, the Engineer, and the Designer. Any inquiries from the Contractor will be directed to the Client or the Client's engineer. A comprehensive communication protocol will be outlined in a project manual, provided to the Contractor after the contract is finalised.

The Contractor will submit periodic reports (anticipated monthly) to the Client regarding the progress of the peer review.

All communication will be conducted in English.

After 3 (three) months, the Contractor will prepare an interim peer-review report (draft version of the report) and submit it to the Client for evaluation. This interim report should encompass all proposals and actions intended by the Contractor to enhance the solutions in the nIDP. In the interim report, the Contractor must substantiate all proposals and measures with calculations. The Client will involve the Designer and Engineer in evaluating the interim peer-review report. Any questions or clarifications arising from the evaluation of the interim peer-review report will be compiled by the Engineer and forwarded to the Contractor and/or Designer.

Following the evaluation of the interim peer-review report and any raised questions (approximately 30 days later), a meeting will be convened. During this meeting, the Contractor will present the proposals and solutions outlined in the interim peer-review report. Additionally, questions regarding the interim peer-review report from the Client, Engineer, and Designer will be addressed, along with any agreed-upon points of the peer-review report. Based on the final findings, the Designer will prepare the final version of the Conceptual design, which will then serve as the basis for further work on the project (preparation of DGD, tender documentation, PZI, investment documentation).

The interim peer-review report should be written in English.

Following the coordination meeting, the Contractor will produce the final the peer-review report incorporating the alignments agreed upon during the meeting.

The peer-review report should be written in English.

The peer-review report must cover all areas of expertise relevant to the implementation of the project.

Proposed table of contents for peer-review report

- INTRODUCTION

  - OBJECTIVES AND SCOPE OF THE REVIEWED WORK

  - METHODS AND MANNER OF IMPLEMENTATION

  - INPUT DATA AND SOURCES OF INFORMATION

- REVIEW OF CONSTRUCTION AREA

  - UPPER RESERVOIR WITH INTAKE/OUTLET STRUCTURE AND OTHER FACILITIES

  - PENSTOCK

  - POWER PLANT CAVERN AND ACCESS ROUTES AND EXTERNAL FACILITIES

  - DOVODNO/ODVODNI KANAL IN VTOČNO/IZTOČNI OBJEKT PRI SPODNJEM BAZENU

- REVIEW OF GEOLOGICAL AND GEOTECHNICAL CONDITIONS

  - ASSESSMENT OF GEOLOGICAL CONDITIONS

  - ASSESSMENT OF GEOTECHNICAL CONDITIONS

- INSPECTION OF STEEL STRUCTURES

  - HYDROMECHANICAL EQUIPMENT IN THE UPPER RESERVOIR

  - HYDROMECHANICAL EQUIPMENT IN THE LOWER RESERVOIR AND TUNNEL

  - STEEL LINING OF THE PENSTOCK

- PREGLED STROJNE OPREME INSPECTION OF MECHANICAL EQUIPMENT

  - GENERAL

  - MACHINE PUMP/TURBINE

  - MAIN INLET VALVE

  - AUXILIARY SYSTEMS (HVAC, DRAINAGE SYSTEM, etc.)

- INSPECTION OF ELECTRICAL EQUIPMENT AND CONTROL SYSTEMS

  - GENERAL

  - ENGINE/GENERATOR MACHINE WITH AUXILIARY SYSTEMS

  - SN ELECTRICAL EQUIPMENT OF ENGINE/GENERATOR MACHINE

  - BLOCK TRANSFORMER

  - SWITCHYARD 400 kV (GIS)

  - CONTROL AND PROTECTION SYSTEMS

  - AUXILIARY POWER SYSTEMS OF THE POWER PLANT (SN, NN AC, NN DC, DEA)

  - POWER PLANT AUXILIARY SYSTEMS

  - BUILDING INSTALLATIONS

- INSPECTION OF COMMUNICATION SYSTEMS AND CONTROL SYSTEMS

  - GENERAL

  - COMMUNICATION LINKS BETWEEN PSP BUILDINGS

  - COMMUNICATION SYSTEM CONCEPT

  - COMMUNICATION REDUNDANCY CONCEPT

  - TECHNOLOGY PROCESS NETWORK

  - BUSINESS NETWORK

  - TELEPHONE SYSTEM

  - EXERNAL TELEPHONE CONNECTION

  - MOBILE COMMUNICATIONS

  - VIDEO AND SECURITY SURVEILLANCE

  - SEISMIC MONITORING

- FINDINGS, CONCLUSIONS AND SUGGESTIONS

The table of contents above is merely a proposal. The Contractor is free to design the report following their best practice. However, the table of contents provides information on the need/requirement to address the project and the concept in a comprehensive manner.

Preparation of tender documentation LOT TGD

For the purposes of the Kozjak PSP project, the construction or selection of contractors is expected to consider several LOTs, at least the following LOTs:

- LOT TGD	turbine, generator, overhead crane, MIV, auxiliary systems, etc.

- LOT A	construction LOT, possibility of breaking down into, for example, groundwork on the reservoir and underground works

- LOT H	hydromechanical equipment and penstock

- LOT S	switchyard

- LOT EO	electrical equipment

- LOT T	transformer(s)

- LOT C	roads

- LOT DV	transmission line, investor ELES – system operator

- ……

The subject of this ToR is LOT TGD only. According to the experiences and good practice of the Client, the usual composition of LOT TGD consists of several books, as shown below:

Book 1: 	General part of the tender documentation

Book 2A: 	Price sheets

Book 2B:	Technical data sheets

Book 3: 	General technical requirements and specifications

Book 4:	Special technical requirements

Book 5:	Drawings

With the exception of Books 1 and 5, the other books deal separately with turbine, generator and overhead crane.

A more detailed structure of the tender documentation is shown as a model in the Annex to this ToR and may be modified/upgraded to take into account the ECI process, based on the proposal and coordination with the consultant. The content is shown for the sole purpose of understanding the expected level of the procedure, scope and quality of preparation of the tender documentation.

It should be emphasised here that flexibility of equipment is required. The final solution as to whether this will be ensured by the synchronous machine (CFSM) or the induction machine (DFIM) is precisely the subject of the ECI procedure – see point 3.3.

For LOT TGD, the following delivery limits are expected: complete turbine (with regulator) and generator (with excitation), and in terms of technology CFSM (synchronous machine with full converter, the latter being included in the scope of supply), overhead crane in cavern, MIV, all associated auxiliary systems (turbine drainage, water passage drainage, oil cooling systems, oil vapour extraction, pressure vessels, compressed air...), complete control and protection of the generator set, electrical enclosures for the power supply of the generator set equipment, sensors, instrumentation, valves, actuators, drives and cabling of power, signal, control and communication connections, all including installation and commissioning.

Book 1, which was initially prepared by the Client, also includes a proposal – a draft contract with the equipment supplier. LOT TGD is intended to be designed using the principles of the FIDIC Yellow Book. In the general part of the tender documentation (i.e. Book 1), the consultant must be involved especially in the drafting of the contract, in particular in order to comply with the ECI procedure. The procurement procedure itself will be carried out in accordance with Slovenian public procurement legislation. Changes may be made, in particular as a result of participation in calls for tenders for co-financing (grants) or financial construction by means of bank loans.

Consultancy services during the call for tenders phase

Due to the specificity of the project, the Client’s estimation is that it will be necessary to gain the interest of several suppliers in the tender phase for the supply of the key equipment (turbine/generator) through the so-called Early Contractor Involvement (ECI) procedure. The steps and procedures of the tender will be coordinated with the selected consultant, who will accompany the Client until the final selection and signing of the contract with the selected supplier as considered in TGD LOT. The main purpose of the entire ECI procedure is to obtain the optimal technical solution for the project in cooperation with the suppliers. The final objective is to ensure early involvement of the equipment supplier and the Designer in the procurement process and to obtain three (3) competitive bids for the execution of the works or the supply of key equipment. These services are directly linked to point 3.2. where the tender documentation will prescribe the procedure with an expected 2-stage evaluation of the tenders.

During the first stage, a procedure will be defined whereby the relevant qualifications of the suppliers are expected to be verified and the suppliers will verify their ability to supply the relevant equipment through a more detailed analysis of the input data. For this stage, the Client also plans a partial reimbursement of the costs of qualified suppliers who will participate in the process of verifying the feasibility of supplying and offering a suitable technological solution.

During the second stage, where the aim is to bring in 3 bidders, the most economically advantageous bid will be selected.

During both stages, the consultant will work together with the Client and the Engineer to prepare an adequate supplier selection procedure, specifying the qualification conditions, the evaluation criteria for the technical solutions provided, as well as the criteria for the final selection of the most economically advantageous bid.

The scope of this work is estimated in terms of hours and can be seen in the attached price sheet.

According to this ToR, the Contractor will accompany the Client and help with their consultancy services until the contract with the selected equipment supplier is signed, as considered in TGD LOT.

At the tender stage, the tenderer must already have given a basic idea of how the tender procedure will be carried out using the ECI method. In this document, they should roughly explain what approach they propose, what evaluation criteria they propose for each phase, how they would motivate potential tenderers to participate in the tendering process.

Preparation/review of the proposal for CDE and BIM

The Client will work with the Engineer to prepare a comprehensive proposal for the implementation and use of BIM in the Common Data Environment (CDE) for DEM and the HSE Group to use in the Kozjak PSP project. The document is/will be aimed at decision makers to have as clear a picture/vision as possible of the introduction of modern processes in the CDE in terms of:

- Setting up the CDE (HW in SW requirements, data availability, information security, etc.

- Proposal for the use of dimension of BIM processes (staffing, skill needs, XDimension of BIM use)

- Proposal for the use of BIM level (how to define the requirements for LOD, maturity of the environment to be able to follow the BIM requirements, etc.)

- Impact of decisions on investment management processes, maintenance and operation of built facilities

- Cost assessment

- SWOT analysis to help select or confirm the optimal proposal for the next steps in BIM implementation

The consultant examines the proposal and provides specific suggestions on the submitted document and proposes possible solutions based on their experience.

REQUIREMENTS FOR DRAFTING DOCUMENTATION

The documentation must be written in Slovenian or English. Upon completion, the documentation will be provided to the Client or the Client's engineer in three (3) hard copies and an electronic copy in both PDF and active formats. The electronic documentation should be transferred via USB memory stick or uploaded to a designated server/portal. Both the printed and electronic versions of the documentation must be identical. Upon completion, the documentation will become the property of the Client/Investor. The Client/Investor will hold all rights related to the review, peer review, and the usage or authorisation of the completed document by third parties involved in subsequent phases of the project's documentation. The documentation may only be used for the Kozjak PSP project. Prior to the final handover, the Contractor will electronically submit the completed documentation to the Client for inspection. The Client will engage the Designer and Engineer in the inspection process. The inspection is anticipated to last up to 30 days, with the Client having the option to extend the review period by a maximum of 2 additional weeks if necessary. At this time, a coordination meeting with the nIDP designer will also be organised to take a position on all the comments and observations made by the developer. The final report will be submitted by the Contractor within 1 month, in accordance with the timetable envisaged in point 8 of this ToR.

The following requirements must be adhered to when drafting the documentation: Use of software tools compatible with MS Word (for text), MS Excel (for tables and charts), MS Access (for databases), AutoCAD (for all graphical annexes), MS Project (for schedules, timetables), and Adobe Acrobat Reader (for PDF documents) is mandatory for all processing stages. The documentation should be structured in a way that enables the transfer of results to a GIS environment.

CONTRACTOR'S OBLIGATIONS

As stipulated in the signed contract, the Contractor commits to:

- execute the work to a high standard, adhering to professional norms, the Terms of Reference and agreed-upon timetable;

- consider relevant legislation, regulations, standards, good engineering practices, and technological advancements pertinent to the scope of the Terms of Reference;

- at their own expense and within a timeframe agreed upon with the Client, Engineer, and Designer, incorporate additions and modifications to the scope of services if deficiencies are identified in the services rendered;

- provide the Client with the agreed volume of documentation, both in paper and electronic formats;

- submit documents to the Client for review and approval before final issuance;

- maintain up-to-date progress of the work, inform the Client of interim results, and collaborate with the Client, Engineer, and Designer;

- promptly notify the Client in writing of any complications encountered during the work process;

- obtain the remaining necessary information that is not held by the Client or is not included in the Client's obligations.

CLIENT'S OBLIGATIONS

The Client agrees to provide the study designer with the following:

- technical input data required for executing the works outlined in this Terms of Reference. The inspection copy of the revised IDP will be delivered in English in a digital version. Other necessary documentation (DPN Decree, revised IDP from 2011, studies produced until now, technical bases, research, reports), that the Contractor considers necessary for further work will be as needed translated and handed over in English to the agreed extent.

- designate a contact person who will be available for further clarification and act as a liaison with the Contractor;

- review the documentation prepared by the Contractor (the Client is expected to finish the review within 4 weeks of receiving the inspection copy);

- organise a coordination meeting following the inspection of each document.

PAYMENT CONDITIONS

Payment will be based on the Price list, which is an integral part of the tender documentation. The Contractor will attach to the invoice a monthly situation, certified by the Client's representative, indicating the degree of certainty of the works or completion of each activity in the Price list. The payment period is 45 days from the date of receiving the invoice. An invoice not accompanied by a certified monthly situation or a certified completion of each stage of the works in accordance with the Price list will be rejected.

TIME SCHEDULE FOR PREPARING THE DOCUMENTATION

The execution of works and documentation preparation outlined in this ToR must adhere to the following deadlines, which may be subject to change due to Client modifications or additional requirements. The estimated timeframe for the production of the documentation begins upon the signing of the contract with the selected Contractor:

|  | Signing of the contract: | March 2025 |
| --- | --- | --- |
|  | Handover of draft version of the report on nIDP review: | 3 months after contract signing (review documentation will be handed over in full when the contract is signed) |
|  | Handover of the final review report | 1 month after receiving all comments |
|  | Analysis of the proposal for CDE and BIM | 3 months after contract signing |
|  | Start of preparing of LOT TGD | 6 months after contract signing |
|  | Handover of draft version of LOT TGD | 12 months after contract signing |
|  | Handover of final version of LOT TGD | 30 days after receiving/coordinating all proposals |
|  | Start of tendering procedure LOT TGD | June 2026 |
|  | End of tendering procedure LOT TGD and end of contract | May 2027 |

The end of tendering procedure also means signing the contract with the selected equipment supplier. This is also the end of the contract; hence, it is expected that all work under this contract will be completed by 31/05/2027.

ANNEXES

The annexes to this Terms of Reference include the following:

  - Annex 1 – Table of contents of the nIDP

  - Annex 2 – Detailed model for the organisation of tender documents for LOT TGD