| TEHNIČNA SPECIFIKACIJA | TECHNICAL SPECIFICATION |
| --- | --- |
| 1. OPIS PREDMETA NAROČILA | 1. DESCRIPTION OF THE SUBJECT MATTER OF THE CONTRACT |
| Predmet javnega naročila je izvedba svetovalnih storitev, katerih cilj je podpora pri pripravi in izvedbi celovite strategije za izboljšanje bonitetnih ocen Republike Slovenije v obdobju dveh let. | The subject of the public contract is consultancy services to support the preparation and implementation of a comprehensive strategy to improve the credit ratings of the Republic of Slovenia over a period of two years. |
| Storitve vključujejo naslednje vsebinske sklope: | The services comprise the following content areas: |
| Razvoj strategije za izboljšanje bonitetnih ocen, analiza bonitetnih dejavnikov in priprava kreditne zgodbe (400 ur) | Development of a strategy to improve credit ratings, analysis of credit factors and preparation of a credit case (400 hours) |
| Priprava celovite strategije z upoštevanjem metodoloških pristopov treh bonitetnih agencij, ki jih določi naročnik. | Preparation of a comprehensive strategy, taking into account the methodological frameworks of the three credit rating agencies designated by the Contracting Authority. |
| Izdelava podrobnih analiz in argumentov za izboljšanje ocen glede na metodologijo posamezne agencije. | Detailed analysis and arguments for improving the ratings according to each agency's methodology. |
| Priprava strukturirane »kreditne zgodbe« na podlagi modeliranja in primerjav z najmanj tremi primerljivimi državami znotraj ciljne bonitetne skupine. | Preparation of a structured “credit case” based on modelling and comparisons with at least three comparable countries within the target rating group. |
| Podpora pri pripravi na bonitetne preglede (420 ur) | Support in preparation for credit rating assessments (420 hours) |
| Svetovanje naročniku pri pripravi in vodenju komunikacije s tremi bonitetnimi agencijami, ki jih določi naročnik. | Advising the Contracting Authority on the preparation and management of communications with three credit rating agencies designated by the Contracting Authority. |
| Izdelava predstavitvenih gradiv, podatkovnih analiz in drugih strokovnih materialov. | Preparation of presentations, data analyses and other expert documentation. |
| Organizacija in izvedba strukturiranih brifiranj v obliki predstavitev ali delavnic (v živo ali na daljavo), katerih namen je preverjanje pripravljenosti, usklajenost sporočil in pričakovanj. | Organization and delivery of structured briefings in the form of presentations or workshops (on-site or remote) to verify readiness, consistency of messages and expectations. |
| Strokovno svetovanje in iskanje dodatnih priložnosti (400 ur) | Expert advice and identification of additional opportunities (400 hours) |
| Usposabljanja in krepitev kapacitet naročnika v obliki interaktivnih delavnic, predavanj ali simulacij (v živo ali na daljavo). Izvajalec pripravi tudi gradiva in pisne povzetke. | Training and capacity building for the Contracting Authority in the form of interactive workshops, lectures or simulations (on-site or remote). The provider shall also prepare supporting materials and written summaries. |
| Neprekinjeno svetovanje v zvezi z ocenjevalnimi postopki, odzivi agencij in prepoznavanjem dodatnih potencialov za izboljšanje ocene. | Ongoing advisory support in relation to rating processes, agency feedback and potential rating enhancement opportunities. |
| 3. ČASOVNI OKVIR IN IZVEDBA STORITEV | 3. TIMELINE AND PERFORMANCE OF SERVICES |
| Pogodba se sklene za obdobje 24 mesecev. | The contract shall be concluded for a period of 24 months. |
| Izvajalec mora z izvajanjem storitev po pogodbi pričeti takoj po sklenitvi pogodbe. | The Service Provider must commence service implementation immediately upon conclusion of the contract. |
| Storitve se bodo izvajale kombinirano – na lokaciji naročnika in na daljavo. | The services will be delivered in a hybrid form – both on-site at the Contracting Authority’s premises and remotely. |
| 4. NADZOR, PREVZEM IN POTRDITEV OPRAVLJENIH STORITEV | 4. SUPERVISION, ACCEPTANCE, AND CONFIRMATION OF SERVICES PERFORMED |
| Izvajalec bo po sklenitvi pogodbe v dogovoru z naročnikom pripravil izvedbeni načrt, ki bo predstavljal formalni operativni okvir za izvajanje storitev. Ta načrt bo vseboval najmanj: | Upon contract signature, The Service Provider undertakes to prepare, in coordination with the Contracting Authority, an implementation plan, which shall constitute the formal operational framework for the performance of the services This plan shall include at minimum: |
| - razdelitev storitev po vsebinskih in časovnih fazah; | - a breakdown of services by content and time phases; |
| - okvirni terminski načrt za izvedbo posameznih storitev oziroma faz; | - an indicative timeline for the implementation of each service or phase; |
| - opredelitev izhodnih rezultatov in pričakovanih učinkov po posameznih sklopih; | - definition of outputs and expected impacts by content area; |
| - obliko sodelovanja, poročanja in usklajevanja z naročnikom. | - the format of cooperation, reporting and coordination with the Contracting Authority. |
| Ta načrt bo služil kot podlaga za izvedbo, sprotno spremljanje napredka in vmesni ter končni prevzem posameznih storitev oziroma faz. Če tako predvideva izvedbeni načrt je izvajalec dolžan naročniku predložiti pisno poročilo oziroma drugo ustrezno dokazilo o izvedbi (v nadaljevanju: poročilo). | This plan shall serve as the basis for implementation, ongoing progress monitoring, and interim and final acceptance of individual services or phases. If so, provided in the implementation plan, the Service Provider shall be obliged to submit to the Contracting Authority a written report or other appropriate proof of performance (hereinafter: report). |
| Naročnik ima po prejemu poročila 20 delovnih dni za pregled in podajo morebitnih pripomb. V primeru pomanjkljivosti mora izvajalec pomanjkljivosti odpraviti v 10 delovnih dneh od prejema pripomb oz. v dogovoru z naročnikom. | The Contracting Authority shall have 20 working days upon receipt of the report to review and submit any comments. In case of deficiencies, the Service Provider shall rectify them within 10 working days from receipt of comments, or as otherwise agreed with the Contracting Authority. |
| 5. FINANČNI POGOJI IN PLAČILA | 5. FINANCIAL TERMS AND PAYMENTS |
| Določi se skupna vrednost pogodbe v EUR brez DDV za obdobje 24 mesecev. | The total value of the Contract in EUR excluding VAT is determined for a period of 24 months. |
| Naročnik bo izvajalcu povrnil tudi potrebne potne stroške in stroške prenočišča, ki so potrebni za kakovostno izvedbo predmeta pogodbe in bodo nastali po predhodnem dogovoru z naročnikom, vendar ne več kot 20.000 EUR brez DDV v celotnem obdobju trajanja pogodbe. Izvajalec je ob uveljavitvi povračila potnih stroškov dolžan predložiti ustrezno dokumentacijo, ki dokazuje nastanek le-teh. Upravičeni potni stroški so: | The Contracting Authority shall also reimburse the Service Provider for necessary travel and accommodation expenses essential for the proper performance of the subject-matter of the Contract, provided they are incurred with the prior consent of the Contracting Authority and do not exceed EUR 20,000 excluding VAT over the entire duration of the Contract. When claiming reimbursement, the Service Provider shall submit appropriate documentation proving that such expenses have been incurred. |
| - kilometrina za uporabo lastnega osebnega vozila v službene namene v višini, določeni z veljavno Uredbo o davčni obravnavi povračil stroškov in drugih dohodkov iz delovnega razmerja, Uradni list RS, št. 140/06 s spremembami in dopolnitvami; | - mileage for the use of a private vehicle for business purposes, reimbursed at the rate specified in the currently applicable Regulation on the Tax Treatment of Reimbursement of Expenses and Other Income from Employment (Official Gazette of the Republic of Slovenia, No. 140/06, as amended); |
| - stroški prevoza z javnimi prevoznimi sredstvi (vlak, taksi, avtobus, letalo), pri čemer se kot upravičen strošek šteje le ekonomski oziroma II. razred; | - The cost of transport by public transport (train, taxi, bus, plane), provided that only second-class or economy-class fares shall be deemed eligible for reimbursement; |
| - ter stroški prenočišča do višine 150,00 EUR brez DDV na osebo na nočitev. | - accommodation costs up to EUR 150.00 excluding VAT per person per night. |
| Računi se plačajo v 30 dneh po prejemu oziroma v roku, določenem v vsakokrat veljavnem zakonu, ki ureja izvrševanje proračunov Republike Slovenije. Prevzem storitve temelji na dokumentiranem rezultatu (npr.: izdana analiza za naslovitev možnosti izboljšanja bonitetnih ocen glede na ocenjevalne modele posameznih bonitetnih agencij, izvedena delavnica za naročnika z gradivi, predstavitveno gradivo in ‘brifiranje’ pred bonitetnim pregledom ali obiskom, kot določeno z izvedbenim načrtom). | Invoices shall be paid within 30 days of receipt at the latest, or within the time limit laid down in the law currently governing the execution of the budgets of the Republic of Slovenia. Acceptance of services is based on documented outputs (e.g. an issued analysis addressing credit rating improvements according to agency models, a delivered workshop with materials, briefing documentation prior to a credit rating assessment, as defined in the implementation plan). |
| 6. SANKCIJE IN ODSTOP OD POGODBE | 6. SANCTIONS AND TERMINATION |
| Pogodbena kazen za zamudo s pričetkom aktivnosti v skladu z rokom določenim v pogodbi zaradi razlogov na strani izvajalca ali za zamudo s pripravo strategije znotraj 2-letnega roka zaradi razlogov na strani izvajalca: 0,5 % vrednosti pogodbe v EUR z DDV na dan, za vsak dan zamude, do največ 10 % vrednosti pogodbe v EUR z DDV. | Contractual penalty for delay in commencing the activities within the deadline specified in the Contract due to reasons attributable to the Service Provider, or for delay in the preparation of the strategy within the two-year period for reasons attributable to the Service Provider: 0.5% of the total Contract value in EUR including VAT per day of delay, up to a maximum of 10% of the total Contract value in EUR including VAT. |
| Naročnik lahko brez odpovednega roka takoj pisno odpove pogodbo: - če izvajalec zamuja več kot deset (10) delovnih dni s pričetkom izvajanja pogodbe ali posamičnih faz po dogovorjeni časovnici; - izvajalec izvaja storitve v nasprotju s standardi stroke ali predpisi; - izvajalec krši določila o zaupnosti ali varstvu podatkov; - pri izvajalcu pride do insolventnosti, stečaja ali likvidacije, zaradi česar ne more izpolnjevati pogodbenih obveznosti. | The Contracting Authority may may terminate the Contract immediately in writing without notice: - if the Service Provider is more than ten (10) working days late in starting the Contract or individual phases according to the agreed timetable; - the service provider provides services in breach of professional standards or regulations; - the service provider breaches confidentiality or data protection clauses; - the Service Provider becomes insolvent, bankrupt or is wound up and is unable to fulfil its contractual obligations. |
| 7. KONČNE DOLOČBE | 7. FINAL PROVISIONS |
| Pogodba je sklenjena v slovenskem in angleškem jeziku, pri čemer se v primeru razhajanj uporablja slovenska različica. | The contract shall be concluded in Slovenian and English. In the event of any inconsistency or ambiguity in the interpretation of the provisions of the Contract, the Slovenian version shall prevail. |
| Pogodbenika soglašata, da bosta sporazumno reševali morebitne spore, ki nastanejo v zvezi z izpolnjevanjem pogodbenih obveznosti. Če sporazum med pogodbenima strankama ne bi bil mogoč je za reševanje sporov pristojno stvarno pristojno sodišče v Ljubljani. | The Contracting Parties agree to resolve any disputes arising in connection with the performance of contractual obligations amicably. Should an amicable settlement not be possible, the Contracting Parties agree that the court with subject-matter jurisdiction in Ljubljana shall have jurisdiction to decide the dispute. |
| Pogodba sledi določbam ZJN-3 in OZ. | The contract is governed by the Public Procurement Act (ZJN-3) and the Obligations Code (OZ). |