Implementation and maintenance of a planning tool to support Planning and Budgeting activities for the GEN-I Group

Functional specification

Prepared by: David Vidmar

Ljubljana,  October 2025

Table of contents

1.	Introduction	1

2.	Key objectives of the tender	1

3.	Current Planning and Budgeting Landscape	1

4.	Tender timeline	2

5.	GEN-I Group organizational structure	3

6.	Nonfunctional requirements	4

6.1.	Analysis phase	4

6.2.	Demo sessions	5

6.3.	Training	5

6.4.	User Acceptance Testing	5

6.5.	Project Management and Reporting	5

6.6.	Environments	6

6.7.	Source code review and handover	7

7.	Functional requirements	7

7.1.	Key Required Functionalities	8

7.2.	Additional Functionalities by Modules:	9

7.2.1.	HR Planning	9

7.2.2.	Cost Planning	10

7.2.3.	Revenue and Cost of goods sold Planning	10

7.2.4.	Investment and Depreciation Planning:	10

7.2.5.	Project Planning	10

7.2.6.	Debt and Interest Planning:	11

7.2.7.	Public Procurement Planning	11

7.2.8.	Cost allocation keys	11

7.2.9.	Reporting (Financial Statements)	12

7.3.	Integrations	12

8.	Warranty, maintenance and SLA	12

8.1.	Warranty	12

8.2.	Maintenance & SLA	13

8.2.1.	Response times	14

8.3.	Upgrades	15

Table of figures

Figure 1 Organizational structure on 7. 4. 2025	3

Figure 2 Response times	14

# Introduction

GEN-I, trgovanje in prodaja električne energije d.o.o. (“GEN-I”), is issuing a public tender for the implementation and maintenance of an enterprise-grade planning solution (“Solution”) for the entire GEN-I Group (“Group”). The Group is always expanding with new subsidiaries forming on a yearly basis, so a flexible and functional tool is required to sate GEN-I’s growing needs.

An additional purpose of the public tender is to analyze and improve our current planning and budgeting business processes in line with the chosen tool.

# Key objectives of the tender

The public tender’s key objectives are:

- The implementation of an enterprise-grade planning Tool for the entire Group (see GEN-I Group organizational structure to see the current snapshot of the Group)

- Conducting a detailed analysis of the current planning and budgeting process

- Preparing a detailed project plan to ensure milestones are met at the agreed upon deadline

- Optimizing the planning and budgeting process to be in-line with the chosen Solution

- Execution of all required Solution upgrades, changes and configurations

- Integrating the Solution with our identified back-end system, in the least with our Data Warehouse, at the most with other satellite (such as Salesforce Gecko and Microsoft Business Central 365) and other ERP systems

- Facilitate easier adoption of the Solution by

  - Preparing of user and administrator manuals

  - Executing structured training for the key users

- Export of the data to our chosen ERP, Data Lake or Data Warehouse

- Migrating 3 years’ worth of historic data (both financial plan and realization)

# Current Planning and Budgeting Landscape

Currently, GEN-I uses Microsoft Office Solutions, primarily Microsoft Excel, for its planning process, which has facilitated the Planning and Budgeting process since before 2020. Due to the company's rapid and drastic growth (business volume, number of employees, etc.), managing such processes on this scale is prone to error’s and is not transparent enough so a new Solution is required.

The current pain points are:

- a large volume of input data;

- a greater number of people involved;

- a greater number of final financial statements and their increased complexity;

As part of the analysis to find new technological tools, we want to pursue the most advanced information solutions and good industry practice, so we will approach a comprehensive redesign of business processes instead of upgrading existing ones.

# Tender timeline

The new tool is set to go live in 2026 with the following key milestones (M signifies the contract signing date):

- 31st of December 2025:

  - Prepared project plan with functional, non-functional and integration requirements,

  - Prepared development environment only for HR, Cost Planning module and allocation keys

- 31st of March 2026 (UAT 1):

  - Environment configured for the following segments:

    - HR Planning,

    - Cost Planning,

    - Cost Allocation Keys,

  - All other activities for Solution testing completed (includes all configuration activities, data migration activities, training sessions completed),

  - Integration with ERP and DWH established and functional,

- 30th of April 2026 (PROD 1):

  - UAT 1 successfully completed (no remaining bugs or discrepancies with this technical specification),

  - Production environment ready, with data, configuration and upgrades migrated from UAT,

  - Solution in active use,

  - Relevant user and administrator manuals prepared,

- 31st of October 2026 (UAT 2):

  - Environment configured for the remaining segments,

  - All other activities for Solution testing completed (includes all configuration activities, data migration activities, training sessions completed) for the remaining segments,

  - Integration with ERP and DWH established and functional,

- 28th of February 2027 (PROD 2):

  - UAT 2 successfully completed (no remaining bugs or discrepancies with this technical specification),

  - Production environment ready, with data, configuration and upgrades migrated from UAT,

  - All user and administrator manuals prepared,

  - All user acceptance tests completed and any identified bugs repaired,

  - Hypercare

- 1st of March 2027 until 30th of October 2028

  - Maintenance and support

# GEN-I Group organizational structure

Figure 1 Organizational structure on 7. 4. 2025

# Nonfunctional requirements

## Analysis phase

The Contractor will own analysis and design activities using the steps described below:

- The entire phase is made from the following activities

  - Analyze

  - Model

  - Present

  - Review

Analyze

The contractor’s team will conduct workshops with GEN-I’s team in order to identify functional and nonfunctional requirements. Workshops will be done in person in GEN-I’s offices in Ljubljana, Slovenia.

Model

The Contractor will map identified processes and requirements to the Solution and endeavor to use out-of-the-box functionalities wherever possible. Where not possible, the Contractor will document in detail the identified gap and the proposed solution. The Contractor is expected to actively help the client in identifying opportunities for the optimization of business processes by leveraging the out of-the-box functionalities of the Solution. The Contractor must ensure the availability of senior domain experts to provide guidance and support during the analysis phase.

Present

The Contractor will prepare a formal document in Excel, which will cover in detail all functional and nonfunctional requirements. The document shall describe the following:

- All functional requirements, which are identified during the analysis workshops. The functionalities should be split into sections. All requirements need to have a short description.

- A marking to identify requirements that need development

- A separate section for nonfunctional requirements

- A separate section for integrations (originating system, target system, short description, effort required, is a change request and any other pertinent information)

The Contractor will present all the functionalities in person at GEN-I’s location in Ljubljana, Slovenia.

Review

After the presentation the Contractor must submit all relevant materials to GEN-I for review. The Contractor will allow fourteen calendar days for GEN-I’s review. Afterwards, the suggested solution is either approved or rejected for further review and re-work. In the latter case, findings are gathered and work on resolving the issues proceed. The duration of the re-work will be subject to the complexity encountered. If required, Analyze-Model-Present steps are repeated until approval is obtained. Approval may be delayed until an appropriate extension description is provided and approved by GEN-I.

As part of this phase, GEN-I will prepare high-level test scenarios, described in chapter 6.4.

Approval

Approval and rejections as per this Point shall be delivered by the GEN-I Project Manager or any other GEN-I Project member via email. All requirements in this Tender documentation must be met by the Contractor’s solution and the solution must be approved by GEN-I.

The Contractor shall submit a project plan along with the functional and non-functional requirements, which supports implementing the Solution within the dates set forth in this tender.

## Demo sessions

The Contractor should as part of the project plan prepare demonstrations of the Solution, where it demonstrates one or more functionalities described in chapter 7. The purpose of these demonstrations is to align expectations between the Contractor and GEN-I. The demonstrations may be done on ‘demo’ data if GEN-I’s data is not available.

After the demonstration GEN-I reserves the right to amend the test scenarios submitted at the end of the review phase.

## Training

To ensure the successful adoption of the Solution, it's crucial to empower key users within GEN-I to transfer their knowledge to other users in the organization. This approach, often referred to as "train the trainer," enables these empowered individuals to serve as subject matter experts and facilitators of learning. The training should be executed in person at GEN-I's location in Ljubljana, Slovenia.

## User Acceptance Testing

User Acceptance Testing (UAT) commences after the Contractor has implemented all agreed functional and non-functional requirements, no later than milestone 2 mentioned in chapter 4.

Before user acceptance testing (UAT) can commence, the contractor must first conduct thorough testing of the program using GEN-I’s data. This step is essential to ensure that all functionalities are working correctly and that the program meets GEN-I’s specific requirements. GEN-I will provide high-level test scenarios after the presentation phase for the contractor to test. GEN-I will not exceed more than 15 tests per functionality group unless agreed with the contractor. Only upon successful completion of this preliminary testing phase will the program be ready to proceed to UAT.

## Project Management and Reporting

The Contractor is required to meet the following requirements in the Implementation phase:

- Biweekly and final reporting:

  - The Contractor will send biweekly reports and a final report with the following sections:

    - Overall Project Status

    - Open questions, blockers, warnings etc.

    - A detailed Project Plan which includes all functional and nonfunctional requirements along with their status (the output from the analysis phase may be used to fill in this section). The statuses used are “Not yet started”, “In progress”, “Done”, “Delayed”, “Cancelled” unless otherwise agreed.

    - Project invoicing to date - a list of issued invoices with basic details (date of issue, amount, sum of invoices) and their sum. The list also contains the cost of services not yet invoiced for the current month on biweekly reports.

    - Frequency:

      - Reports should be sent biweekly (every second Monday for the previous two weeks), and a final cumulative report is composed at the end of the Implementation phase of the project.

      - The client can request up to 5 ad-hoc reports at any time during the Implementation phase of the project.

  - Format:

    - Document format (.xlsx unless otherwise agreed)

  - Repository:

    - Reports are copied to the designated GEN-I Microsoft Teams Folder.

  - Readability and structure:

    - The report must be prepared in a concise and structured form.

    - Descriptions must be unambiguous and must provide a clear understanding of how the Contractor is meeting each of the requirements (they must include descriptions, print screens, written explanations, references to recordings of the workshop sessions where the requirements were demonstrated etc.).

    - The completion of one-time (non-repetitive) requirements can be described once, but how the Contractor is meeting continuous (on-going) requirements needs to be reported on a continuous basis.

  - Meetings

    - The frequency of meetings will be discussed during the analysis phase but should occur at least once per month and at most once per week. The Report should be sent regardless of the set meeting frequency.

  - Approval:

    - Each report needs to be approved by the client.

  - Conditions for payments:

    - Reports that are approved by the client are a prerequisite for every invoice to be approved.

## Environments

The Contractor is required to provide the following types of environments for the successful implementation of the Solution:

- Test / Development environment

  - The primary environment for all demonstrations and user tests. This environment should be connected to GEN-I’s test systems where applicable.

  - The environment must support data refresh from another (e.g. production) environment.

  - The environment should be powerful enough to support user testing.

- Production environment

  - The production environment is where the solution is deployed. This environment should be connected to GEN-I’s production systems where applicable.

The Contractor may suggest other environment configurations but should note them in the tender proposal.

## Source code review and handover

All code developed specifically for GEN-I must be delivered to GEN-I’s repositories. This includes:

- Source code of all GEN-I specific improvements

- The Solution’s data (unless GEN-I accepts a SaaS environment, where GEN-I will not be providing any infrastructure)

The Source code must:

- Be delivered to a GEN-I Azure DevOps repository

- Be accompanied by comments

- Be reviewed by a senior staff member from the Contractor

- Must be in line with generally accepted coding standards

# Functional requirements

The functional requirements are set as an acceptance condition in the following document of this document:

Attachment 1: Tender_Spec_Planning_Solution_Clean.xlsx

All bidders must complete the document, by completing all the fields in columns E and F, and G where applicable.

# Warranty, maintenance and SLA

## Warranty

For all products created based on this public tender (including, without limitation, upgrades and patches for the Solution), a general warranty of 24 months applies, starting from the day the product is accepted, installed in the production environment, and confirmed by the client.

The warranty can be claimed for all products that are not technically flawless and/or contain defects or other deficiencies identified by the client (incomplete or non-compliant operation of the application in relation to the functional specification or any other description that was presented to the developer by the client before development started or during the implementation process). A deficiency cannot result from changes in the business environment, technological changes requiring technology upgrades, modifications, or obsolescence of third-party components used.

For all such defects, the client defines the severity level of the defect or deficiency as specified in the table below. The client submits the defect report, including a description of the issue, to the contractor for resolution.

The contractor is obligated to carry out all warranty repairs at their own expense. Warranty repairs shall also not be counted towards the allocated hours defined in chapter 8.3. The warranty defined in this article does not cover defects or deficiencies caused by force majeure.

The warranty does not apply to defects in products that result from:

- Malfunctions of hardware or third-party software,

- Use of products contrary to the contractor’s instructions,

- Force majeure or other reasons beyond the contractor’s control.

- The warranty does not include:

Hardware and delivered licensed software, including their functionalities and operation, which are subject to the manufacturer’s terms and conditions if not provided by the contractor,

Software components from third-party vendors, and possible interactions between hardware and software that are beyond the contractor’s control or differ from the system architecture defined for a specific project in the technical documentation.

If a warranty claim submitted by the client is later found to be unfounded during the resolution process (e.g., correct operation, operation in accordance with the specification, functionality of the hardware and licensed software, or non-functionality caused by modifications to the solution architecture made by the client outside the agreed project scope), the client shall reimburse the contractor for the time spent resolving such a claim based on the contractor’s general price list and in accordance with the contract amendment proposal under ZJN-3.

## Maintenance & SLA

As part of the basic maintenance service, which does not result in functional changes to the Solution, the provider is expected to deliver the following services to the client for the duration of the contract:

- Performing administrative and management tasks related to contract execution,

- Resolving operational and usage disruptions of the information system (diagnostics, troubleshooting, coordination, and notifications), emergency technical interventions in the system, applications, and databases based on client requirements,

- Carrying out functional and technical maintenance tasks for the business information system,

- Ensuring the availability of a properly trained technical and consulting team,

- Monitoring legislative changes related to the business information system and updating solutions accordingly,

- Consulting and diagnosing issues and errors,

- Maintaining system code and documentation (technical and user documentation),

- Assisting users, system administrators, and other business partners of the client when dealing with interconnected and dependent systems,

- Fixing operational issues in the business information system, including updates, patches, and enhancements to the business information solution,

- Providing support for additional implemented solutions that are not part of the standard system,

- Delivering the necessary support for the effective operation of the system,

- Installing critical software patches,

- Providing additional explanations, consulting, and training on system usage,

- Preparing statistical and analytical reports,

- Other support services as agreed between the parties.

All changes are prepared and implemented in the system in agreement with and upon approval by the client.

### Response times

| Priority | Description | Time for first response | Time to resolution |
| --- | --- | --- | --- |
| Critical | - Non-standard operation of the business information system, resulting in a complete system failure or a significant decrease in operational quality, or affecting other software connected to the solution. - Requests for immediate assistance and functional updates without which the system can no longer be used. The criterion for determining a critical level issue is the absence of any workaround for a problem that threatens business operations through a process in the system. | 2 hours | 4 hours |
| High | - Non-standard operation of the system, leading to a complete system failure, a significant decrease in operational quality, or causing failure or a substantial decline in the performance of other software connected to the system. - Requests for immediate assistance and functional updates without which the system’s performance is significantly reduced. For high-level issues, a short-term workaround exists to allow the temporary completion of the business process. | 4 hours | 8 hours |
| Medium | - Non-standard system operation and requests for immediate assistance and functional updates that only affect less critical business processes. | 8 hours | 7 days or by agreement |
| Low | All other requests | 16 hours | 7 days or by agreement |

Figure 2 Response times

The response time is counted within the client’s working day, which is every business day from Monday to Friday, from 08:00 to 16:00 (Slovenian local time), excluding Saturdays, Sundays, public holidays, and other legally designated non-working days. If the client reports a critical or high-priority issue at the end of the working day, the contractor is still obligated to respond even if the response time extends beyond the client’s working hours.

## Upgrades

As per our agreement, we reserve the right, though not the obligation, to utilize up to 400 hours of implementation time for various out-of-scope activities related to the functionalities described in chapter 7. These activities may be undertaken during any phase mentioned in the tender timeline, ensuring flexibility and adaptability in addressing unforeseen needs and enhancing project outcomes.