Kozjak PSHPP

TERMS OF REFERENCE

LOT 1

Preparation of expert documentation for the construction of the storage basin of the Kozjak PSHPP at Kolarjev vrh, activities and documentation regarding test fields

Maribor, October 2025

Table of contents

1	SUBJECT OF THE TERMS OF REFERENCE UNDER LOT 1	3

1.1	Subject and objective of the ToR	3

1.2	Services	3

1.3	Basis for preparing documentation	5

1.4	Scope	5

2	REQUIREMENTS FOR THE PREPARATION OF TECHNICAL DOCUMENTATION FOR THE CONSTRUCTION OF THE STORAGE BASIN	6

2.1	Contents of technical documentation for the construction of the storage basin	7

2.1.1	Review and analysis of existing documentation and research	7

2.1.2	Design of the storage basin	7

2.1.3	Monitoring of the facility	8

2.1.4	Maintenance and operation	8

2.1.5	Construction timeline	8

2.1.6	Material movements and surpluses	9

2.1.7	Designer's estimate of the value of the works	9

2.2	Requirements for implementing BIM processes	9

2.3	Land survey	11

3	Implementation of embankment test fields, measurements, and tests	11

3.1	Design and construction of test embankments	12

3.2	Equipment for mechanical installation	14

3.3	Course of work	15

3.3.1	Preparation of the base – formation level	15

3.3.2	Quality control of materials intended for installation in test embankments	15

3.3.3	Construction of test embankment	16

3.3.4	Control of the effectiveness of the rolling and control of the quality achieved	16

3.3.5	Work management and supervision	18

3.3.6	Control of the properties of the embankment after a specified resting period	18

3.4	Report of the test field implementation	19

4	OTHER OBLIGATIONS OF THE CONTRACTOR UNDER LOT 1	19

5	OBLIGATIONS OF THE CLIENT	20

6	SCHEDULE FOR THE PERFORMANCE OF SERVICES UNDER LOT 1	21

SUBJECT OF THE TERMS OF REFERENCE UNDER LOT 1

Subject and objective of the ToR

- Preparation of technical documentation for the construction of a storage basin, using existing material at the site of the upper storage basin of the Kozjak PSHPP at Kolarjev vrh. Based on the prepared documentation, completed research, and field inspections, prepare technical documentation that will analyze the input data and provide solutions that, taking into account all safety requirements and completed geological/geomechanical research, hydrogeological studies, and test embankment fields, enable the construction of the storage basin with the maximum possible use of material on site and thus the minimum possible movement of material. To this end, the excavated and reused material will be levelled as much as possible in the embankments of the upper storage basin and in the landfills near the upper storage basin.

- Support to the owner in implementing the test fields

Services

- Technical documentation for the construction of the storage basin

- Review and analysis of existing documentation and research, which the client will provide to the contractor in electronic format, presumably in PDF (documentation prepared before and after the adoption of the DPN)

- Preparation of technical documentation for the construction of the storage basin at the level and content of the project for implementation, detailed design or “for construction”:

- analysis and review of the proposed solutions based on the existing documentation,

- analysis of geological/geotechnical surveys and the possibility of installing material on site, both in the banks of the accumulation lake and the landfill, as well as the road (local road),

- analysis of hydrogeological surveys (interim results, as monitoring will take place over two years),

- dimensioning and planning of the storage basin as a whole, including the drainage system under the storage basin in such a way that it will ensure safe operation and comply with all regulations, standards, and legal requirements for safety, and that, as far as possible, given the properties of the material, the material used will be located at the planned construction site of the storage basin

- mass balances – the designer shall take into account as much as possible also the material from excavation works for tunnels and cavern,

- detailed technical report with detailed construction technology,

- detailed technical drawings of all mentioned parts of the storage basin,

- detailed documents and information needed for tender documentation – tendering according to FIDIC red book

- the location and dimensions of the path along the dam of the storage basin, including access to the inlet/outlet structure for the purpose of accessing the storage basin, the top of the basin, and the structures that will be located on the basin,

- design of technical monitoring for the purpose of monitoring the dam to ensure the highest possible level of dam safety

- specification of requirements or restrictions for the arrangement of the embankments of the accumulation basin dam (details of drainage and dewatering, possible planting and other arrangements, etc.)

- designer's estimate of the construction value or cost estimate and detailed construction schedule by construction phase,

- The documentation (plans) must be produced in digital form and designed in accordance with the BIM (Building Information Modeling) methodology, which includes structured modeling of the object, coordination between disciplines, and digital monitoring of all phases of the project. The documentation must enable the linking of models with attributes, spatial verifiability, and quantitative analysis.

- Cooperation with the client, engineer, consultant, DGD designer, and EIA author in terms of developing the optimal solution and at public presentations to the local community and civil initiatives. To a greater extent, meetings are expected to be held via communication channels (TEAMS) and, if necessary, physically at the client's premises and at public presentation locations. One live meeting for coordination with engineer, consultant (from LOT 2), Client will be organized by the Client after draft peer review.

Clarification: inlet/outlet structure, bridge to inlet/outlet structure, sealing details between pressure pipe and reservoir are not part of scope under this ToR.

- Support to the owner in implementing the test fields

- The Design services will follow the regular design development pathway, where the various technical and material parameters are defined, which will form the basis of the Field Tests. The Designer will prepare all the required specifications and information needed for the test field as well as assist the DEM in the preparation of the Terms of Reference (ToR) and BoQ for the execution of the Test field, which themselves would be undertaken as part of a separate Lot (as described below). The Designer takes an active role in supervising the Test Fields, with the results being incorporated into the final Detailed Design once the tests have been completed. The deliverable would be the complete Detailed Design for the Upper Reservoir.

- Preparation of technical requirements for the test fields implementation, measuring, laboratory tests and supervision of onsite works, on site measurements, tests and results. A document with technical requirements will be part of the ToR for the test fields implementation. Tender for the test fields will be separate order.

- Support during implementation of the test fields.

The requirements for individual services are specified in more detail below in this ToR.

Basis for preparing documentation

The basis for preparing documentation and technical documentation for the construction of the storage basin in accordance with this ToR is the DPN, the project and other documentation already prepared, as listed in Table 6, legislation, regulations, guidelines, Eurocodes, standards, and other relevant documentation dealing with the design and construction of large embankments. The design must take into account good engineering practice in the design and construction of large embankments around the world.

Scope

The scope of the documentation for the construction of the storage basin is as follows:

- the boundary of the DPN area for the location of the storage basin,

- maintenance roads and access to facilities at the reservoir are planned within the scope of the embankment planning – the boundary is the location of the junction of maintenance roads with public local roads,

- local roads – local roads are not part of the planning under this ToR, but the contractor will have to take into account the data on the location and construction arrangements of local roads, which it will receive from another designer and will take into account when planning the embankment and roads across the embankment

- the drainage gallery and the entire drainage system below the storage basin floor are considered an integral part of the storage basin and are designed within the framework of the technical documentation under this ToR,

- inlet/outlet structure in the storage basin – area of the slope for the arrangement of the bed around the inlet/outlet structure, the inlet/outlet structure itself is not covered by this ToR, as the design of the structure is currently being optimized and the structure as such is not yet complete; however, the contractor shall specify the requirements for the connection and sealing of the bottom lining of the storage basin with the area of the bottom slope around the inlet/outlet structure in accordance with this ToR,

- The vertical shaft for the installation of the penstock running between the upper basin and the powerhouse is not covered by this ToR.

- bridge to the intake/outlet structure – access from the maintenance paths across the embankment of the storage basin to the bridge structure–, and the foundations of the bridge structure are not covered by this ToR; the contractor will receive information on the location and construction arrangements of the foundation from the designer DGD for PSP and will take the foundation into account when designing the embankment and the final elements of the joint and sealing of the bottom of the storage basin,

- water level vent structure with connection to the water level – the vent structure itself is not subject to consideration under this ToR, but the contractor will take it into account when designing the embankment based on information about the location and construction arrangements of the structure. in this study, the contractor will only take into account the quantities of excavated material that will be released at the location of the upper basin.

REQUIREMENTS FOR THE PREPARATION OF TECHNICAL DOCUMENTATION FOR THE CONSTRUCTION OF THE STORAGE BASIN

The contractor will prepare technical documentation for the client on the use of materials at the site of the upper storage basin of the Kozjak PSHPP at Kolarjev vrh. The documentation will be prepared in Slovenian language or in English language. In accordance with the subject ToR of the produced documentation, individual documents must include content from all areas relevant to the individual document (architecture, construction, electrical engineering, mechanical engineering, fire safety, landscape architecture, etc.).

To prepare the documentation, the contractor must appoint a design manager and engineers from each field. The appointed design manager and other engineers must be from the list of reference personnel in the application or tender and must meet the conditions set out in the document General Instructions to Tenderers.

The completed documentation shall be submitted to the client in three (3) printed copies, an electronic copy in PDF format, and active source formats for the preparation of documentation by transferring the documentation to the client's portal. The printed and electronic versions of the documentation must be identical. The completed documentation becomes the property of the client, who thereby acquires all rights related to the review, revision, and use or enabling of the use of the prepared document by third parties involved in the project in subsequent phases of the preparation of documentation for the same project.

All documentation produced must be compatible with current versions of programs such as:

  - MS WORD for text,

  - MS EXCEL for tables and spreadsheets,

  - MS ACCESS for databases,

  - graphic attachments in *.ifc and *.dwg formats (Autodesk Revit, AutoCAD or other programs that allow export to these file formats) and

  - timelines in MS PROJECT.

The documentation produced at each stage is submitted to the client for review. The client will review the documentation within one month and submit a report with comments, suggestions, and remarks. The review will also include an engineer, a DGD designer for PSP, and EIA author. The contractor is obliged to consider the comments, suggestions, and remarks in a meaningful way or to argue for a solution different from the client's proposal and to respond to the client's comments, remarks, and questions.

The technical documentation must be prepared at the PZI level (contain all content in accordance with the Regulations and rules of the IZS profession, for construction documentation, execution documentation, detailed design, for FIDIC red book tender documentation, detailed construction technology, mass balances, detailed technical drawings) and will serve as the basis for planning the transport of materials in real time (transport m3/day) and the execution of construction, therefore, it must contain all the necessary content in accordance with the Rulebook on Detailed Content of Documents and Forms Related to the Construction of Objects, including all forms, the Building Act, professional rules, regulations, standards, good practice, and all necessary detailed content, requirements, and technical solutions for the manufacture of equipment and materials and for the performance of services in the field.

The documentation must include plans from all relevant areas for the comprehensive treatment of the storage basin and water supply or provision of water sources.

During further planning and construction, the contractor will cooperate with the client, the client's supervisor, and the contractor in terms of interpreting the solutions provided in the documentation according to this ToR.

Contents of technical documentation for the construction of the storage basin

The contents of the documentation must be prepared at the level of PZI documentation. The documentation must be prepared in accordance with the requirements of relevant legislation and regulations, guidelines, standards, and must take into account professional rules and the requirements of this ToR.

Review and analysis of existing documentation and research

Prior to commencing design work, the contractor must review all documentation, technical bases, and studies already prepared that relate to the area of the planned accumulation and embankment system. The documentation must include:

- a technical analysis of the adequacy and applicability of existing research and documents,

- identification of any missing information necessary for further design,

- proposals for additional research necessary for the safe, reliable, and comprehensive design of the storage basin and embankments,

- justification of the choice of methods and scope of additional research based on the designer's assessment of risks and technical requirements.

Design of the storage basin

When designing the storage basin, the contractor must perform:

- Analysis of geological and geomechanical research

These are intended to determine the suitability of the location for the embankment foundation, identify potential geotechnical risks, and determine the mechanical properties of the ground and construction materials for stable construction. They provide the basis for stability analyses and modeling of the embankment's performance under various loads.

- Analysis of hydrogeological investigations

These are necessary to assess the interaction between the storage basin and the groundwater, determine the risk of filtration, assess the need for drainage systems, and the possible installation of injection curtains to prevent water infiltration.

- Seismological analysis

Determines the seismic hazard of the location and specifies the loads for seismic design. It serves to verify the stability of the embankment during earthquakes and ensures adequate protection against liquefaction and settlement.

- Structural design

Ensures the optimal design of the embankment in accordance with functional, stability, safety, and operational requirements. It includes the following key elements:. It includes the following key elements:

- Embankment/dam body: Its main purpose is to ensure the stability and shape of the upper storage basin structure while retaining water in the basin. The embankment body is constructed in layers with simultaneous compaction of earth material obtained by sorting excavated material. The material for installation is mechanically processed in advance and prepared for installation in the embankment (additives may also be added in small quantities). Depending on the progress of other works (pipeline installation, etc.), the embankment can be built in its entirety or in sections. In the case of excavated earth material of very different qualities, it can be mixed together to improve its quality, or individual materials can be installed in embankment zones that differ in terms of load-bearing capacity, earthquake resistance, etc., thus allowing lighter soil to be used in low-load embankment zones, while the highest quality material is used in high-load embankment zones. After construction, the entire embankment must ensure a homogeneous structure.

- The sealing of the basin is ensured by an asphalt coating or according to designer proposal or technical solution laid on a granular sub-base and a drainage layer. Drainage pipes with an outlet into the drainage/control corridor are to be installed below the basin floor. Sealing of the joint between the storage basin and the inlet/outlet basin – a solution must be provided that will be taken into account by the designer of the inlet/outlet basin.

- Filters: Layers around the drainage system that prevent fine particles from being washed out of the embankment into the drainage zones. The filters are designed according to erosion protection criteria and ensure water permeability but not soil particle permeability.

- Drainage: A system of drainage layers and pipes that allows for the controlled collection and drainage of water that may seep through the embankment. It is designed to reduce pore pressures and ensure the stability of the structure. A properly functioning drainage system is crucial for long-term safety. In the control/drainage corridor below the basin floor, seepage water is collected in a shaft and pumped back into the basin.

- Monitoring equipment: Includes shafts, measuring and control devices that enable accumulation level control and controlled filling and emptying. This equipment must be reliable, accessible for maintenance, and protected from external influences and possible blockages.

- Consideration of safety risks and specification of risk mitigation solutions

- detailed technical report with detailed construction technology,

- detailed technical drawings of all mentioned parts of the storage basin,

- detailed documents and information needed for tender documentation – tendering according to FIDIC red book

Monitoring of the facility

The contractor under this ToR must provide for continuous technical monitoring systems that are essential for continuous monitoring of the facility's functioning and detection of any deviations. Monitoring provides information for preventive measures and ensures long-term safety.

Maintenance and operation

It specifies measures and procedures for the safe use of the embankment throughout its entire life cycle. It includes instructions and protocols for filling, operation, and regular maintenance, which are necessary to prevent degradation.

Construction timeline

The contractor must prepare a realistic, phased construction timeline that includes key construction phases ( earthworks, installation of the core, filter elements, drainage, and equipment). The plan enables effective organization of the construction site, timely execution, supervision of the work progress, and, above all, serves to determine the necessary quantities of individual materials to be transported and to optimize transport.

Material movements and surpluses

A quantitative analysis of the quantities of excavated and used material is required. The volumes of material to be incorporated into the embankment body and the residues (surpluses) for which temporary or permanent storage locations must be provided are determined. The aim is to optimize costs and prevent environmental impacts.

Mass balances – the designer shall take into account as much as possible also the material from excavation works for tunnels and cavern.

Designer's estimate of the value of the works

Based on the documentation prepared, the contractor must prepare a designer's bill of quantities. The estimate must be based on the anticipated quantities, prices of construction works and equipment, and include provisions for unforeseen costs. The purpose of the estimate is to guide the client in preparing the investment documentation and tender conditions.

Requirements for implementing BIM processes

The client's intention in planning the Kozjak PSHPP is to manage the project effectively through the implementation of BIM processes, on the basis of which the project will be implemented efficiently, on time, to a high standard, in accordance with the client's requirements, and economically. The planned BIM design processes, to which the provisions of the SIST EN ISO 19650 series of standards apply mutatis mutandis, must ensure:

effective and appropriately documented communication between all project stakeholders,

the possibility of active monitoring of project development,

control and approval of design solutions by the designer and client.

The client's goal is to use the implementation of BIM processes to ensure careful and economical management of the investment, design, execution, and management and maintenance throughout the entire life cycle of the building, its components, elements, and equipment. The implementation of BIM processes must enable:

- conformity and accuracy of digital information models (conflicts, project standards, etc.)

- coordination and recording of all project development changes,

- consistent use of CDE (storage, recording, communication between stakeholders),

- evaluation of quantities based on information (geometric and non-geometric) from models and sub-models,

- use of information from models and sub-models during implementation,

- use of information from final models and sub-models during operation and maintenance.

For the planned implementation of BIM processes, the contractor must prepare a BIM Execution Plan (BEP) in accordance with the recommendations of professional chambers and standards, in which it defines the planned method of implementing BIM processes, which, after the contractor has been selected, must be coordinated with the client. The contractor must submit a proposal for a BEP when submitting the tender. The content of the BEP proposal must define the following: The content of the BEP proposal must define the following:

the strategy, purpose, and objectives of BIM implementation;

information about the project and the client's requirements highlighted by the implementation of BIM processes;

definition of the use of BIM processes by determining roles and responsibilities, anticipated models and sub-models and their coordination in a combined model, protocols for documenting changes and control and approval of individual models;

determination of the anticipated processes by defining the project coordination baseline, the method of managing and transferring models, communication protocols and milestones for coordination, coordination and transfer of digital models; if the project baseline has already been defined in previous or parallel phases of the project, the already defined coordinate baseline must be adopted.

determination of project standards (coordinate system, units of measurement, method of naming information containers and definition of the method for determining the Level of Information Need (LOIN); if project standards have already been defined in previous or parallel phases of the project, the already defined project standards must be adopted.

definition of the planned information tools, software versions, and format of the planned information containers;

establishment of a table of building blocks for determining the attributes and properties required for the project (LOIN);

definition of a strategy for fulfilling the obligations assumed and a method for ensuring the cooperation of all stakeholders based on the open BIM approach.

LOIN is determined by mutual agreement in the final BIM implementation plan by the designer on the basis of a proposal prepared in accordance with SIST EN 7817-1:2024, the planned lots, and the client's requirements. The BEP may be supplemented and upgraded on an ongoing basis depending on the development stage of the project, based on an agreement between the client and the contractor. When using a BIM-compliant classification method, the contractor must ensure additional labeling according to the HSE group's KKS classification system standards and ensure that the attributes and properties that are important for project information are provided for the building elements. Data exchange based on the digital information model is carried out in open format *.IFC, version 2x3 or higher, whereby all digital information models and their sub-models must be saved in a uniform IFC version.

Upon completion of the documentation, a complete information model (BIM model) is delivered to the client in .IFC open format and in the original format of the parent software:

BIM model with all sub-models (project handover for review) and

BIM model with all sub-models (project handover after review).

The completed information models, including all information and attributes, become the property of the client, who acquires all rights related to reviewing, reviewing, and processing, as well as for the use or enabling of equivalent use of the completed model by third parties involved in the project in subsequent phases of documentation preparation for the same object.

The implementation of BIM processes is envisaged in a Common Data Environment (CDE), which is provided by the client or the client's contractor under a separate contract and where all information containers are stored. The coordination of spatial models and sub-models within the scope of this ToR shall be ensured by the client in a common data environment, for which purpose the contractor shall provide its own BIM coordinator. After the documentation has been completed and coordinated, the finished information model (BIM model), with all associated sub-models and all information (all components, their attributes and properties), shall be handed over to the client in .ifc open format and in the native format of the source software.

Land survey

The contractor will receive the land survey plan from the client after signing the contract.

Support to the owner in implementing the test field

The technical requirements for the test fields implementation

The contractor shall prepare technical requirements for the test fields implementation. Those requirements will be part of the tender documentation for the test fields implementation order.

Processed shall be:

- Design and construction of test embankments

- Equipment for mechanical installation

- Course of work

  - Preparation of the base – formation level

  - Quality control of materials intended for installation in test embankments

  - Construction of test embankment

  - Control of the effectiveness of the rolling and control of the quality achieved

  - Work management and supervision

  - Control of the properties of the embankment after a specified resting period

- Report of the test field implementation

Support during the test fields implementation

The contractor shall support to the owner at:

- Review of the test fields documentation

- Onsite works supervision – 2 site visits are foreseen!

- Cooperation at the meetings (online, in the owner premises, onsite)

- Results clarification of the test fields measurement and tests

OTHER OBLIGATIONS OF THE CONTRACTOR UNDER LOT 1

Under the signed contract, the contractor undertakes to:

performs work under this ToR in accordance with the terms of reference, to a high standard, in compliance with legislation, regulations on project and other documentation and forms for the construction of buildings, relevant standards, professional rules, good practice, and the client's instructions,

provide appropriate personnel, equipment, and machinery to perform the work within the specified deadlines;

site visit of engineers responsible for preparing of design documentation is mandatory

cooperate with the client, engineer, DGD designer, and participate in public presentations;

at its own expense and within the time limit agreed with the client, perform additions and changes to the scope of services taken over if it is found that the contractor has performed the services inadequately;

obtain consent from owners and other consents for the implementation of test fields;

prepare all graphic attachments in the documentation in a manner suitable for use in a GIS environment. This means that the labeling of project lots, equipment, and devices must also be designed in such a way that it will be usable within the GIS environment.

Before the documentation is prepared, a list of folders by professional field must be prepared and submitted for approval. The contractor shall determine the structure of the documentation folders in agreement with the client, whereby the designer shall prepare a proposal for all documentation no later than 20 working days after signing the contract and shall finalize it with the client for each individual phase no later than 10 working days before the start of the preparation of the documentation for each individual phase;

coordinate the scope of BIM with the client's requirements no later than 30 days after signing the contract, and

hand over to the client the scope of documentation agreed upon in the contract in paper and electronic form;

submit a review copy of the individual documentation to the client for review, and take into account the comments, suggestions, and remarks provided in the final draft, or justify different solutions.

Documentation prepared under this LOT 1 will be subjected to review of third party (LOT 2). One live meeting will be organized by Client after draft review report from consultant under lot 2, to coordinate, communicate and adjust all technical solutions.

OBLIGATIONS OF THE CLIENT

The client will provide the contractor with:

the input data listed in the table below (in electronic form),

the name of a contact person who will be available for additional explanations (each of the clients will provide their own contact person),

cooperation with contractors in communicating with landowners and the local community for the purposes of implementing test fields,

supervision of the implementation of the test fields, and

review and confirmation of the documentation.

Table 6 The client shall provide the contractor with the following documents and information

| Document / information: | Submission: |
| --- | --- |
| DPN with enclosures | After signing the contract |
| IDP from 2005 | After signing the contract |
| Revised IDP from 2012 | After signing the contract |
| Revised IDP prepared in 2024 | After signing the contract |
| Land survey plan with certificate from 2024 | After signing the contract |
| DPP and design guidelines | After signing the contract |
| Reports on geological and geomechanical investigations and, if necessary, the investigation samples (samples are available for inspection at the client's premises) | After signing the contract |
| Results of hydrogeological investigations (hydrogeological investigations are ongoing, therefore interim results will be submitted upon completion of the investigations, as well as the report and final results) | After signing the contract |
| Technical bases for EIA relevant to the storage basin and EIA | After signing the contract or as soon as they are completed |
| Input data from other designers: inlet/outlet structure with penstock structure of the surge tank vent with vent pipe local access roads connected to maintenance roads along the structure of the storage basin | Submitted after signing the contract and: after optimization is complete and the design of the inlet/outlet structure is confirmed approximate data in nIDP, more specific data and solutions provided by the DGD designer approximate input data provided by nIDP, more specific solutions will be provided in the PZI project documentation, which will be commissioned |

The documentation listed above in Table 6 will be made available to the contractor in electronic form on TEAMS/SharePoint portal. The contractor will be granted access to the portal with the specified content. The remaining documentation (legislation, regulations, standards, IZS professional rules, etc.) necessary for the performance of activities under this contract shall be obtained by the contractor itself.

SCHEDULE FOR THE PERFORMANCE OF SERVICES UNDER LOT 1

When preparing documentation in accordance with this ToR, the deadlines listed below must be observed.

| Item | Activity description | Deadline (months) |
| --- | --- | --- |
|  | Technical documentation for the construction of the storage basin |  |
|  | Review and analysis of existing documentation and status report | 1 after signing the contract |
|  | Preparation of documents with basic proposals for technical solutions, which shall be the subject of coordination | 6 after results of the test fields implementation |
|  | Documents of final coordinated technical solutions | 3 months after 1.2 |
|  | Support to the owner in implementing the test fields |  |
|  | Requirements for test field implementation (technical requirements for tender documentation) | 1 after signing the contract |
|  | Support during the test fields implementation | According to time schedule for test fields |

During the execution of the contract, the client reserves the right to change the schedule due to factors beyond its control. Due to the coordination of solutions with the designer for obtaining building permit, EIA author, and water resource owners, as well as participation in public presentations, the final deadline for the completion of all activities under this contract is May, 31st, 2027