DRAFT CONTRACT

for

Reactor Cavity Manipulator Crane Upgrade Project

hereinafter referred to as:

RCMC Upgrade Project

(Mod. 1302-FH-L)

Effective as of  _______________________  by and between:

NUKLEARNA ELEKTRARNA KRŠKO d.o.o.

Vrbina 12, 8270 Krško, Slovenia, 	
represented and duly authorized by Mr. Gorazd Pfeifer, President of the Management Board and Mr. Saša Medaković, Member of the Management Board

(hereinafter referred to as "PURCHASER" or "NEK" or "NPP Krško")

on one part

and

…………………………………………………………………………………………….

……………………………………………………………………………, represented and duly authorized by  …………………………………………………..

(hereinafter referred to as "SELLER" or “Contractor”)

on the other part

Whereas, SELLER represents that it is fully qualified to provide PURCHASER  with  the turnkey Project “Reactor Cavity Manipulator Crane Upgrade” and shall do so in accordance with the terms and conditions herein specified,

and

Whereas, the representatives of SELLER and PURCHASER possess proper and sufficient authority to agree, and

Now therefore, SELLER and PURCHASER have agreed as follows:

Subject of the Contract: Reactor Cavity Manipulator Crane Upgrade Project

The following documents shall constitute the Contract:

-  PART I: -  General Terms and Conditions (this Document)

- PART II: -  NEK Technical Specification No. SP-ES1454, Rev. 2 for

Reactor Cavity Manipulator Crane Upgrade Project

(hereinafter referred to as “SP-ES1454”) including all its

Appendices

-  PART III:  - Quotation  No. ……………

PART I - GENERAL TERMS AND CONDITIONS

# TABLE OF CONTENTS

TABLE OF CONTENTS	3

0	DEFINITIONS AND ABBREVIATIONS	4

1	SELLER'S SCOPE OF SERVICES AND DELIVERY	7

2	PURCHASER'S RESPONSIBILITIES	9

3	QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS	9

4	DELIVERABLES TO BE PROVIDED TO PURCHASER	9

5	SCHEDULE REQUIREMENTS	9

6	DELIVERY TERMS AND CONDITIONS	10

7	PRICE	10

8	PAYMENT TERMS AND SCHEDULE	11

9	INSPECTIONS, TESTS & HANDOVER PROTOCOL	13

10	LIQUIDATED DAMAGES	14

11	SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION	16

12	WARRANTY	17

13	T A X E S	19

14	LICENSES, PERMITS AND AUTHORIZATIONS	20

15	INSURANCE AND INDEMNITY	21

16	LIABILITY	22

17	PROPRIETARY INFORMATION	23

18     CLAIMS	24

19     ARBITRATION	25

20     SUBSTANTIVE LAW	25

21     FORCE MAJEURE	25

22     SUSPENSION OF WORK AND TERMINATION	27

23    CHANGES	30

24     ANTI-CORRUPTION CLAUSE	31

25     SOCIAL CLAUSE	32

26     OTHER PROVISIONS	32

27     ASSIGNMENT	35

28     ENTIRE AGREEMENT	35

29    LANGUAGE	35

30     EFFECTIVE DATE OF CONTRACT	36

31    NOTICES	36

32   ATTACHMENTS	37

# DEFINITIONS AND ABBREVIATIONS

As used throughout the Contract, the following terms shall have the meaning set forth hereinafter:

PURCHASER shall mean NUKLEARNA ELEKTRARNA KRŠKO (NPP Krško), Vrbina 12, 8270 Krško, Slovenia, represented by Mr. Gorazd Pfeifer, President of the Management Board and Mr. Saša Medaković, Member of the Management Board.

SELLER or CONTRACTOR shall mean

………………………………………………………………………………………

……………………………………………………………………………………….represented by ……………………………………………………………………..

PARTY or PARTIES shall mean PURCHASER or/and SELLER as herein referred to individually or collectively.

CONTRACT shall mean the agreement between PURCHASER and SELLER consisting of General Terms and Conditions of the Contract (PART I), NEK Technical Specification SP-ES1454, Rev.2 (PART II) and Quotation No. ………………

The Contract documents are complementary, and what is called for by anyone of them shall be binding as if called for by all. Any conflicts in the Contract documents shall be reasonably resolved by PURCHASER after mutual discussion with SELLER. The validity dates of documents and any data listed in this Contract shall commence with the effective date of the Contract.

SCOPE OF SERVICES AND DELIVERY or WORK shall mean all engineering and design, licensing support, procurement and supply of all equipment and material, installation and installation supervision, commissioning of RCMC Upgrade Project and all other requirements set forth in or necessary to perform the Contract for RCMC Upgrade Project.

PROJECT shall mean all activities requested by SP-ES1454, Rev. 2 i.e. by

this Contract.

PROJECT MANAGERS shall mean the PURCHASER’s and the SELLER’s designated representatives through whom all technical, commercial, Quality Assurance and Licensing matters shall be channeled.

COMMERCIAL REPRESENTATIVES shall mean the PURCHASER’s and the SELLER’s designated representatives through whom commercial matters will be evaluated.

SP-ES1454 shall mean NEK Technical Specification SP-ES1454, Rev. 2 for RCMC Upgrade Project including NEK Equipment Specification No. 677055A, Rev. 0 for Refueling Machine Upgrade and all other Appendices, with all design, technical, engineering, QA and other requirements incorporated.

SP No.677055A shall mean NEK Equipment Specification No. 677055A, Rev. 0 for Refueling Machine Upgrade which is an integral part (Appendix 1) of SP-ES1454.

QUOTATION shall mean SELLER’s Quotation No.: …………… dated ……………..

PLANT, SITE, NE Krško, NEK, NPP Krško shall mean Nuclear Power Plant Krško.

SITE shall mean and include the area of the Plant and its adjacent areas necessary and relevant to the operation of the Plant.

APPROVED shall mean the status of any document to be furnished by the SELLER to PURCHASER under Contract which is approved by PURCHASER with or without comments but which is not rejected by PURCHASER. The date for the resolution of PURCHASER’s comments shall be mutually agreed upon prior to the approval. In no circumstances the approval can relieve SELLER from the responsibility for failures within SELLER’s Scope of Services and Delivery.

FIXED AND FIRM TOTAL CONTRACT PRICE shall mean all-inclusive total price to be paid to SELLER as per Article 7.1 of the Contract.

HARDWARE shall mean all equipment, spare parts, consumables and materials together with required software needed for the completion of the Project and as defined in the contractual documents.

REACTOR CAVITY MANIPULATOR CRANE or REFUELING MACHINE shall mean the equipment to be manufactured fully in accordance with SP No. 677055A.

SERVICE shall mean all the activities to be performed to fulfill all requirements as per SP-ES1454.

ALARA shall mean As Low as Reasonably Achievable.

ASL shall mean Approved Suppliers List

BOM shall mean Bill of Material

DAT shall mean Delivered at Terminal NPP Krško Site as per Incoterms 2020

DMP shall mean Design Modification Package

ESD shall mean Engineering Service Division

FAT shall mean Factory Acceptance Testing

HOP shall mean Handover Protocol

IP shall mean Installation Package

PMM shall mean Project Management Manual

PQP shall mean Project Quality Plan

RCMC shall mean Reactor Cavity Manipulator Crane

QA shall mean Quality Assurance

SAT shall mean Site Acceptance Testing

SNSA shall mean Slovenian Nuclear Safety Administrator

TOP shall mean Turn-Over Package

VAT shall mean Value Added Tax

ZVISJV shall mean Zakon o varstvu pred ionizirajočimi sevanji in

Jedrski varnosti (Radiation Protection and Nuclear Safety Act).

# SELLER'S SCOPE OF SERVICES AND DELIVERY

SELLER shall perform on a turnkey basis the RCMC Upgrade Project fully in accordance with NEK Technical Specification SP-ES1454, Rev. 2, including all its Appendices, and other contractual documents.

Turnkey principle

SELLER shall perform all engineering, necessary to develop modification packages, components dismantling, installation and modification work including the supply of all necessary hardware all in accordance with the agreed upon SP-ES1454 and provisions of this Contract. SELLER shall be responsible, in compliance with the requirements of SP-ES1454 and all referenced documents including PURCHASER’s relevant procedures, listed in SP-ES1454, for the detailed design, product quality assurance, materials procurement, fabrication, testing, certification, code stamping prior to shipping, examination, inspection, receiving inspection, and pre-service inspection, cleaning.

Any hardware, software or services not specially included in the Contract shall be deemed to be included in SELLER’s undertaking if their inclusion is required to make the hardware supplied physically or functionally complete meeting all performance criteria in accordance with SP-ES1454 and this Contract.

All modification packages will comply with the codes and standards approved for use by PURCHASER, affecting the scope of work to be performed.

During engineering and design the SELLER will check the as-built status for all important locations.

SELLER will develop and provide all necessary construction activities (procedures, organization, material handling, rigging and transportation, erection, quality assurance/quality control, welding, painting/coating, insulation) when required by the SP-ES1454.

SELLER shall be responsible for installing turnkey supplied Hardware so that it is complete with the existing piping and structural support system in accordance with SP-ES1454 and other contractual documents.

SELLER shall be responsible for developing and providing to PURCHASER  all documentation, drawings, equipment lists, schedules, stress analyses, seismic analyses and other documents necessary for the dismantling of hardware to be replaced and the installation, assistance to licensing, and operation of supplied Hardware as required by the SP-ES1454.

Transfer of title and risk of loss shall pass from SELLER to PURCHASER upon the Handover Protocol signature (Attachment C) by both the Parties.

SELLER’s Responsibility

SELLER's Scope of Services and Delivery shall be completed in a way which will achieve and meet all performance criteria according to SP-ES1454 and other requirements of contractual documentation.

Nothing shall relieve SELLER of the responsibility to perform analyses, tests, inspections and other activities that through the process become necessary to ensure that the design and materials, as well as the product quality, shall meet the requirements in accordance with the contractual documents.

SELLER shall be responsible for compliance with all detailed requirements of SP-ES1454 its referenced documents and other contractual documents.

Subcontractors

For a part of the Scope of Services and Delivery SELLER may engage the subcontractors which have been listed in the Quotation and accepted by PURCHASER. If SELLER upon signature of this Contract wants to change or select new subcontractor(s), this shall be subject to PURCHASER approval, which shall not be unreasonably withheld. Based on the law of ZVISJV (Act on Protection against Ionizing Radiation and Nuclear Safety) and based on “Pravilnik o dejavnikih sevalne in jedrske varnosti (JV 5)” Article 67, PURCHASER is responsible for establishing surveillance on SELLER and its subcontractors to ensure high quality and nuclear safety for the public.

SELLER shall ensure that all subcontractors meet high standards of competence, experience and capacity in relation to the tasks to be entrusted to them and that they fully comply with the SP-ES1454 requirements and the contractual documents.

Since SELLER retains full responsibility for all aspects of subcontractors performance including quality and schedule, SELLER shall ensure that adequate periodic audit and surveillance of the subcontractors is maintained. SELLER shall identify to all subcontractors all applicable Quality Assurance and Quality Control requirements imposed by PURCHASER’s specifications on SELLER and shall ensure compliance thereto. All subcontractors shall be on SELLER’s Approved Suppliers List. NEK’s right of access to SELLER’s subcontractors’ facilities for the purpose of inspection or audit shall be imposed by SELLER’s documents.

During the engineering phase of the Project, SELLER shall engage qualified companies with a proven experience record of the development of Design Modification Packages in accordance with NEK procedures.

Such qualified companies (subcontractors) shall ensure support in the engineering phase and installation and support phase response time less than eight (8) hours to ensure timely preparation and processing of potential FDCR (Field Design Change Request) per NEK ESP-2.609 procedure, provided that “response time” shall not mean “resolution time”.

SELLER shall not subcontract any portion of the Work without the written approval of PURCHASER Responsible Engineer, which shall not be unreasonably withheld. The absence of any reply from the PURCHASER within three (3) weeks is considered as approval under the condition that SELLER sends prior notification to PURCHASER within two weeks. Subcontractors performing augmented quality service will need to have either quality assurance program approved by PURCHASER or work in conjunction with SELLER Quality Assurance Program.

Full overall responsibility always remains on SELLER’s side concerning participation of SELLER’s subcontractors.

# PURCHASER'S RESPONSIBILITIES

PURCHASER’s responsibilities are defined in SP-ES1454, Section 36.

# QUALITY ASSURANCE, TECHNICAL AND OTHER REQUIREMENTS

SELLER shall meet all quality assurance requirements, design, engineering, and technical requirements as well as procedures, codes and standards as stated in SP-ES1454.

# DELIVERABLES TO BE PROVIDED TO PURCHASER

SELLER shall submit to PURCHASER all deliverables as stated in SP-ES1454 and other contractual documents

# SCHEDULE REQUIREMENTS

Overall Project Schedule is given in Attachment A to this Contract.

Main Schedule Completion Milestones are given in the Table below:

| Item | Description | Delivery schedule |
| --- | --- | --- |
| 1. | PMM and PQP submitted to NEK | July 2026 |
| 2. | Design inputs submitted to NEK | August 2026 |
| 3. | Submittal of Final DMP with 10CFR50.59 package (version approved by Purchaser) | April 2027 |
| 4. | Technical Procurement Specifications for major equipment as per Section 11.3.8 of SP-ES1454 submitted to NEK | April 2027 |
| 5. | Manufacturing Work Sequence and Inspection Plan submitted to NEK | April 2027 |
| 6. | Outage 2027 Walkdown | April 2027 |
| 7. | Site Installation Package submitted to NEK | March 2028 |
| 8. | Successfully performed FAT and submittal of Test Reports | June 2028 |
| 9. | Instruction Manuals submitted to NEK | July 2028 |
| 10. | Delivery of Refueling Machine and material and tools needed for installation activities to NEK | August 31, 2028 |
| 11. | Demolition of the existing RCMC, installation of the new RCMC and successful SAT completion | October 2028 (within …….… (max 9) days) |
| 12. | Installation Report submitted to NEK | November 2028 |
| 13. | TOP submitted to NEK | January 2029 |
| 14. | Fuel unloading support | April 2030 |

# DELIVERY TERMS AND CONDITIONS

Equipment, spare parts, material and all other deliverables of SELLER’s Scope of Services and Delivery as stated in Art. 1 above shall be delivered DAT NPP Krško Site as per Incoterms 2020 provided that the transfer of title and risk of loss shall pass from SELLER to PURCHASER upon the Handover Protocol (Attachment D) signature by both Parties.

Delivery of shipping documents

As soon as possible, but not later than on three (3) days before the day of delivery of goods, in order to ensure timely receipt and customs clearance, SELLER or its forwarding agent shall send to PURCHASER the following information and documents:

- estimated time of arrival of shipment at NEK site

- shipping invoice with description of goods, quantity, unit and total price per each item and total price

- packing list

- copy of AWB or RWB or B/L, etc. (relative to means of transportation)

Temporary Import to NPP Krško site

SELLER shall (providing and using its Carnet A.T.A., if applicable) organize and perform at its cost all transportation and insurance of all temporarily imported equipment, instruments, material, etc. necessary to perform SELLER’s Scope of Services and Delivery under this Contract to NPP Krško site, return from NEK site and insurance of them also during the stay at NEK site.

Title and risk of loss/or damage to such temporarily imported equipment, tools, etc. shall remain all time with SELLER.

# PRICE

7.1     The all-inclusive Total Fixed and Firm Contract Price for the Base Scope of Services and Delivery as per Art. 1 above under the terms and conditions of this Contract is:

EUR …………………… (excl. V.A.T.)

(in words:……………………………………………………… Euros)

All labor, materials, equipment, parts, components, and services like engineering and documentation, as well as living, traveling and similar costs of SELLER's personnel, etc. necessary for SELLER to fulfill its obligations as stated in Art. 1 of this Contract are included in the above Fixed and Firm Total Contract Price.

7.2   The Price Structure for the Base Scope is given below:

| Item | Scope of Services and Delivery | Fixed price in EUR (excl. VAT) |
| --- | --- | --- |
| 1 | Project management, administration, training |  |
| 2 | Design & Engineering |  |
| 3 | Procurement & Manufacturing |  |
| 4 | Demolition, Installation & Commissioning |  |
| 5 | Post installation support (outage October 2028 and April 2030) |  |
| 6 | Transportation DAT NPP Krško |  |
|  | TOTAL (1-6) |  |
|  | Portion of subcontractors’ price in services |  |
|  | Portion of subcontractors’ price in hardware |  |
|  | Mark-up for subcontractors’ scope of work (%) |  |

*Note: The prices under 1 through 6 already include here provided Contractor’s mark-up value for subcontractors’ scope of work as well as subcontractors’ price portion.

# PAYMENT TERMS AND SCHEDULE

8.1.	Payment terms

All payments under this Contract will be made by means of a bank transfer, net due thirty (30) days upon PURCHASER approval of the received invoice. The invoice shall be approved or rejected within 15 days from the receipt. If the invoice is not rejected within 15 days from the receipt, it is considered to be approved.

Payment instalments:

Payment will be made against commercial invoices, upon receipt of 	deliverables as described in the table provided below:

| Item | Description of Payment Milestones |  | Payment Amount (% of Fixed and Firm Total Contract Price) |
| --- | --- | --- | --- |
|  | PMM and PQP approved by NEK |  | 5 |
|  | Design inputs approved by NEK |  | 5 |
|  | Final DMP approved by NEK |  | 10 |
|  | Technical Procurement Specifications for major equipment as per Section 11.3.8 of SP-ES1454 submitted to NEK |  | 5 |
|  | Site Installation Package approved by NEK |  | 5 |
|  | Successfully performed Factory Acceptance Test (FAT) and submittal of Test Reports |  | 10 |
|  | Delivery of Refueling Machine and material and tools needed for installation activities |  | 15 |
|  | Demolition of existing RCMC, installation of new RCMC and HOP signed after successfully performed SAT, against submittal of Warranty Bond/Guarantee |  | 30 |
|  | Turn over package (TOP) approved by NEK |  | 10 |
|  | All warranty issues/claims resolved/closed and outage 2030 unloading support completed |  | 5 |
|  |  | SUM | 100 |  |

If SELLER engages the subcontractor(s) who wants to be paid directly and they submit the signed »Subcontractor’s Data and Bidder’s Consent for Direct Payment« as per Attachment D, NEK is obliged to pay the subcontractor directly.

Besides the invoice submitted by SELLER to PURCHASER with total amount of the payment due including the value of subcontractor work specified separately, SELLER shall also approve and submit the invoice of its subcontractors for each payment milestone.

SELLER authorizes PURCHASER to make direct payments to the subcontractors for their services and supplies, based on the approved invoices addressed to SELLER.

If a subcontractor is replaced after the conclusion of the Contract or if the SELLER concludes a contract with a new subcontractor which is subject to direct payment, the SELLER that concluded the Contract with the PURCHASER must submit to the latter, within 5 days of change the following:

- statement that all non-disputed liabilities have been settled to the original

subcontractor;

- authorization for the payment of provided and delivered work or products

directly to the new subcontractor, and

- consent of the new subcontractor to the acceptance of direct payment

In case that the subcontractors are not paid directly by PURCHASER, SELLER and subcontractor shall submit a Statement of performed payment to subcontractor within sixty (60) days after the Project completion as per Attachment G.

8.2	Guarantees

The Bank Good Performance Guarantee to the amount of 10% of the Fixed and Firm Total Contract Price as per Art. 7.1, in the form and content according to Attachment A, shall be submitted to PURCHASER not later than thirty (30) days after the Contract signature with a validity of 30 days upon signature of the Handover Protocol. The validity of the Bank Good Performance Guarantee shall be extended, if needed.

If SELLER fails to perform its contractual obligations as to the quantity, quality and schedule, due to reasons attributable to SELLER, PURCHASER shall be entitled to call for the Good Performance Guarantee up to its total amount. PURCHASER shall notify SELLER of disputed contractual obligations and its intent to call for the Guarantee.

The Warranty Bond/Guarantee to the amount of 5% of the Fixed and Firm Total Contract Price (see Art. 7.1) shall be submitted to PURCHASER in the form and content according to Attachment B with a validity of 30 days after the end of the warranty period as stated in Art. 12.3 below.

If SELLER does not fulfill its obligations under Art. 12 within reasonable mutually agreed period of time in no case exceeding the warranty period as stated in Art.12.3, PURCHASER is then entitled to call for the Warranty Bond/Guarantee issued by SELLER’s bank up to its total amount. PURCHASER shall notify SELLER of disputed contractual obligations and its intent to call for the Guarantee.

All here above-mentioned Guarantees shall be issued at SELLER’s cost by a first-class bank and shall be returned by PURCHASER to SELLER on their date of expiry.

# INSPECTIONS, TESTS & HANDOVER PROTOCOL

All tests and inspections shall be performed in accordance with SP-ES1454.

After successful completion of the Project the Parties, SELLER and PURCHASER, shall sign the Handover Protocol as per Attachment C if no significant faults are counteracting. Minor remaining issues such as open Project deficiencies reports of category C and D to be taken care of by SELLER or PURCHASER shall be registered in the Handover Protocol and the signing of the Handover Protocol shall not be withheld for such minor remaining issues

The prerequisites to sign the Handover Protocol are successfully performed Site Acceptance Tests with completed resolution of all open items (non-conformances and deficiency reports category A and B) and NEK receipt of Test Reports.

The Parties shall sign the Handover Protocol within ten (10) days after the preconditions in the previous paragraph are fulfilled. The protocol shall include at least:

(i)	statement that the requirements of Article 9 have been met;

(ii)	a list of all open Project deficiencies reports of category C and D. No open deficiencies category A and B (as defined in PMM) are allowed.

Signing of the Handover Protocol does not interfere with the rights of PURCHASER related to warranty for hidden defects for which SELLER is responsible.

# LIQUIDATED DAMAGES

10. 1   Liquidated Damages for Delay

In case of delay in completion of the milestones as defined in Article 5 of the Contract, due to reasons solely attributable to SELLER, SELLER shall pay to PURCHASER liquidated damages as follows:

- 20.000 € per week of delay in completion of Item 3. (Submittal of Final DMP to PURCHASER) as stated in Article 5, starting after the first day of delay,

- 20.000 € per week of delay in completion of Item 7 (Submittal of Final Installation Package to PURCHASER) as stated in Article 5, starting after the first day of delay

- 40.000 € per hour of delay in completion of Item 11 (Demolition of the existing RCMC, installation of the new RCMC and successful SAT completion) as stated in Article 5, starting after the first hour of delay.

Liquidated damages for delay as set forth above shall not exceed, in aggregate 15 % of the Fixed and Firm Total Contract Price set forth in Article 7.1.

- 10.2    Liquidated Damages for Underperformance

10.2.1 Functionalities of RCMC

All functionalities of RCMC, safety features and interfaces shall meet requirements defined in SP-ES1454 resulting in no delays associated with RCMC operability during nuclear fuel loading in outage 2028 and unloading in outage 2030.

In a case that, after the SAT, inoperability of RCMC causes a delay during nuclear fuel reloading in outage 2028 or unloading in outage 2030, SELLER shall pay liquidated damages for performance to the amount of 40.000 € per each hour of the attributable delay.

10.2.2 Use of Servomotors for Bridge and Trolley Drives & Provision of Documents

SELLER warrants to PURCHASER the following:

- Use of servomotors for bridge and trolley drives (encircle applicable):

- Yes

- No

- Provision of documents to NEK as defined in Section 11.3 of SP-ES1454 (encircle applicable):

- Provision of all documents subject to or generated for the project without any restrictions other than restrictions stipulated in 17.2 of this Contract

- Provision of all documents in accordance with the previous paragraph, with additional restrictions that the full content of 11.3.6.1, 11.3.8, 11.3.9, 11.3.14 d,e,y,z may only be observed at Contractor’s facilities

- Provision of all documents in accordance with the previous paragraph with additional restrictions to the above

If SELLER fails to achieve the warranted performance(s) as given above, the Fixed and Firm Total Contract Price shall be reduced, in respect of the performance value not met, by the same percentage achieved during evaluation of the bid for the relevant warranted performance(s).

Total liquidated damages with respect to the failure in performance as set forth above (Art. 10.2.1 & 10.2.2) shall be limited to 10% of the Fixed and Firm Total Contract Price as per Article 7.1.

Total liquidated damages as set forth above per Art. 10.1 and 10.2 shall be limited to 25% of the Fixed and Firm Total Contract Price as per Article 7.1.

10.3    Liquidated Damages for Violation of Occupational Safety and Health

(OSH), Fire Safety (FS) and Foreign Material Exclusion (FME) Rules and Regulations

PURCHASER may demand payment of a contractual penalty if SELLER violates contractual obligations by:

- violating the legislation and requirements of the Krško NPP in the area of occupational safety and health (OSH), fire safety (FS) and Krško NPP procedures,

- violating the provisions of the safety plan and the instructions of the safety and health at work coordinator for the work execution phase in accordance with the Decree on ensuring safety and health at work on temporary and mobile construction sites, (Official Gazette of the Republic of Slovenia, No. 83/2005),

- work suspension due to serious violations of OSH measures (endangering the life and health of workers)

based on violations of OSH and FS requirements recorded by the person in charge of PURCHASER's Safety at Work, project manager, work supervisor, head of department, head of unit, sector director…), repeated violations in the book of measures from OSH at the construction site and entered in the minutes of the coordination meeting or the violation recorded in the request of the corrective program (ZKP) on the basis of which the request of the Occupational Safety and Health at Work Department the request for the calculation of the contractual penalty is given.

The amount of the penalty for each individual deviation from the above is EUR 10,000 per breach and is not included in other contractual penalties. Prior to being penalized for the first time SELLR shall be given a written warning. In the case of repeated individual violations, the multiples of the above penalties will be charged (eg 2 x violation = 2 x penalty, 3 x violation = 3 x penalty, etc.). The cumulative liquidated damages pertaining to breaches of OSH, FS, and FME rules per this Article 10.3 shall not exceed the Total Price stipulated in this Contract.

PURCHASER reserves the right to permanently remove the worker who does not comply with the rules of OSH and FS from the Site.

PURCHASER has the right to withdraw from the contract due to the violations of the provisions of OSH and FS on the part of the contractor.

Violation of the provisions of OSH and FS may also be a reason for the bid impermissibility and the exclusion of the contractor from future procurement processes.

Any extension of the contractual deadlines, price increase or claims for damages due to the suspension of works for the above reasons are not permitted.

# SAFETY AND HEALTH AT WORK AND PROTECTION AGAINST IONIZING RADIATION

In order to ensure safety and health at work, SELLER shall follow the provisions of the Law on Safety and Health at Work (Official Gazette of RS No. 43/11), ADP procedure 1.1.033 Safety and Health at Work at NPP Krško and in compliance with provisions of a separate written Agreement concluded in accordance with Article 39 of the Law on Safety and Health at Work of the Republic of Slovenia.

SELLER shall make sure that the performance of Work is in accordance with internal procedures and instructions issued by the responsible PURCHASER’s employees.

In order to fulfill the provisions of the Act on Protection against Ionizing Radiation and Nuclear Safety, the contractual parties shall adhere to the Agreement on Protection against Ionizing Radiation (applicable for suppliers performing services in the controlled area). Based on the provisions of this Agreement, SELLER shall provide all necessary data and signed statements of workers by which they allow transferring the information on their personal dose rates for further use.

SELLER shall test his subcontractor workers on their knowledge of safety rules and document such in-house testing by signing Statement on complying with Act on Ionizing Radiation Protection and Nuclear Safety.

SELLER who employing simultaneously more than 15 workers on Site (per one Purchase Order/Contract or more Purchase Orders) or performing high risk works shall nominate and ensure the presence of a safety at work expert depending on the number of workers and the degree of the worker(s) safety risk exposure.

The criteria for temporary Site presence of the safety at work expert are as follows:

- 15 – 30 workers               1 day/week

- 31 – 50 workers               2 days/week

- 51 – 80 workers               3 days/week

- 81 – 150 workers            permanent presence

- ˃ 150 workers                  ˃ 2 workers/permanent presence

NOTE: The above numbers do not include permanently hired staff

Should PURCHASER learn that SELLER has not fulfilled relevant above criterion, within 3 working days PURCHASER will invite him in writing (by e-mail, mail) to do it. The Site presence of the required safety at work expert on the day following the receipt of the above invitation will be considered as a fulfillment of the above criterion.  If SELLER does not comply with the above criterion, SELLER shall pay liquidated damages for violation of Safety at Work rules (as per Contract article No. 10.3) i.e. 1000€ for each day of non compliance.

One week before the beginning of Site works as a minimum, the Contractor shall submit to PURCHASER a list containing the details on safety at work expert  presence on Site. In case of doubt in the level of risk associated with the works to be performed and resulting demand for safety expert Site presence, the Contractor may contact directly Mr. Rudi Janežič (e-mail: rudi.janezic@nek.si )

In order to fulfill the provisions of the Act on Protection against Ionizing Radiation and Nuclear Safety, the contractual parties shall adhere to the Agreement on Protection against Ionizing Radiation (applicable for suppliers performing services in the controlled area). Based on the provisions of this Agreement, SELLER shall provide all necessary data and signed statements of workers by which they allow transferring the information on their personal dose rates for further use.

The contractual works shall be carried out in compliance with legislative requirements, prescribed standards, and technical regulations, with the aim of meeting the requirements of the environmental management system in accordance with ISO 14001. For waste generated as a result of  SELLER's work under the contract, PURCHASER shall provide the possibility for sorting and temporary storage of waste (at the construction site or worksite). SELLER shall ensure the transport of waste to the final disposal site and obtain the appropriate documentation for the handover of waste.

# WARRANTY

12.1	SELLER warrants that all the Hardware furnished under this Contract shall be new and free from liens, encumbrances and defects in title and shall be free from defects in design, workmanship and material and that the Hardware delivered under this Contract shall achieve the design, performance and functional requirements as stipulated in SP-ES1454 i.e. in this Contract. Approval of designs, drawings, samples, test results, suppliers and schedules by PURCHASER shall not in any way limit or diminish the SELLER’s warranties hereunder.

12.2	SELLER warrants that all services he provides shall be in full conformity with the Contract; shall comply with all applicable codes, standards, laws, rules, and regulations; shall be performed in a highly professional and workmanlike manner which would be exercised by those who perform similar services at the time the  services are performed and shall be free from defects in design, material and workmanship; shall conform to applicable specifications, and shall be free from all liens and encumbrances and shall achieve the design, performance and functional requirements as stipulated in SP-ES1454 i.e. in  this Contract. Warranties shall survive acceptance or payment for any and all services required pursuant hereto but shall end with the elapse of the pertinent warranty period as per Article 12.3

12.3	The warranty mentioned in paragraph 12.1 and/or 12.2 above shall be for the period of …………years (min. four and a half (4,5) years) starting from the date the Handover Protocol is signed by both Parties. The Contract shall remain in effect until the expiration of the warranty period.

12.4	SELLER shall remedy at his own cost all faults and hardware and software deficiencies other than normal wear and tear or faults or deficiencies not attributable to PURCHASER detected and reported in writing claim to SELLER by PURCHASER provided that such PURCHASER’s claim has been received by SELLER within the warranty period. The reporting shall be made within thirty (30) days after the detection of the fault or deficiency. The remedy shall be made by (i) replacement or repair of the faulty or deficient unit (spare part or equipment) at SELLER’s option approved by PURCHASER, such approval being not unreasonably withheld, and within shortest reasonable period of time to be determined between the Parties or (ii) repeat of the defective services.

SELLER’s obligations to remedy faults or deficiencies under the warranty shall be deemed to have been fulfilled when SELLER has either made the remedy at the Site or delivered and installed the replacement unit to PURCHASER and PUCHASER has inspected and accepted it. A refusal shall be for justified reasons only. SELLER shall pay the transportation and insurance cost from Krško Site to the designated facility and back to DAT Krško Site.

A fresh warranty period shall commence for the repaired or replaced Hardware or the repeated services. The duration of this new warranty must last for the remaining duration of the original warranty as stated in Art 12.3. above or extend for a minimum of 2 years after the completion of the remedy, whichever of these durations is longer. However, SELLER will no longer have any warranty obligations after the sum of years calculated as the total of the original warranty period specified in Art. 12.3 plus the duration of the fresh warranty, following the start date of the warranty period as stated in Art. 12.3 above.

12.5	If SELLER does not fulfill his obligations under Article 12.4 above within a mutually agreed upon period of time, PURCHASER shall be entitled to correct the defective pieces of Hardware or services at the expense of SELLER provided that such expense shall not exceed the price of the new above defective pieces/services as reasonably evaluated by PURCHASER and SELLER on the basis of the current international market prices.

12.6	If it becomes necessary for SELLER to repair or provide replacement Hardware under these warranties, PURCHASER, without cost to SELLER, shall, to the extent necessary for SELLER to perform its warranty obligations, (i) provide reasonable access to the defective part(s) 
(ii) make available to SELLER, PURCHASER's facilities, equipment and tools available on Site, and (iii) perform any necessary decontamination.

12.7   SELLER is obliged to ensure the delivery of required repair/remedy services, replacement parts and software upgrades for the period of at least 20 (twenty) years following the expiration of Warranty Period. SELLER shall be entitled to appropriate remuneration in accordance with SELLER's standard rates.

In case SELLER does not fulfill its above said obligation, SELLER shall reimburse NEK for all the costs of engineering services done in order to modify the Hardware due to SELLER’s inability to provide required original spare parts and/or repair services.

Following the 20-years period after the expiration of the contractual Warranty Period, if the replacement parts are not available, the Purchaser and Seller will discuss and agree an alternative solution involving the provision of adequate replacement parts at SELLER standard prices.

12.8	The express warranties and remedies set forth in this Article 12 shall constitute the sole and exclusive warranties, guarantees and remedies made to the PURCHASER and are exclusive and in lieu of all other warranties, guarantees and remedies of any kind. Any further rights and claims arising from warranty are excluded except as provided under Article 16.1.

# T A X E S

  - SELLER shall be responsible for the payment of all taxes, duties, tariffs, fees  and other like charges of SELLER arising from or in connection with the subject  matter of the Contract except for taxes stated in Art. 13.4 below.

  - SELLER shall register with Slovenian Taxing Authorities and obtain Slovenian VAT ID Number. In that case SELLER's invoices to PURCHASER shall include Slovenian VAT. SELLER is responsible for calculation and payment of Slovenian VAT according to the Slovenian VAT Act. In no case shall SELLER impose his Slovenian subcontractors VAT in his invoices to PURCHASER.

  - If SELLER does not register with the Slovenian Taxing Authorities and has   no Slovenian VAT ID Number, PURCHASER will pay VAT and apply »Reverse Charge according to Article 196 Council Directive 2006/112/EC as amended by Council Directive 2008/8EG.

  - PURCHASER shall be responsible only for the payment of Slovenian import

## customs duties (payable at Slovenian border) and relevant Slovenian V.A.T.

# LICENSES, PERMITS AND AUTHORIZATIONS

14.1	If required, SELLER shall assist PURCHASER in all its own dealings with the Government Agencies, Licensing Bodies/Authorities and independent inspection agencies in Slovenia. This shall be limited to assistance in obtaining and maintaining licenses, permits and authorizations that may be required for SELLER’s performance under the Contract. To the extent requested, SELLER shall make any necessary presentations to, participate in meetings with, and furnish required information to the competent Slovenian authorities.

SELLER shall be responsible for all dealings with Government Agencies outside Slovenia. This shall include but not necessarily be limited to obtaining, maintaining and paying for licenses, permits and authorizations that may be required for SELLER’s performance under this Contract concerning manufacturing, export and transportation of Hardware within SELLER’s Scope of Services and Delivery.

14.2	Licensability

SELLER shall make sure that the design of the Hardware supplied as far as the SELLER’s Scope of Services and Delivery is concerned meets the applicable licensing standards existing in Slovenia at the time of Contract signature and defined in SP-ES1454.

PURCHASER shall be responsible for any and all licensing activities related to the Hardware with necessary support of the SELLER as defined hereabove.

# INSURANCE AND INDEMNITY

PURCHASER’s Insurance at PURCHASER’s Cost

PURCHASER represents that it is the responsible operator of the Plant. Therefore, in no event and under no circumstances shall SELLER, its subcontractor, suppliers, directors, agents and the personnel employed by any of them, (hereinafter collectively referred to as the “Indemnified Parties”), irrespective of their activities under this Contract be considered as being the nuclear operator of the Krško Nuclear Power Plant. For its own protection and the protection of the Indemnified Parties, the PURCHASER has in effect and shall maintain in force Material Damage Insurance Policy including machinery break down covering also nuclear and fire perils, and Third Party Liability Insurance Policy against liability and risks arising out of or resulting from a Nuclear Incident (as defined in the Convention on Third Party Liability in the Field of Nuclear Energy of 29th July 1960, as amended by the Additional Protocol of 28th January 1964,  by the Protocol of 16th November 1982 and by the Protocol of 12th February 2004 - the Paris Convention) provided in accordance with Slovenian Nuclear Liability Legislation and available within the Slovenian Insurance Market.

SELLER’s Insurance at SELLER’s Cost

Equipment Insurance. SELLER shall procure and maintain in full force and effect, until their removal, insurance of SELLER’s materials, equipment, tools and other objects on Site.

Liability Insurance. SELLER shall procure and maintain in full force and effect until leaving the Site insurance against damage to or loss of the property of PURCHASER and damage or loss and injury to third parties (including without limitation PURCHASER’s subcontractor and suppliers and its or their employees), occasioned by any negligent act or omission of SELLER, its subcontractor and suppliers and its and their employees.

Scope of Services and Delivery Insurance. SELLER shall procure and maintain in full force and effect until leaving the Site insurance of the Scope of Services and Delivery for its full replacement value insofar as it relates to equipment and material, at any time against damage or loss howsoever caused. PURCHASER shall be a named insured under such insurance. Any proceeds under such insurance shall be applied towards the repair or replacement of any part of the Scope of Services and Delivery damaged or lost.

Personnel Insurance. SELLER in respect of all personnel employed by SELLER and its subcontractor for work on Site shall procure and maintain such insurance against occupational injury as is lawfully required from employers in the relevant jurisdiction(s).

Insurance arranged in pursuance of the above Articles shall be with a recognized international insurer. SELLER upon request shall submit to PURCHASER certificates of the insurance policies.

# LIABILITY

SELLER's Liability and Indemnity. SELLER shall be liable in respect of, and hereby agrees to indemnify and hold PURCHASER and its subcontractor and all of its or their officers, agents, servants and employees ("Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of PURCHASER and of damage to the property of, and injury (including death) to, any third party (such term including employees of PURCHASER's and SELLER's subcontractor and suppliers of any tier) to the extent that such claim, loss, damage, liability or expense arises out of or results from acts or omissions attributable to SELLER, its subcontractor and suppliers of any tier and their respective directors, officers, agents, servants or employees during their performance of the Work or from defects in design, workmanship and material of the Scope of Services and Delivery.

PURCHASER’s Liability and Indemnity. PURCHASER shall be liable in respect of, and hereby agrees to indemnify and hold SELLER, its subcontractor and suppliers and all of its or their directors, officers, agents, servants and employees (hereinafter referred to as the "Indemnitee") harmless from any claim, loss, damage, liability or expense on account of damage to the property of and/or injury (including death) to the Indemnitee or any third party which arises out of or results from acts or omissions attributable to PURCHASER or its subcontractors, or any of its or their respective directors, officers, agents, servants or employees.

The Indemnified Parties as defined in Article 16.1 shall in no event be liable with respect to any loss of, damage to property and/or injury (including death), caused by or resulting from a Nuclear Incident and PURCHASER shall indemnify, hold harmless and waive any and all claims and rights of recourse against SELLER.

Definition. For purposes of this Contract, "Nuclear Incident" shall have the meaning assigned to it by the Paris Convention on Third Party Liability in the field of Nuclear Energy of 1960 as amended by the Protocol of 1964, 1982 and 2004.

A party to the Contract who employs a subcontractor to perform its obligations under the Contract shall be liable to the other party, as for its own actions, for the non-performance or improper performance of the party’s obligations by the subcontractor.

Damages, to which parties to the Contract are entitled in accordance therewith, shall be paid against the indemnified party’s invoice thirty (30) days net. If SELLER fails to pay damages in accordance with the Contract against said PURCHASER’s invoice, PURCHASER is entitled to demand the payment out of the guarantee valid at that time SELLER’s Bank Good Performance Guarantee or Warranty Bond/Guarantee.

The total and cumulative liability of the SELLER, including any claim, warranty, cost and expenses of any kind arising out of or resulting from any cause whatsoever, whether based on contract, tort (including negligence), strict liability or otherwise shall in no event exceed 100% of the Total Contract Price. In no event and under no circumstances shall SELLER and PURCHASER be liable for indirect or consequential damages, unavailability of plant, plant outage, plant shutdowns or services interruptions, loss of use of equipment or replacement power, costs of capital, loss of profits or revenues or loss of use thereof, arising at any time, whether founded on contract, tort (including negligence), strict liability or otherwise as well as any indirect or consequential losses or damages of any nature.

The limitations under this Article shall not apply for damages which are caused willfully or by gross negligence on the part of SELLER, its subcontractors and all of their directors, officers, agents, servants and employees.

SELLER shall only be liable for damages occurring up to the end of the pertinent Warranty Period if such damages are reported to the SELLER immediately after occurrence or discovery of the damage.

# PROPRIETARY INFORMATION

PURCHASER’s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by PURCHASER in connection with the Scope of Services and Delivery under this Contract shall remain PURCHASER' s property. SELLER agrees not to use or release to any third party such Information except for purposes of performance of SELLER's obligations under the Contract unless prior written consent of the contrary is given by the PURCHASER. With respect to such information being disclosed to a subcontractor of SELLER, SELLER shall cause the subcontractor to execute such undertakings as are necessary to give effect to this provision. SELLER shall give PURCHASER a receipt for property furnished by PURCHASER and shall be responsible for safekeeping and return to PURCHASER upon request, upon termination of the Contract, or upon termination of the services to which such property applies.

SELLER‘s Information

Information such as but not limited to all originals of engineering and related data, plans, maps, drawings, computer programs, and specification furnished in any form by SELLER or its subcontractor in connection with the Scope of Services and Delivery under this Contract shall remain SELLER 's or its subcontractor's proprietary information.

PURCHASER agrees to use such information only for purposes of verification of the design of the Scope of Services and Delivery, for commissioning, operation, testing, analyses, maintenance, and repairs and the installations at Site and the design and execution of any modification therein or extension thereof and agrees to disclose such information to third parties only for obtaining licenses, permits and other official approvals or as required by mandatory law.

In case of disclosure to third parties, PURCHASER shall cause the party to which information is to be provided to execute such undertakings as are necessary to give effect to this provision, save in the case of disclosure to public authorities where PURCHASER shall limit as far as practicable the scope of information so furnished.

The ownership for SELLER's software shall remain with SELLER. SELLER grants the PURCHASER a non-exclusive, non-transferable, personal right to use the software and firmware supplied under the Contract for operation, maintenance and repairing the deliveries of the SELLER under this Contract.

SELLER shall have the right to call for arbitration in the event PURCHASER violates Section 17.2, and also to seek and receive provisional ruling awaiting the valid arbitral decision.

17.3	The provision of this Article 17. shall not apply to Information, notwithstanding any confidential designation thereof, which is known to the receiving Party without any restriction as to disclosure or use at the time it is furnished, which is or becomes generally available to the public without breach of any agreement, or which is received from a third party without limitation or restriction on said third party or to the receiving Party at the time of disclosure.

# 18     CLAIMS

Any claim of a Party to the Contract shall be in writing and shall be justified in detail and shall be immediately submitted by the Party through a letter or fax, to the authorized representative of the other Party and in no event later than thirty (30) days after discovery of basis for such claim. In case the basis of the claim is of such a nature that it requires longer claim submittal period, then this period will be adequately prolonged. The claiming Party will inform the other Party thereof in advance. No claim shall be valid under the Contract if submitted to the other party 30 days after the expiry of the respective warranty period. The Party against whom the claim has been made shall notify the claiming Party of its acceptance or dismissal of the claim within thirty (30) days after the receipt of the claim. If no such notification is received by the claiming Party within the said time, the claim is deemed to have been accepted by the other Party.

All claims shall be resolved satisfactorily within mutually agreed time period.

# 19     ARBITRATION

  - Any differences or disputes arising from or in connection with this Contract shall be settled by an amicable effort on the part of both the Parties to the Contract. An attempt to arrive at a settlement shall be deemed to have failed as soon as one of the Parties to the Contract so notifies the other Party in writing.

  - If an attempt by the parties to arrive at a settlement has failed, any differences or disputes arising out of or in connection with the Contract shall be finally settled in accordance with the Arbitration Rules of the International Chamber of Commerce (Paris) by three arbitrators appointed in accordance with the said Rules.  Any such arbitration shall take place in Zurich (Switzerland) and shall be conducted in the English language. The procedural law of this place shall apply where the Rules are silent.

  - Any arbitral award shall be rendered in writing and be final and binding upon the Parties. To enforce compliance with such arbitration   decision, it may be entered in the appropriate court in either SELLER’s country or Slovenia, assuming the country otherwise has jurisdiction over the Parties. The arbitral tribunals shall decide on the matter of costs of the arbitration.

  - All disputes shall be settled in accordance with the provisions of this Contract. Arbitration under this Article is the sole remedy for disputes arising out of the Contract, its performance or the enforcement thereof.

  - Performance under this Contract shall continue if reasonably possible during any disagreement or court proceeding, and no funds payable to  either Party under the Contract shall be withheld on account of such disagreement or proceeding.

# 20     SUBSTANTIVE LAW

All differences, disputes or claims shall be settled in accordance with the provisions of the Contract, otherwise in accordance with the substantive law in force in Switzerland, without reference to any Swiss conflict of laws and connexity rules incompatible with such choice of law.

# 21     FORCE MAJEURE

21.1	Neither Party to the Contract shall be considered to be in default in the performance of its obligations to the extent that the performance of any such obligation is hindered, prevented or delayed by a Force Majeure circumstance, occurred after entering into the obligations, and which could not be foreseen by the Party in entering into obligations.

21.2	A force majeure circumstance shall mean any circumstance existing which is beyond a Party’s reasonable control and which is not a result of its fault or negligence, including but not limited to: acts of God, such as storm, flood, or earthquake; acts or omissions of civil or military authority,; war (declared or undeclared), acts or omissions of governmental authority, such as quarantine, embargo, priorities of trade, delay or failure to issue Construction Permit; civil disturbances, such as revolution, rebellion, riots, or insurrection; sabotage, transport accident, fuel or energy shortage, or any other circumstances beyond reasonable control of the Party, which may interfere with the commencement or progress of the Scope of Services and Delivery. The deficiency of labor force and/or defects in material and/or strike of local character with SELLER’s suppliers and subcontractors will not be deemed as Force Majeure.

21.3 	Upon the discovery of the occurrence of any such Force Majeure circumstance, the party affected by it shall within thirty (30) days of becoming known notify the other Party thereof, and of its estimated effect, by a registered letter, shall use diligent efforts to eliminate such circumstance and mitigate its effects, and shall keep the other Party fully informed of the progress of its efforts. In the notice of the Force Majeure circumstance, the Party shall indicate the cause of the Force Majeure circumstance, its beginning date and anticipated duration with the confirmation by a competent authority, such as Chamber of Commerce, of the validity of the notice. The affected Party shall also notify in the same way the other Party of the termination of the Force Majeure circumstance. However, this communication is dispensed with if the impact of the conditions of Force Majeure on compliance with the contractual obligations becomes obvious to the other Party in any other way. If the circumstances of Force Majeure also affect the postal routes, the thirty (30) days period for notification shall be deemed to apply only after termination of the obstacles in postal transmission.

21.4	The time for the performance of the obligation of the affected Party shall be extended by a time equal to the duration of the Force Majeure circumstance. Any exceptions to the above shall be mutually agreed upon by the Parties.

21.5	If either Party is prevented from performance of the Contract for a continuous period in excess of three weeks because of Force Majeure either Party may suspend the Scope of Services and Delivery. If furthermore a Force Majeure impediment exceeds one (1) month individually or three (3) months in aggregate due to Force Majeure the Contract may be terminated if both the Parties agree in writing with such decision provided that neither Party is entitled to any profit on the account of the other Party. The termination shall take effect at the date mutually agreed by the Parties. In case the Scope of Services and Delivery is suspended or terminated, the SELLER shall be paid for the Scope of Services and Delivery performed up to the date of suspension or termination.

21.6 	Under Force Majeure circumstances, each Party bears its own costs.

# 22     SUSPENSION OF WORK AND TERMINATION

  - Suspension of Work and Termination of Contract by PURCHASER for Default

PURCHASER shall have the right to suspend the Work or any portion of the Work or to terminate the Contract for material default, which shall include the following:

- Significant discontinuances and disturbances of SELLER in the progress of the Work which seriously delays the Project Time Schedule.

- SELLER’s insolvency or bankruptcy, or other financial inability to carry on the Work.

- Failure on the part of SELLER to observe any material requirements of the Contract (not limited to schedule, quality and technology of work), having a direct consequence on the performance of the Contract.

- Collusion for the purpose of illegally procuring a contract or perpetrating fraud on PURCHASER in the construction of the Work under this Contract.

- SELLER has engaged subcontractors for a part of the Scope of Services and Delivery for which PURCHASER did not provide approval or even rejected them.

PURCHASER shall give SELLER written notice of any default which may be a basis for termination hereunder, and shall provide SELLER the opportunity to cure or institute acceptable action to cure such default in a period not to exceed thirty (30) days from receipt of such notice. Such suspension or termination, if issued, will be by a written order to SELLER whereupon SELLER shall immediately comply therewith.

When the Work is suspended for any of the causes itemized above; or for any other cause or causes constituting a material default of SELLER, SELLER shall discontinue the Work or such part thereof as PURCHASER shall designate. SELLER shall store all the Work in such way that it does not impede or obstruct activities on Site or get damaged or deteriorate. SELLER shall proceed with Work promptly when notified by Purchaser to resume operations. SELLER shall not be entitled to receive payments for additional costs and expenses as consequence of suspension.

In case of termination PURCHASER shall have the power to complete the Work herein described or such part thereof as it may deem necessary at the expense of the SELLER. Such expense shall be deducted by the PURCHASER from any payments due to the SELLER. If there are no payments due, the SELLER shall reimburse the PURCHASER such amounts. SELLER shall store all the Work in such way that it does not impede or obstruct activities on Site or get damaged or deteriorate and PURCHASER shall have the right to take possession of or use the whole or any portion of the Work completed or then in progress and SELLER shall transfer the title of such Work to PURCHASER. SELLER shall be entitled to such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and shall not be entitled to any claim for damages or for loss of anticipated profits.

SELLER shall not suspend Work without written direction by PURCHASER order of a court, or governmental agency and will not be entitled to additional compensation by virtue of such order. Neither will it be liable to PURCHASER in the event the Work is suspended by such order.

  - Suspension of Work and Termination of Contract for Convenience by PURCHASER

The performance of the Work under this Contract may be suspended or terminated by PURCHASER at any time, for its convenience. Any such suspension or termination shall be by submittal to SELLER of a written Notice of Termination, which shall be effective upon receipt.

PURCHASER shall have the authority to suspend the Work wholly or in part for such period or periods as it may deem necessary. For the suspension under this clause SELLER shall be entitled to receive payment for the part of the Works performed up to the date of suspension including all additional costs and expenses demonstrably accruing to SELLER and its subcontractors as consequence of the suspension and shall be entitled to an equitable adjustment of schedule. Should such suspension exceed a maximum period of 12 months, SELLER and PURCHASER shall mutually agree how to proceed. If the agreement is not reached SELLER shall be entitled to terminate the Contract within next six months and be entitled to the reimbursement as stated in article 22.2., 3rd paragraph.  During suspension SELLER shall store all materials in such manner that they will not obstruct or impede activities at the Site unnecessarily nor become damaged in any way, and it shall take every precaution to prevent damage or deterioration of the Work performed. SELLER shall proceed with the Work promptly when notified by PURCHASER to resume operations.

In case of termination, SELLER shall be entitled to 1) such part of the Contract price as reasonably allocable to the Scope of Services and Delivery already executed and to 2) reimbursement of all direct and documented expenses demonstrably incurred, including demobilization costs, in the termination of this Contract and SELLER’s supplies and subcontracting arrangements.

After receipt of a Notice of Termination, and except as otherwise directed by PURCHASER, SELLER shall:

- Stop Work under the Contract on the date specified in the Notice of Termination.

- Place no further orders or subcontracts for materials, services or facilities.

- Terminate all orders and subcontracts.

- Settle all outstanding liabilities and all claims arising out of such termination of orders and subcontracts, with the approval or ratification of PURCHASER to the extent it may require, which approval or ratification shall be final for all purposes of this clause.

- Transfer title to PURCHASER and deliver in the manner, at the times, and to the extent, if any, directed by PURCHASER:

1) 	The fabricated parts, work in process, completed work, supplies, and other material produced as a part of, or acquired in connection with the performance of the Work terminated by the Notice of Termination; and

2) The completed, or partially completed plans, drawings, information, software and other property (except for SELLER proprietary software) which, if the Contract had been completed, would have been required to be furnished to PURCHASER.

- Take such action as may be necessary, or as PURCHASER may direct, for the protection and preservation of the property related to the Contract which is in the possession of SELLER and in which PURCHASER has or may acquire an interest.

At any time after thirty (30) days after the termination date specified in the Notice of Termination, SELLER may submit to PURCHASER a list, certified as to quantity and quality; of any or all items of termination inventory not previously disposed of, exclusive of items the disposition of which has been directed or authorized by PURCHASER, and may request PURCHASER to remove such items or enter into a storage agreement covering them. Not later than fifteen (15) days thereafter, PURCHASER will accept title to such items and remove them or enter into a storage agreement covering the same; provided, that the list submitted shall be subject to verification by PURCHASER upon removal of the items or, if the items are stored, within forty-five (45) days from the date of submission of the list, and any necessary adjustments to correct the list as submitted, shall be made prior to final settlement.

After receipt of a Notice of Termination, SELLER shall submit to PURCHASER his termination claim. Such claim shall be submitted promptly but in no event later than five (5) months from the effective date of termination, unless one or more extensions in writing are granted by PURCHASER upon request of SELLER made in writing with such five (5) months period or authorized extension thereof. Upon failure of SELLER to submit his termination claim within the time allowed, PURCHASER may determine, on the basis of information available to it, the amount, if any, due to SELLER by reason of the termination and shall thereupon pay to SELLER the amount so determined, which shall be the sole amount to which SELLER shall be entitled as a result of such termination.

Nothing contained in this section shall limit or alter the rights which PURCHASER may have for termination of this Contract under the article hereof entitled Suspension of the Work and Termination of Contract by PURCHASER for Default or any other right which PURCHASER may have for default or breach of Contract by SELLER.

  - In case of material breach of the Contract by PURCHASER including but not limited to PURCHASER’s failure to make payment or PURCHASER’s insolvency and if PURCHASER fails to make good such material breach within reasonable time (three months) after having been informed by SELLER in writing of such material breach, SELLER may terminate the Contract. In case of termination, SELLER shall be entitled to receive all payments set forth in article 22.2.,3rd paragraph.

# 23    CHANGES

In case that certain services and supplies are not included in the original Contract, but due to unpredicted circumstances unknown at the time of Contract signature have become necessary for the completion of the Project and without difficulties cannot be performed separately from the Contract, according to the Slovenian Public Tendering Law (Article.95) the Contractor can be invited for negotiation.

SELLER shall, at the PURCHASER’s request, make changes in design or equipment, material or services, not included in the original Contract, but due to unpredicted circumstances unknown at the time of the conclusion of the Contract, if changes in design, equipment, material or services become necessary for the completion of the Project and cannot be performed separately from the Contract without significant difficulties. In such a case the PURCHASER shall invite the SELLER to negotiations by means of a formal letter, while the negotiations shall be subject to the rules provided in this Article.

Any changes to this Contract shall not have any effect until the SELLER and the PURCHASER have agreed on the price to be paid to the SELLER, the delivery or the performance schedule, Quality Assurance conditions and other affected terms and conditions, so as to reflect any changes in 1) SELLER’s efforts which may be required, 2) the scope of work, 3) the time of the performance and the impact on the schedule, 4) the warranties, and 5) the costs to complete.

Upon receipt of the formal letter with the invitation for negotiations, which must include a description of the object of the change and the reasons for such a change, SELLER shall prepare and submit to PURCHASER a proposal for a Change Order in written form, which shall:

a) describe the scope of the proposed change,

b) quote in term of man-hours, rates, prices or otherwise as appropriate, the estimated increase or decrease in the total price that would result from the implementation out of the requested change,

c) specify those terms and conditions which are affected by the change, including time for performance and warranties, and

d) if appropriate, indicate the date on which the SELLER would proceed with the change.

If changes are to be required by any Governmental Agency or Authority, including the United States Nuclear Regulatory Commission, prior to institution of the changes, SELLER and PURCHASER shall agree on the price to be paid to SELLER for the changes. Such a requirement will constitute an obligation for PURCHASER to initiate the new public procurement procedure as required and an equitable adjustment shall be made in the Project schedule.

PURCHASER and SELLER agree that negotiations for change of this Contract shall be considered an independent procedure in which the SELLER may submit reservations with a technically viable justification or other conditions, insofar as they apply only to the object of the change.

In the event negotiations regarding changes requested by PURCHASER do not lead to a Change Order but do have an impact on the schedule, the project schedule will be extended appropriately.

SELLER may propose changes to PURCHASER, but may not implement them without the prior written consent of PURCHASER.

Any changes to this Contract shall be made in writing; the Parties agree that changes in any other form shall be considered void.

In case that subcontractors will be engaged for additional or unforeseen services and hardware supplies the SELLER’s markup percentage shall not exceed: _______ (%). The SELLER will be required to present to PURCHASER copies of Purchase Orders / Agreements (part related to the price) to demonstrate the applied mark-up.

23.1   Change in laws

Any amendment, enforcement or change of interpretation of any Slovenian Government or any other applicable laws, rules, regulations and decrees or other decision and their requirements for compliance as the same shall relate to the Scope of Services and Delivery, whatsoever issued, amended or enforced by any competent authority (including codes and standards and safety regulations) after the date of signature of the Contract is not scope of supply and it may result in the hereabove defined  procedures for Changes or launching of new public procurement.

# 24     ANTI-CORRUPTION CLAUSE

The Contracting Parties shall undertake not to give, promise or receive any present or payment in cash or in any other valuable object to or from each other either directly or indirectly or through any official, officer or any other individual employed in the government or any authority (division, department, agency) or through any political party or any candidate of any political party with the intention of bribing so that any official, officer or any other employee, party or candidate would be tempted to abuse his/her position or to exert influence on any law or any decision made by government or any other competent government department with the purpose to obtain or retain a deal or to direct a deal to a commission agent or to any of his assistants, representatives, distributors, subsidiary companies or any other associated companies. In case the act stated in the previous paragraph has been committed or attempted to be committed, the Contract that had been concluded or had come into force already shall become null and void. In case the Contract is not valid yet, it shall be deemed not to be concluded.

# 25     SOCIAL CLAUSE

During his involvement in this Project, SELLER shall fulfil all applicable obligations in the field of environmental, social and labour laws, as they are set out in the European Union legislation, national legislation, collective agreements or the rules of international environmental, social and labour regulations and if they do not fulfil the above stated obligations the contract will be terminated. Applicable international social and environmental conventions are listed in Attachment X of EU Directive 2014/24/EU and Attachment XIV of EU Directive 2014/25/EU.

# 26     OTHER PROVISIONS

Documentation to be Submitted for SELLER Team

The documents to be submitted to PURCHASER at the latest 30 days before arrival of SELLER's personnel, including his subcontractors at NEK site are as follows:

Documents needed for NEK's cardkey issuance and security vetting:

Based on the NEK Instructions on Security Vetting of Outside Workers attached hereto as part of Attachment E, SELLER shall perform security vetting for his on-site crew.

Additionally, SELLER shall fill in, sign and submit to PURCHASER the following documents attached hereto as Attachment E:

- Request for Entry Card for Outside Worker (6.5-C)

- Written Agreement on Ensuring Collective Occupational Health   and Safety, Fire Protection and Environmental Management

- Statement on complying with Act on Ionizing Radiation Protection and Nuclear Safety (6.3-C)

- Agreement with Security Vetting Procedure (6.1-C) *

- Security Vetting Questionnaire (6.2-C) *

*These documents, completed and signed, should be kept in the personal file

of the worker in SELLER’s company for five years after the service/work

performed at NEK. These forms (including the required attachments) are not

requested to be submitted to PURCHASER but should be available at PURCHASER request.

The security vetting shall be performed by Ministry of the Interior of the Republic of Slovenia in compliance with the provisions of Article 155. of ZVISJV-1 and appendices of ADP-1.8.005, revision 5. The employer sends an application for carrying out a security vetting of his employees to the Ministry of the Interior of the Republic of Slovenia.

Documents needed for work in NEK's radiation controlled area

The documents to be submitted to PURCHASER for the workers who shall perform the activities in NEK's radiation controlled area are as follows:

    - Agreement on Radiological Protection (to be previously provided for signature by NEK)

    - Personal qualification records

    - HP records

    - Medical examination certificate

SELLER shall also, at SELLER's cost, obtain the approval from Slovenian Nuclear Safety Administration (SNSA) at the Ministry of the Environment, Climate and Energy that SELLER has obtained license in his country to work in the radiation controlled area under conditions and in accordance with procedures equivalent to conditions and procedures as required under the Slovenian Act on Ionising Radiation Protection and Nuclear Safety.

For Temporary Supply for Work in Controlled Area all SELLER's supplied equipment or tools will, upon demobilization, either meet Site unrestricted release criteria to be removed by SELLER and returned to SELLER’s facilities or be shipped by SELLER as a radioactive shipment to SELLER’s or to his subcontractor's facility. In no case shall PURCHASER shall keep any equipment or tools as radioactive waste. PURCHASER shall not accept tools/equipment with detected alpha contamination radiologically checked at the Site entrance control.

Equipment will be controlled after decontamination and before shipping.

Equipment should be below the following acceptance limits for utilization on other plants:

| Contamination Bq / cm² | / | Low toxic | Other |
| --- | --- | --- | --- |
| Removable | tbc | 0,4 | 0 |
| Fixed | tbc |  | tbc |

SELLER shall be obliged to use its best efforts to minimize the quantity of wastes generated by SELLER's Scope of Services (consumables, etc.).

Labor Permits and Visas

SELLER shall obtain, at SELLER's cost, Slovenian labor permits and visas required by Slovenian authorities to permit SELLER's personnel to perform the services under this Contract.

Documents needed for the Employment Service of Slovenia (applicable only for field services for Contractors from EU)

In accordance with the Transnational Provision of Services Act (Official Gazette of RS, no. 40/23), the foreign employer from EU is required to register with the Employment Service of Slovenia, before starting to provide services, and provide information about:

1. the company name and seat or the address of the employer;

2. the name and date of birth of the responsible person for the employer;

3. the names, dates of birth and citizenships of the posted workers and the addresses of their residences in the RS;

4. the name and date of birth of the posted worker who will be a liaison between the foreign employer and the competent supervisory bodies, when appropriate;

5. the type of service;

6. the duration of performing the service;

7. the address or the location of providing services;

8. the company name, the name and seat or the address of the client.

A foreign employer from EU is required to ensure that when he posts his workers to the RS, the following documents are kept on the location where the activity is carried out and can be provided for inspection at the request of the supervisory body:

a) a copy of the act of posting or a copy of the contract between the client and the service provider and their translation into Slovenian,

b) a certificate of submitted registration of the provision of services,

c) copy from appropriate register showing company's economic activities with translation into Slovenian,

d) certificate of registering trade in accordance with law regulating trades or certificate of company formation in state of employment with their translation into Slovenian,

e) copies of employment contracts and their translations into Slovenian,

f) copies of payroll lists and their translation into Slovenian,

g) register of presence and its translation into Slovenian,

h) documents in the field of Industrial Safety and their translation into Slovenian,

i) proof of wages paid out or copies of equal documents for all posted workers and their translation into Slovenian, and

j) A1 Forms

Export Control

PURCHASER  agrees not to disclose, transfer, export, or re-export, directly or indirectly, any and all Westinghouse furnished items, including but not limited to Proprietary Information, technology, materials, equipment, spare parts, services, deliverables, training, training materials, software and other export controlled items furnished hereunder, or any direct products or technology resulting therefrom (collectively, “Export Controlled Items”) to any country, or entity, without prior written consent of Westinghouse, which shall not be unreasonably witheld, and only in accordance with applicable export control and sanctions laws and regulations of: the European Union (E.U.), including, EU 2021/821 and EU 833/2014; hereinafter collectively referred to as “Applicable Export Laws and Sanctions Laws”.

Further, the PURCHASER represents and warrants that:

(i)	the PURCHASER not use the Export Controlled Items in any nuclear, chemical, or biological weapons proliferation activities, and

(ii)	the PURCHASER will not disclose Export Controlled Items to any countries for which the E.U. or other applicable governments and international organizations maintain an embargo or to  residents thereof if prohibited by such embargo, and

(iii)	the PURCHASER and its personnel (including its employees,, officers, directors and principal owners): (a) do not appear in any published lists of natural persons and entities whose export or import privileges have been denied or restricted in any way, which are maintained by the governments of the , E.U., , or other applicable countries or international organizations,

The PURCHASER shall fully comply with all such Applicable Export Laws and Sanctions Laws with regard to the Export Controlled Items it receives hereunder and shall cooperate in good faith with the reasonable requests of Westinghouse made for purposes of its compliance with such Applicable Export Laws and Sanctions Laws, including submittal of End Use Certifications as a condition to Westinghouse contract acceptance or performance when required by applicable government authorities. The PURCHASER will insert similar provisions in any agreement it has for the furnishing to third parties or its clients of any Export Controlled Items; provided, however, that the PURCHASER shall be solely responsible for its and such third parties’ and clients’ compliance with applicable requirements of Applicable Export Laws and Sanctions Laws.

Notwithstanding any other provisions in this Purchase Order, the obligations set forth in this Article shall be binding so long as the relevant Applicable Export Laws and Sanctions Laws are in effect.

# 27     ASSIGNMENT

No Party shall assign this Contract in whole or in part without the prior written consent of the other Party, which consent shall not be unreasonably withheld.

# 28     ENTIRE AGREEMENT

The Contract shall constitute the entire and definitive agreement between Parties thereto with respect to the terms and conditions which shall govern. The Contract will supersede all prior written or oral communications between the Parties concerning the subject matter of the Contract which communication upon signature of the Contract by both Parties shall become null and void.

No waiver, alteration or modification of the Contract shall be binding to the Parties unless made in writing and signed by duly authorized representative of the Parties.

# 29    LANGUAGE

SELLER and PURCHASER agree that the official version of the Contract, the Appendices and the Technical Specification shall be in English.

All notices, communications or approvals contemplated hereunder shall be in English.

All Technical Documentation, specifications, drawings, reports specified in the Technical Specification and all other documents referred to by this Contract and any of its constituting part are required to be in English.

All SELLER’s identified personnel shall be capable to communicate in one of the three languages (Slovenian, Croatian or English). Please, be aware that the knowledge of one of these three languages is a prerequisite to attend and pass the General Employee Training as a precondition for working at NEK.

# 30     EFFECTIVE DATE OF CONTRACT

The effective date of the Contract shall be the date of the Contract signature by the Parties as provided on the first page of the Contract.

Despite any conflicting provision contained in this Contract of the applicable Contract documents, the provisions of the following Articles shall survive expiration or termination of this Contract:

Article 15 – Insurance and Indemnity

Article 16 – Liability

Article 17 – Proprietary Information

Article 18 – Claims

Article 19 – Arbitration

Article 20 – Substantive Law

Article 22 – Suspension of Work and Termination

# 31    NOTICES

Any notice pursuant to this Contract shall be deemed to have been duly made

when sent to the following address:

PURCHASER:

Nuklearna Elektrarna Krško

Vrbina 12

8270 Krško, Slovenia

Attention: 	Mr. Robert Planinc, for technical issues

Phone:   00386/7/48-02-148

e-mail: robert.planinc@nek.si

Mrs. Vesna Deak, for commercial issues

Phone:   00386/7/48-02-436

e-mail:  vesna.deak@nek.si

Telefax:  00386/7/4921-528, 4921-006

SELLER:

………………………..

……………………….

……………………….

Attention:         ………………………………….

Phone:  …………..

e-mail:  …………

# 32   ATTACHMENTS

The following Attachments are constituent integral parts of this Document Part I General Terms and Conditions, as listed below, and are attached hereto:

ATTACHMENT A:	Bank Good Performance Guarantee

ATTACHMENT B:    Bank Guarantee for Good Performance during

Warranty Period

ATTACHMENT C: 	Handover Protocol on Successful Completion of

the Project

ATTACHMENT  D:	Subcontractor’s Data and SELLER’s Consent for Direct Payment

ATTACHMENT  E:   Documentation to be filled in, signed and  provided by			                     	           SELLER  for its and its  subcontractors on-site Team

ATTACHMENT F:    Statement of received payment for subcontractor's part

of services, delivery or/and civil works (if applicable

For SELLER

For PURCHASER:

Nuklearna Elektrarna Krško d.o.o.

Saša Medaković			             Gorazd Pfeifer

Member of the Management Board                President of the Management Board

## ATTACHMENT A

BANK GOOD PERFORMANCE GUARANTEE (draft)

Date: ……..

Name and address of the Beneficiary

TYPE OF GUARANTEE: Performance Guarantee

GUARANTEE NO.: …………………..

THE GUARANTOR: ……………..

THE APPLICANT: ……………

THE BENEFICIARY: …………………

THE UNDERLYING RELATIONSHIP: The Applicant’s obligation in respect of the Contract

No. …….. dated ………….concluded between Beneficiary and the Applicant, with which the Applicant is obliged to perform the Project ..…………. at a total price of EUR ……….... According to the conditions of the above mentioned Contract, a Performance Guarantee in the amount of ……% of the total Contractual price,

i.e. EUR ……….., is required.

GUARANTEE AMOUNT AND CURRENCY: ………………………EUR

(in words:  .………………./100 Euros)

ANY DOCUMENT REQUIRED IN SUPPORT OF THE DEMAND FOR PAYMENT, APART FROM THE SUPPORTING STATEMENT THAT IS EXPLICITLY REQUIRED IN THE TEXT BELOW: none

LANGUAGE OF ANY REQUIRED DOCUMENTS: English

FORM OF PRESENTATION: paper presentation only by registered mail or any courier service.

For the purpose of identification, Beneficiary’s demand for payment has to be presented through Beneficiary’s business bank, confirming the Beneficiary’s signature(-s) in demand for payment appear to conform to specimen(s) held in Beneficiary’s Bank’s records.

PLACE OF PRESENTATION:

EXPIRY: ……………….

As Guarantor, we hereby irrevocably undertake to pay the Beneficiary upon receipt by us of his first written demand, any amount up to the Guarantee Amount upon presentation of the Beneficiary’s complying demand, in the form of presentation indicated above, supported by such other documents as may be listed above and in any event by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, indicating in what respect the Applicant is in breach of its obligations under the Underlying Relationship.

The Guarantor will effect payment at sight without delay and not later than fifteen (15) days from the receipt of Beneficiary's first written request as set out above.

Any demand under this Guarantee must be received by us on or before Expiry at the Place for presentation indicated above.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758.

## ATTACHMENT B

BANK GUARANTEE FOR GOOD PERFORMANCE

DURING WARRANTY PERIOD (draft)

Date: ……..

Name and address of the Beneficiary

TYPE OF GUARANTEE: Warranty Guarantee

GUARANTEE NO.: …………………..

THE GUARANTOR: ……………..

THE APPLICANT: ……………

THE BENEFICIARY: …………………

THE UNDERLYING RELATIONSHIP: The Applicant’s obligation during warranty period in respect of the Contract  No. …….. dated ………….concluded between Beneficiary and the Applicant for the Project …….………..at a total price of EUR ………...

According to the Conditions of the above Contract a Warranty Guarantee in the amount of ……% of the total contractual price, i.e. EUR ……….., is required.

GUARANTEE AMOUNT AND CURRENCY: EUR ……….

(in words: Euro .………………./100)

ANY DOCUMENT REQUIRED IN SUPPORT OF THE DEMAND FOR PAYMENT, APART FROM THE SUPPORTING STATEMENT THAT IS EXPLICITLY REQUIRED IN THE TEXT BELOW: none

FORM OF PRESENTATION: Paper presentation only by registered mail or any courier service. The demand must be presented through the intermediary of your bank confirming that your signature(s) on your demand for payment appear to conform to specimen(s) held in your bank’s records.

PLACE FOR PRESENTATION: ………

EXPIRY: ………………. (The Guarantee shall be valid from the date of issuance of this Guarantee till 30 days after the end of the Warranty period as stated in the Contract, Art. 12.3.)

The Guarantee shall be valid from the date of issuance of this Guarantee till  30th day after the end of the Warranty period as stated in the Contract.

As Guarantor, we hereby irrevocably undertake to pay the Beneficiary upon receipt by us of his first written demand, any amount up to the Guarantee Amount upon presentation of the Beneficiary’s complying demand, in the form of presentation indicated above, supported by such other documents as may be listed above and in any event by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, indicating in what respect the Applicant is in breach of its obligations under the Underlying Relationship.

Beneficiary’s statement must state, that the Applicant after the receipt of request to make good a deficiency in the warranty period under the Underlying Relationship, hasn’t fulfilled his contractual warranty obligations under the Underlying relationship.

The Guarantor will effect payment at sight without delay and not later than fifteen (15) days from the receipt of Beneficiary's first written demand as set out above.

Any demand under this Guarantee must be received by us on or before Expiry at the Place for presentation indicated above.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758.

## ATTACHMENT C

## HANDOVER PROTOCOL

ON SUCCESSFUL COMPLETION

of

Reactor Cavity Manipulator Crane Upgrade Project

(Mod. 1302-FH-L)

We hereby certify that the Project “Reactor Cavity Manipulator Crane Upgrade, Mod. 1302-FH-L” has been successfully completed fully in line with the scope, schedule, delivery time and other terms and conditions stipulated in the Contract No. ………………….  and is operationally and functionally satisfying the requirements as stated in NEK Technical Specification No. SP-ES1454, Rev.2

The list of all open Project deficiencies reports of category C and D is attached hereto.

The list of remaining non-installed items of hardware with relevant technical/QA documentation and part numbers and other details necessary for warehouse acceptance which shall be moved to PURCHASER’s warehouse with the transfer of Title and Risk of Loss is attached to this Protocol.

All the requirements as stated in Art. 9 of the Contract No. ……………… have been met. The date on which the warranty period commences is the date  this  Handover Protocol is signed by both Parties.

Date: 	                                                                           Date:

For SELLER						For PURCHASER

## ATTACHMENT  D

Subcontractor’s Data and SELLER’s Consent for Direct Payment

Bidder………………………………………………………………………………………………

We declare that we will engage below stated subcontractor for the part of the Scope of Services and Delivery under the Contract for

……………………………………………………………………………………………………

Name and head office: ……………………………………………………………………………………………..

TAX number: ………………………………………………………………………………………………………

Registration number: ………………………………………………………………………………………………

IBAN: …………………………………………………….…………………………………………………

Statutory representative: ……………………………………………………….……………………………..…

Scope of Services and Delivery to be performed by subcontractor: .………………………………………………………………………………………………………

Value of the services and delivery to be performed by subcontractor:

…………………………………………without VAT………….…………………….. with VAT

Place of performance of work: ……………………………………………………………………….…………………..………

Deadline for performance of work: ……………………………………………………………………………………………………

We declare to be engaged in above stated Scope of Services and Delivery performance as subcontractor to the SELLER.

Please indicate your option:

- We request to be paid directly by Purchaser at our account number, for our part of performed scope of Services and Delivery based on the invoice approved by the SELLER.

- We do not request to be paid directly by Purchaser and therefore we declare that we are informed that no later than 60 days after signing the hand over protocol we and the SELLER need to submit the Statement Att.11 of this Bidding Documentation to Purchaser that we have been reimbursed for the performed services, delivery and/or civil works

With signature of this statement we declare the fulfillment of the following conditions:

- subcontractor fulfills all the conditions requested with this Bidding Documentation for his part of the work, delivery or civil works.

We authorize the Purchaser to acquire the necessary data for this public procurement process, which will confirm the fulfillment of the above conditions.

Place and date: 			Stamp: 		      Bidder’s Signature:

________________		                                                  __________________

Subcontractor’s Signature

## ATTACHMENT  E

Documentation to be filled in, signed  and  provided (except

form 6.1-C & 6.2-C) by SELLER  for its and its subcontractors

on-site team:

- Instructions on Security Vetting of Outside Workers for Unescorted Access to and Work at Krško NPP, and on Obtaining the Entry Card

- Request for Entry Card for Outside Worker (6.5-C)

- Written Agreement on Ensuring Collective Occupational Health

and Safety, Fire Protection and Environmental Management

- Agreement on Radiological Protection

- Statement on complying with Act on Ionizing Radiation Protection

and Nuclear Safety (6.3-C)

- Agreement with Security Vetting Procedure (6.1-C)

- Security Vetting Questionnaire (6.2-C)

## ATTACHMENT F

STATEMENT OF RECEIVED PAYMENT FOR SUBCONTRACTOR'S PART OF SERVICES, DELIVERY OR/AND CIVIL WORKS (if applicable)

CONTRACTOR:__________________________________________

and

SUBCONTRACTOR:                   ______________________________

hereby declare that the Subcontractor stated above has received all payments

due for his part of the services, delivery and/or civil works under the Contract

No._______________

for the _________________________________.

(subject of the public tender)

Place and Date: 		  Stamp:    	 		 Bidder’s Signature:

Subcontractor’s Signature:

In accordance with article 94.6 of ZJN-3, the Purchaser shall receive this statement in 60 days after the main Contractor issues the final invoice.